## Instructions
Rev. 04/25
Project Audit Template |  |  |  |  | Districts | Area Offices | County
This Audit template is formatted to align with the numbering system of the Project File Index Folder Structure. |  |  |  |  | Abilene | Abilene | Anderson | Yes | CPM | Five-Day Workweek
[5 empty] | Amarillo | Alice | Andrews | No | Bar | Six-Day Workweek
| Per CCAM Chapter 4, Section 4, all project records are required to be reviewed to verify project compliance with federal regulations (as applicable) and performance of work according to plans and specifications. Audits will be performed by the District Construction Office and based on a set schedule. Interim audit will be performed 6 months from when time starts, annually, and at Final. |  |  |  | Atlanta | Alpine | Angelina | N/A |  | Seven-Day Workweek
[5 empty] | Austin | Amarillo | Aransas | Complete |  | Standard Workweek
[5 empty] | Beaumont | Athens | Archer | Incomplete |  | Calendar Day
[5 empty] | Brownwood | Bastrop | Armstrong | Requested |  | Other
[5 empty] | Bryan | Beaumont | Atascosa |  |  | Restricted Work Hours
| Time Start Date: |  | Make copies of green tab "Annual (Blank)" by right clicking on the sheet below and select Move or Copy; once created, rename the new copy as YYYYMMDD Annual |  | Childress | Bell County | Austin |  |  | Nighttime Work
6 month Initial Due: |  |  |  |  | Corpus Christi | Bexar Metro | Bailey |  |  | Five, Six, and Seven-Day Workweeks
Annual Due: |  |  |  |  | Dallas | Big Spring | Bandera |  |  | Nighttime Work Only
| continue annual audits until Final |  |  |  | El Paso | Brazoria | Bastrop |  |  | Nighttime Work and Daytime Work Requiring Inspector
[5 empty] | Fort Worth | Brenham | Baylor
| The day to day activity of the construction project records is the responsibility of the assigned Area Office and project staff. Self audits and reviews can be completed by the Area Office using the Line Item Review Form. During monthly estimate processing, review all pay quantities are accurate. It is highly recommended for the Area Office to use this Audit template as a tool prior to the scheduled audit. |  |  |  | Houston | Brownfield | Bee
[5 empty] | Laredo | Brownwood | Bell
[5 empty] | Lubbock | Bryan | Bexar
[5 empty] | Lufkin | Burnet | Blanco
[5 empty] | Odessa | Carrizo Springs | Borden
[5 empty] | Paris | Childress | Bosque
[5 empty] | Pharr | Collin County | Bowie
| Once an audit is completed by the District Construction Office, ensure to complete the following: |  |  |  | San Angelo | Corpus Christi | Brazoria
| (save the Excel file as a working copy at the DCO level) |  |  |  | San Antonio | Del Rio | Brazos
| 1 | Save as a PDF to add signatures |  |  | Tyler | Denton County | Brewster
| 2 | DCO forward a copy to AE so discrepancies can be addressed (make any updates to PDF doc) |  |  | Waco | Dewitt County | Briscoe
| 3 | AO save Audit and supporting correspondence to project folder 2.8 Audits and Reviews |  |  | Wichita Falls | Dumas | Brooks
[5 empty] | Yoakum | East Dallas County | Brown
[6 empty] | East El Paso | Burleson
[6 empty] | Eastland | Burnet
| Additional Resources: |  |  |  |  | Erath County | Caldwell
| PROJECT RECORDS CHECKLIST |  |  |  |  | Euless | Calhoun
| Chapter 6 – Control of Materials Section 2 – Materials Testing page 6-8 for the Project Records Checklist |  |  |  |  | Fort Bend | Callahan
[6 empty] | Fort Stockton | Cameron
[6 empty] | Gainesville | Camp
[6 empty] | Galveston | Carson
| Project File Index & Item History Review form can be found on the Record Keeper Development page |  |  |  |  | Gatesville | Cass
| Recordkeeper Development Program (state.tx.us) |  |  |  |  | Georgetown | Castro
[6 empty] | Graham | Chambers
[6 empty] | Greenville | Cherokee
[6 empty] | Hillsboro | Childress
[6 empty] | Hondo/Pleasanton | Clay
[6 empty] | Huntsville | Cochran
[6 empty] | Johnson County | Coke
[6 empty] | Junction | Coleman
[6 empty] | Karnes City | Collin
[6 empty] | Kaufamn/Rockwall | Collingsworth
[6 empty] | Kerrville | Colorado
[6 empty] | Laredo | Comal
[6 empty] | Liberty | Comanche
[6 empty] | Littlefield | Concho
[6 empty] | Livingston | Cooke
[6 empty] | Longview | Coryell
[6 empty] | Lubbock | Cottle
[6 empty] | Lufkin | Crane
[6 empty] | Marshall | Crockett
[6 empty] | McLennan County | Crosby
[6 empty] | Midland | Culberson
[6 empty] | Mineola | Dallam
[6 empty] | Montgomery | Dallas
[6 empty] | Mount Pleasant | Dawson
[6 empty] | Munday | Deaf Smith
[6 empty] | Nacogdoches | Delta
[6 empty] | North Bexar | Denton
[6 empty] | North Harris | DeWitt
[6 empty] | North Travis | Dickens
[6 empty] | Navarro/Ellis County | Dimmit
[6 empty] | New Braunfels | Donley
[6 empty] | Odessa | Duval
[6 empty] | Orange | Eastland
[6 empty] | Pampa | Ector
[6 empty] | Paris | Edwards
[6 empty] | Parker County | Ellis
[6 empty] | Pecos | El Paso
[6 empty] | Pharr | Erath
[6 empty] | Plainview | Falls
[6 empty] | Pleasanton/Pearsll | Fannin
[6 empty] | Roma | Fayette
[6 empty] | South Tarrent County | Fisher
[6 empty] | South Travis | Floyd
[6 empty] | San Angelo | Foard
[6 empty] | San Benito | Fort Bend
[6 empty] | Southeast Harris | Franklin
[6 empty] | Sherman | Freestone
[6 empty] | Sinton | Frio
[6 empty] | Snyder | Gaines
[6 empty] | Sulphur Springs | Galvestion
[6 empty] | Texarkana | Garza
[6 empty] | Tyler | Gillespie
[6 empty] | Victoria | Glasscock
[6 empty] | West El Paso | Goliad
[6 empty] | West/Central Harris | Gonzales
[6 empty] | Wharton | Gray
[6 empty] | Wichita Falls | Grayson
[6 empty] | Wise County | Gregg
[6 empty] | Traffic Operations | Grimes
[6 empty] | Dist Maintenance | Guadalupe
[6 empty] | Dist Traffic | Hale
Hall
Hamilton
Hansford
Hardeman
Hardin
Harris
Harrison
Hartley
Haskel
Hays
Hemphill
Henderson
Hidalgo
Hill
Hockley
Hood
Hopkins
Houston
Howard
Hudspeth
Hunt
Hutchinson
Irion
Jack
Jackson
Jasper
Jeff Davis
Jefferson
Jim Hogg
Jim Wells
Johnson
Jones
Karnes
Kaufman
Kendall
Kenedy
Kent
Kerr
Kimble
King
Kinney
Kleberg
Knox
Lamar
Lamb
Lampasas
La Salle
Lavaca
Lee
Leon
Liberty
Limestone
Lipscomb
Live Oak
Llano
Loving
Lubbock
Lynn
Madison
Marion
Martin
Mason
Matagorda
Maverick
McCulloch
McLennan
McMullen
Medina
Menard
Midland
Milam
Mills
Mitchell
Montague
Montgomery
Moore
Morris
Motley
Nacogdoches
Navarro
Newton
Nolan
Nueces
Ochiltree
Oldham
Orange
Palo Pinto
Panola
Parker
Parmer
Pecos
Polk
Potter
Presidio
Rains
Randall
Reagan
Real
Red River
Reeves
Refugio
Roberts
Robertson
Rockwall
Runnels
Rusk
Sabine
San Augustine
San Jacinto
San Patricio
San Saba
Schleicher
Scurry
Shackelford
Shelby
Sherman
Smith
Somervell
Starr
Stephens
Sterling
Stonewall
Sutton
Swisher
Tarrant
Taylor
Terrell
Terry
Throckmorton
Titus
Tom Green
Travis
Trinity
Tyler
Upshur
Upton
Uvalde
Val Verde
Van Zandt
Victoria
Walker
Waller
Ward
Washington
Webb
Wharton
Wheeler
Wichita
Wilbarger
Willacy
Williamson
Wilson
Winkler
Wise
Wood
Yoakum
Young
Zapata
Zavala

## Interim
Interim
CSJ: |  |  |  | Project: |  |  | Highway: |  |  | County:
District: |  |  |  | Area Office: |  |  | Audited by: |  |  | Date:
1 | INDEX and CONTRACT DOCUMENTS
1.1 | Contract Plans on file?
1.1 | Contract Proposal on file?
1.1 | Contract Addendums on file?
1.1 | Bid Tabs on file?
1.1 | Award Letter on file?
Date of Award:
1.1 | Authorization to Begin Work (ABW) & Contract on file?
Date of ABW:
Is Contract signed?
1.1 | Does project have any Advance Funding Agreements (AFA)?
If yes, list the party below and date of agreement.
|  | Name: |  |  |  |  | Date of Agreement:
|  | Name: |  |  |  |  | Date of Agreement:
|  | Name: |  |  |  |  | Date of Agreement:
1.1 | Pre-Bid Q&A on file?
Was a Pre-Bid Conference held?
If yes, list date held (ensure documents on file to support).
1.2 | Prime Contractor 2795-Contractor Staff Designee on file?
| Has there been any modification to the 2795? |  |  |  |  | If yes, list latest update date:
(modifications or updates to Form 2795 may be submitted in email format)
1.3 | Number of APPROVED Subcontractors for Project?
Is Form 2802 on file for all subcontractors?
Are there any unapproved Subcontractors at this time?
If yes, document the name and brief reason why the subcontractor is currently not approved.
|  | Name: |  |  |  |  | Reason:
|  | Name: |  |  |  |  | Reason:
|  | Name: |  |  |  |  | Reason:
Was prime notified of all Subcontractor Approvals?
How many Non DBE subcontracts reviewed?
Were all DBE subcontractors entered into the DMS system?
Were any discrepancies identified, addressed and resolved?
1.4 | Certifications on file as required for (*flaggers-only if requested during audit):
| Flaggers? |  |  |  | Electricians? |  |  |  | Irrigators?
| Profilers? |  |  |  | Welders?
1.5 | Equipment on file if applicable:
| Haul truck measurements? |  |  |  |  | Water truck measurements?
| Equipment OTHER? | [5 empty] | TMA documentation?
Spray Bar Calibrations received?
Asph Distributor Tank Volume Calibrations (may require multiple)?
Overload truck permits?
1.6 | Has the project identified any Utility or ROW management action plans?
If yes, have all deficiencies been addressed and documented?
Have all parties, including the contactor been notified of clearance?
Comments:
2 | CONTRACT ADMINISTRATION
2.1 | TIME-How are working days charged (calendar day, working day, etc.) for the contract?
Has the Contract Time Statement Report been reviewed?
Are time entries in accordance with the contract?
| Original Bid Days: |  |  |  | Added Days: |  |  | Days charged to date:
Has the project been in Time Suspension?
If yes, is all documentation on file to justify the date(s)?
Does the project have any MILESTONES?
How are working days charged for the milestone?
2.2 | Are 10% of payrolls reviewed by the AO?
| Number of reviews completed? | [5 empty] | Were discrepancies noted and addressed?
| Number of Labor Interviews required to date (3 per quarter)? | [5 empty] | Number of Labor Interviews completed?
2.3 | Number of DBE subcontractors and suppliers identified within DMS?
| Number of CUF's completed? |  |  |  | Were CUF discrepancies noted, addressed and resolved?
Were all DBE subcontracts received?
Were all DBE subcontract discrepancies noted, addressed and resolved?
Were any DBE purchase orders received?
Were any DBE purchase order discrepancies noted, addressed and resolved?
| DBE goal? |  | % |  | Any issues identified with project goal compliance?
Is OJT identified for the project?
2.4 | Number of Prompt Pay forms required to date? | [5 empty] | Number of Prompt Pay forms on file?
| Number of Quarterly Prompt Pay Audits completed to date? | [5 empty] | Have all entries been made in SM?
2.5 | Number of Bulletin Board Checklist completed? |  |  |  |  | Were discrepancies noted and addressed?
2.7 | Does project have any Railroad Agreements (if applicable): | [6 empty] | RR included?
| Is ROE agreement on file? |  |  |  |  | If applicable, RR insurance date of expiration?
Does project have TDLR requirements?
Does project require Plans & Approvals for Construction Equipment/Materials on Structures?
Comments:
3 | ENVIRONMENTAL
3.1 | Date of initial 2448?
Does the SWP3 contain all attachments in accordance with Department policy?
| Review SWP3 Guidance |  |  | SWP3 Binder Resources
Do all attachments contain correct information per the guidance manual?
Are SWP3 mark-up sheets being kept up-to-date in the SWP3 binder?
Date of first 2118?
Are 2118's completed in accordance with project's schedule?
Are 2118's signed by authorized TxDOT personnel?
Is a copy of the NOI in the SWP3 binder (5 acres or more disturbed)?
Comments:
4 | ESTIMATES
4.1 | ESTIMATES-Generate estimates monthly when time charges begin and continue until the final estimate/payment is generated (including zero dollar estimates)
Has an estimate been generated for each month since the time start begin date?
| Number of estimates on file? |  |  |  |  | Are all estimates signed?
Any negative estimates processed for the project?
If yes, was Finance notified and is documentation on file?
Comments:
5 | CHANGE ORDERS
5.1 | Change Orders-All Correspondence and Approved or Unapproved COs (CCAM Ch 4 and the Change Order SOP dated January 2022)
| Current number of COs? |  |  |  |  | Approved COs? |  |  | Unapproved COs?
Is 2146 (or District equivalent) completed for each CO?
Comments:
6 | DOCUMENTATION
6.1 | A 10% audit of pay items is required utilizing the Tableau Report found on this link. | [7 empty] | 10% Item Review
Follow the instructions to generate the report based on the audit schedule and attach a PDF copy of the items reviewed to this document. Notate any discrepancies found in the comments section below.
6.2 | Has the Material Sourcing Letter been Received? | [5 empty] | Date of letter?
Has Sampling and Testing Checklist been reviewed for Project?
Are the Mix Designs for project on file and approved? Date:
Is a 3rd party Lab being used for the project?
If yes, date or estimate payment was processed?
Contractor testing Employee and Lab Certifications (if applicable)?
Quality Control Plans on file?
6.3 | Preliminary Schedule on file? |  |  |  |  | Type of schedule?
(due 7 days prior to pre-con unless otherwise agreed; note date received)
Baseline Schedule received and reviewed?
(due 45 calendar days from work start unless otherwise agreed)
Monthly Progress Updates on file?
| Number of monthly progress schedules required to date? | [6 empty] | Number on file?
6.5 | Date Preconstruction Meeting was held?
Is there a complete packet of the Form 2796 and all attachments on file?
Was a copy sent to all attendees?
Has project had any pre-placement meeting(s)?
If yes, please list description and date meeting held below (ensure minutes are in the project records).
Are field project progress meetings held for the project?
If yes, ensure meeting minutes, notes and sign in sheets are properly dated and filed in project records.
6.6 | Have any shop drawings been submitted for the project?
| Number Received? |  |  |  | Number Approved?
Does project have any demolition plans?
| Number Received? |  |  |  | Number Approved?
Comments:
Additional Items to Review during Audit:
DWRs - Ensure there is at least one DWR and project diary entry for each day from when contractor began work date or the date working day charges begin, whichever is first.
First DWR Date?
Are there any unauthorized DWRs to date?
| DAY Reports required to date? | [5 empty] | DAY Reports on file?
| NIGHT Reports required to date? |  |  |  |  | NIGHT Reports on file?
Are dates properly entered in Checklist Event Dates in SM?
Additional AUDIT Comments:
All discrepancies should be reviewed and addressed within 30 days of notification or finding.
Reviewer Signature: | [5 empty] | Completed Date:

## Annual (Blank)
Annual | [10 empty] | Use this blank copy to create a new template each year by right clicking on the sheet tab below and select Move or Copy, select create a copy; once created, rename the new copy as YYYYMMDD Annual
CSJ: |  |  |  | Project: |  |  | Highway: |  |  | County:
District: |  |  |  | Area Office: |  |  | Audited by: |  |  | Date:
1 | INDEX and CONTRACT DOCUMENTS
1.1 | Does project have any NEW Advance Funding Agreements (AFAs)?
If yes, list the party below and date of agreement.
|  | Name: |  |  |  |  | Date of Agreement:
|  | Name: |  |  |  |  | Date of Agreement:
|  | Name: |  |  |  |  | Date of Agreement:
1.2 | Has there been any modification to the 2795? |  |  |  |  | If yes, list latest update date:
(modifications or updates to Form 2795 may be submitted in email format)
1.3 | Number of APPROVED Subcontractors for Project?
Is Form 2802 on file for all subcontractors?
Are there any unapproved Subcontractors at this time?
If yes, document the name and brief reason why the subcontractor is currently not approved.
|  | Name: |  |  |  |  | Reason:
|  | Name: |  |  |  |  | Reason:
|  | Name: |  |  |  |  | Reason:
Was prime notified of all Subcontractor Approvals?
How many Non DBE subcontracts reviewed?
Were all DBE subcontractors entered into the DMS system?
Were any discrepancies identified, addressed and resolved?
1.4 | Certifications on file as required for (*flaggers-only if requested during audit):
| Flaggers (*)? |  |  |  | Electricians? |  |  |  | Irrigators?
| Profilers? |  |  |  | Welders?
1.5 | Equipment on file if applicable:
| Haul truck measurements? |  |  |  |  | Water truck measurements?
| Equipment OTHER? | [5 empty] | TMA documentation?
Spray Bar Calibrations received?
Asph Distributor Tank Volume Calibrations (may require multiple)?
Overload truck permits?
1.6 | Has the project identified any Utility or ROW management action plans?
If yes, have all deficiencies been addressed and documented?
Have all parties, including the contactor been notified of clearance?
Comments:
2 | CONTRACT ADMINISTRATION
2.1 | TIME-How are working days charged (calendar day, working day, etc.) for the contract?
Has the Contract Time Statement Report been reviewed?
Are time entries in accordance with the contract?
| Original Bid Days: |  |  |  | Added Days: |  |  | Days charged to date:
Has the project been in Time Suspension?
If yes, is all documentation on file to justify the date(s)?
Does the project have any MILESTONES?
How are working days charged for the milestone?
2.2 | Are 10% of payrolls reviewed by the AO?
| Number of reviews completed? | [5 empty] | Were discrepancies noted and addressed?
| Number of Labor Interviews required to date (3 per quarter)? | [5 empty] | Number of Labor Interviews completed?
2.3 | Number of DBE subcontractors and suppliers identified within DMS?
| Number of CUFs completed? |  |  |  | Were CUF discrepancies noted, addressed and resolved?
Were all DBE subcontracts received?
Were all DBE subcontract discrepancies noted, addressed and resolved?
Were any DBE purchase orders received?
Were any DBE purchase order discrepancies noted, addressed and resolved?
| DBE goal? |  | % |  | Any issues identified with project goal compliance?
Is OJT identified for the project?
2.4 | Number of Prompt Pay forms required to date? | [5 empty] | Number of Prompt Pay forms on file?
| Number of Quarterly Prompt Pay Audits completed to date? | [5 empty] | Have all entries been made in SM?
2.5 | Number of Bulletin Board Checklist completed? |  |  |  |  | Were discrepancies noted and addressed?
| Does project have any Railroad Agreements (if applicable): | [6 empty] | RR included?
| Is ROE agreement on file? |  |  |  |  | If applicable, RR insurance date of expiration?
Does project have TDLR requirements?
Does project require Plans & Approvals for Construction Equipment/Materials on Structures?
Comments:
3 | ENVIRONMENTAL
3.1 | Date of Initial 2448
Date of Annual 2448
Does the SWP3 contain all attachments in accordance with Department policy?
| Review SWP3 Guidance |  |  | SWP3 Binder Resources
Do all attachments contain correct information per the guidance manual?
Are SWP3 mark-up sheets being kept up-to-date in the SWP3 binder?
Date of first 2118?
Are 2118's completed in accordance with project's schedule?
Are 2118's signed by authorized TxDOT personnel?
Comments:
4 | ESTIMATES
4.1 | ESTIMATES-Generate estimates monthly when time charges begin and continue until the final estimate/payment is generated (including zero dollar estimates)
Has an estimate been generated for each month since the time start begin date?
| Number of estimates on file? |  |  |  |  | Are all estimates signed?
Any negative estimates processed for the project?
If yes, was Finance notified and is documentation on file?
Comments:
5 | CHANGE ORDERS
5.1 | Change Orders-All Correspondence and Approved or Unapproved COs (CCAM Ch 4 and the Change Order SOP dated January 2022)
| Current number of COs? |  |  |  |  | Approved COs? |  |  | Unapproved COs?
Is 2146 (or District equivalent) completed for each CO?
Comments:
6 | DOCUMENTATION
6.1 | A 10% audit of pay items is required utilizing the Tableau Report found on this link. | [7 empty] | 10% Item Review
Follow the instructions to generate the report based on the audit schedule and attach a PDF copy of the items reviewed to this document. Notate any discrepancies found in the comments section below.
6.2 | Has the Material Sourcing Letter been received? | [5 empty] | Date of letter?
Has Sampling and Testing Checklist been reviewed for Project?
Are the Mix Designs for project on file and approved?
Is a 3rd party Lab being used for the project?
If yes, date or estimate payment was processed?
Contractor testing Employee and Lab Certifications (if applicable)?
Quality Control Plans on file?
6.3 | Preliminary Schedule on file? |  |  |  |  | Type of schedule?
(due 7 days prior to pre-con unless otherwise agreed; note date received)
Baseline Schedule received and reviewed?
(due 45 calendar days from work start unless otherwise agreed)
Monthly Progress Updates on file?
| Number of monthly progress schedules required to date? | [6 empty] | Number on file?
6.5 | Date Preconstruction Meeting was held?
Is there a complete packet of the Form 2796 and all attachments on file?
Was a copy sent to all attendees?
Has project had any pre-placement meeting(s)?
If yes, please list description and date meeting held below (ensure minutes are in the project records).
Are field project progress meetings held for the project?
If yes, ensure meeting minutes, notes and sign in sheets are properly dated and filed in project records.
6.6 | Have any shop drawings been submitted for the project?
| Number Received? |  |  |  | Number Approved?
Does project have any demolition plans?
| Number Received? |  |  |  | Number Approved?
Comments:
Additional Items to Review during Audit:
DWRs - Ensure there is at least one DWR and project diary entry for each day from when contractor began work date or the date working day charges begin, whichever is first.
First DWR Date?
Are there any unauthorized DWRs to date?
| DAY Reports required to date? | [5 empty] | DAY Reports on file?
| NIGHT Reports required to date? |  |  |  |  | NIGHT Reports on file?
Are dates properly entered in Checklist Event Dates in SM?
Additional AUDIT Comments:
All discrepancies should be reviewed and addressed within 30 days of notification or finding.
Reviewer Signature: | [5 empty] | Completed Date:

## Final
FINAL
CSJ: |  |  |  | Project: |  |  | Highway: |  |  | County:
District: |  |  |  | Area Office: |  |  | Audited by: |  |  | Date:
1 | INDEX and CONTRACT DOCUMENTS
1.1 | Does project have any NEW Advance Funding Agreements (AFAs)?
If yes, list the party below and date of agreement.
|  | Name: |  |  |  |  | Date of Agreement:
|  | Name: |  |  |  |  | Date of Agreement:
|  | Name: |  |  |  |  | Date of Agreement:
1.2 | Has there been any modification to the 2795? |  |  |  |  | If yes, list latest update date:
(modifications or updates to form 2795 may be submitted in email format)
1.3 | Number of APPROVED Subcontractors for Project?
Is Form 2802 on file for all subcontractors?
Are there any unapproved Subcontractors at this time?
If yes, document the name and brief reason why the subcontractor is currently not approved.
|  | Name: |  |  |  |  | Reason:
|  | Name: |  |  |  |  | Reason:
|  | Name: |  |  |  |  | Reason:
Was prime notified of all Subcontractor Approvals?
How many Non DBE subcontracts reviewed?
Were all DBE subcontractors entered into DMS system?
Were any discrepancies identified, addressed and resolved?
1.4 | Any additional certifications on file as required (*flaggers-only if requested during audit):
If yes, please identify the added certifications:
1.5 | Equipment-any NEW equipment verification documentation needed?
Review Project Records Checklist & Item Specifications; ensure documentation is in project records.
1.6 | Has the project identified any Utility or ROW management action plans?
If yes, have all deficiencies been addressed and documented?
Have all parties, including the contactor been notified of clearance?
Comments:
2 | CONTRACT ADMINISTRATION
2.1 | TIME-How are working days charged (calendar day, working day, etc.) for the contract?
Has the Contract Time Statement Report been reviewed?
Are time entries in accordance with the contract?
| Original Bid Days: |  |  |  | Added Days: |  |  | Days charged to date:
Has the project been in Time Suspension?
If yes, is all documentation on file to justify the date(s)?
Does the project have any MILESTONES?
How are working days charged for the milestone?
| Are all milestones complete? |  |  |  | Have incentive/disincentives been applied?
2.2 | Are 10% of payrolls reviewed by the AO?
| Number of reviews completed? | [5 empty] | Were discrepancies noted and addressed?
| Number of Labor Interviews required to date (3 per quarter)? | [5 empty] | Number of Labor Interviews completed?
2.3 | DBE goal? |  | % | DBE goal paid to date?
Any issues identified with project goal compliance?
Any NEW DBE subcontractors or material suppliers been added to project?
If yes, has subcontract documents been submitted and reviewed?
Have all CUFs been completed?
Is OJT identified for the project?
2.4 | Number of Prompt Pay forms required to date?
Number of Prompt Pay forms on file?
Any Prompt Pay discrepancies identified?
If yes, have discrepancies been noted, addressed and resolved?
Any subcontractor nonpayment notices reviewed for valid disputes?
If yes, is documentation on file to support contract compliance?
| Number of Quarterly Prompt Pay Audits completed to date? | [5 empty] | Have all entries been made in SM?
Is the Final Prompt Pay on file?
2.5 | Number of Bulletin Board Checklist completed? |  |  |  |  | Were discrepancies noted and addressed?
2.7 | Does project have any Railroad Agreements (if applicable): | [6 empty] | RR included?
| Is ROE agreement on file? |  |  |  |  | If applicable, RR insurance date of expiration?
Comments:
3 | ENVIRONMENTAL
3.1 | Date of Initial 2448
Date of Annual 2448
Were all 2448's completed as required?
Does the SWP3 contain all attachments in accordance with Department policy?
| Review SWP3 Guidance |  |  | SWP3 Binder Resources
Do all attachments contain final, updated information per the guidance manual?
Are SWP3 mark-up sheets in the SWP3 binder?
Are 2118's finalized and included in the SWP3 binder?
Are 2118's signed by authorized TxDOT personnel?
Is a copy of the NOT in the SWP3 binder (5 acres or more disturbed)?
Comments:
4 | ESTIMATES
4.1 | ESTIMATES-Generate estimates monthly when time charges begin and continue until the final estimate/payment is generated (including zero dollar estimates)
Has an estimate been generated for each month?
| Number of estimates on file? |  |  |  |  | Are all estimates signed?
Any negative estimates processed for the project?
If yes, was Finance notified and is documentation on file?
Comments:
5 | CHANGE ORDERS
5.1 | Change Orders-All Correspondence and Approved or Unapproved COs (CCAM Ch 4 and the Change Order SOP dated January 2022)
| Current number of COs? |  |  |  |  | Approved COs? |  |  | Unapproved COs?
Is 2146 (or District equivalent) completed for each CO?
Comments:
6 | DOCUMENTATION
6.1 | A 10% audit of pay items is required utilizing the Tableau Report found on this link. | [7 empty] | 10% Item Review
Follow the instructions to generate the report based on the audit schedule and attach a PDF copy of the items reviewed to this document. Notate any discrepancies found in the comments section below.
6.2 | Has the Material Sourcing Letter been updated? | [5 empty] | Date of letter?
Has Sampling and Testing Checklist been reviewed for any items added by Change Order?
6.3 | Schedules - Monthly Progress Updates on file?
| Number of monthly progress schedules required to date? | [6 empty] | Number on file?
6.5 | Has project had any pre-placement meeting(s)?
If yes, please list description and date meeting held below (ensure minutes are in the project records).
Are field project progress meetings held for the project?
If yes, ensure meeting minutes, notes and sign in sheets are properly dated and filed in project records.
6.6 | Have any shop drawings been submitted for the project?
| Number Received? |  |  |  | Number Approved?
Does project have any demolition plans?
| Number Received? |  |  |  | Number Approved?
Comments:
Additional Items to Review during Audit:
DWR's - Ensure there is at least one DWR and project diary entry for each day from when contractor began work date or the date working day charges begin, whichever is first.
Has a DWR been completed for each day?
Are there any unauthorized DWRs to date?
| DAY Reports required to date? | [5 empty] | DAY Reports on file?
| NIGHT Reports required to date? |  |  |  |  | NIGHT Reports on file?
Are dates properly entered in Checklist Event Dates in SM?
Contractor Evaluation - Documented in accordance with contract documents?
Number of evaluations required?
Number of evaluations performed?
Additional AUDIT Comments:
Reviewer Signature: | [5 empty] | Completed Date:

## Closeout Checklist
Project Closeout Checklist
Project Event List - A chronological list of all the major events on the project.
Checklist Events
Critical Dates
Key Dates
Preconstruction Contract Correspondence
Contract
Advanced Funding Agreement (AFA)
Bid Tabulation
Utility or ROW Conflicts
New utility account connections and to disconnect for each project.
Railroad Right of Entry (ROE)
Railroad Insurance Information
TDLR Inspections
Preconstruction Meeting, Notes, Sign-In Sheets, etc.
Partnering Meeting, Invoice, etc.
Preconstruction Safety meeting Notes
DBE/SBE Subcontractors
Subcontract Agreements
Purchase Orders
Monthly /Final Payouts (DMS reporting)
Completed CUFs
Goal Shortfall explanations and analysis if applicable
Subcontract Approval
Subcontract Agreements (Form 2802 Contractor Request for Sub Approval for projects let May 2020)
Monthly/Final Prompt Pay Certification
Prompt Pay Audits (Form 2177A)
Project Schedule
Baseline Schedule
Monthly Updates
Notice of Potential Time Impact
Time Impact Analysis
Materials
Sources
Materials Lists
Tickets
Materials Tests Documentation/Deficiencies
Product Data Sheets
Requests for Material on Hand (MOH)
Materials Invoices
Lab Invoices
Testing Employee and Lab Certifications
Manufacturers Literature
Mix Designs
Certified Test Reports
Quality Control Plans
Joint Density Test Results
Seed Mix Certifications
Construction
Bulletin Board Checklists
Asphalt Pavement Records
Seal Coat Records
Asphalt
Aggregate
ACP Records
Ride Quality Measurement Records
Concrete Pavement Paving and Quality Control Plan
Flowable Fill Construction Method and Plan
Temporary Shoring Details
Pile Driving Correction Plans
Pile Jetting Plans
Pile Bearing Evaluation Documentation
Pile Driving Records and updated Bridge Layouts showing actual foundation elevations, provide to the district bridge office to be included in the bridge file in the bridge inspection management system (currently AssetWise)
Soil Nail Wall Construction Plans
Drilled Shaft Installation Plan
Drill Shaft Records and updated Bridge Layouts showing actual foundation tip elevations, provide to the district bridge office to be included in the bridge file in the bridge inspection management system (currently AssetWise)
Freeze Protection Measures
Plans for Falsework and Forms
Bridge Paint Containment Plans
Special Concrete Finish Plans
Work Plans
Technical Support Representatives
Welding Procedures
Certificate of Conformance
Shop Drawings/Working Drawings
Erection Drawings
Nonconformance Reports
Demolition Plans
SW3P Training List
Herbicide Records
Equipment Verifications
DWRs - Make sure all DWRs in SiteManager have been authorized.
Monthly Estimates
Check Percentage of Work Performed by Prime and Subs
Check Major Items for Over/Underrun Greater than 25%
Change Orders, Force Account, etc. - All Correspondence and Approved or Unapproved COs
Dispute Correspondence, Requests for additional compensation, etc., Approvals, Denials
Traffic Control Plans, Revisions, Contractor Proposed Changes, etc.
Paper copies of FORM 599, “TRAFFIC CONTROL DEVICES INSPECTION REPORT” - Barricade Folder includes all 599s required for both day and night inspections each month Barricade Folder includes all 599s performed
The 599 folder is separate from the project files, labeled with “DO NOT DISCLOSE - EXCEPTED FROM DISCLOSURE BY 23 USC §407.” This file is considered safety information that federal law exempts from discovery, which makes them exempt from disclosure under the Public Information Act.
Environmental Compliance
SW3P Documentation
BMPs
Construction Stage Gate Checklist
Other Environmental Commitment documentation as required.
Buy America/Buy Texas Documentation
Overweight Construction Traffic Submittals and Approvals
Construction Equipment Operating on Structures or Materials Stored on Structures Plans and Approvals
Employee Certifications
Flaggers (if requested)
Electricians
Irrigators
Profilers
Labor Compliance
Payroll hard copies (Form WH-347) if not submitted to the Engineer in the manner prescribed by the Department.
Labor Interviews
OJT
Incident and Injury Reporting (for projects let before September 2020 in which SP 000-010 was not removed by change order
Check EPRS to ensure contractor has submitted incidents and injuries that have occurred on the project. These should correspond to information in the DWRs.
Other Correspondence
Press Release (if applicable)
Disposal of Wells Plugging Report
As Built Plans
Statement of Cost (SOC's) (if applicable)
Final hard copy Contractor Performance Evaluation Form 2707, Form 2707R and complete backup documentation saved in a folder separate from the project files, labeled "DO NOT DISCLOSE - Attorney General Opinion Required."
Form 2803 Project Evaluation (Design) - Required for all FINAL Estimates processed after NOV 2022
District Project Audit(s) (Performed by DCO)