## MAIN INDEX OVERVIEW
Tab 1 - MAIN INDEX OVERVIEW - Overall brief view of Project Folder Setup.
Tab 2 - INDEX - Detailed folder descriptions, naming convention and a search option.
Tab 3 - SEARCH - Single key word search option.
1 | INDEX and CONTRACT DOCUMENTS
| 1.1 | Contract Etc.
| 1.2 | Prime Contractor
| 1.3 | Subcontractors
| 1.4 | Certifications
| 1.5 | Equipment
| 1.6 | ROW and Utilities
2 | CONTRACT ADMINISTRATION
| 2.1 | Project Time
| 2.2 | Labor Compliance
| 2.3 | DBE SBE OJT
| 2.4 | Prompt Pay
| 2.5 | Bulletin Board Checklist
| 2.6 | Lane Closures
| 2.7 | General Correspondence
| 2.8 | Audits and Reviews
3 | ENVIRONMENTAL
4 | ESTIMATES
5 | CHANGE ORDERS
6 | PROJECT DOCUMENTATION
| 6.1 | Pay Item Support
| 6.2 | Materials
| 6.3 | Schedules
| 6.4 | RFI
| 6.5 | Meetings
| 6.6 | Shop Drawings
7 | FINAL PROJECT DOCUMENTATION

## INDEX Details-Naming Convention
PROJECT FILE INDEX
CSJ:
PROJECT:
CONTRACTOR:
KEY WORD SEARCH:
type in key word and press ENTER, scroll through document to find highlighted folder
BOLD Underline - FOLDER NAME or Suggested Naming Convention - Italics (and parenthesis) - brief description, guidance and information
1 INDEX and CONTRACT DOCUMENTS
|  | 1.1 | Contract Etc.
xxxCSJxxx Plans County- project plans
xxxCSJxxx Proposal County - project proposal
xxxCSJxxx Proposal Addendumns County - project proposal addendumns
xxxCSJxxx Bid Tabs - bid tabs can be pulled from TxDOT.gov
xxxCSJxxx YYYYMMDD Award - Award Letter-for naming convention use date of award letter received from CST; date of letter is identical to SiteManager AWARD DATE
xxxCSJxxx YYYYMMDD ABW Contract - Authorization to Begin Work Letter & Contract-for naming convention use date of letter received from CST; date of letter is identical to SiteManager NOTICE TO PROCEED DATE
xxxCSJxxx AFA "Entity Name" - Advanced Funding Agreement(s) identify "Entity Name"; create sub folders for additional Entity(s) as needed; include copy of AFA, Amendment(s) or any additional correspondence as needed
Default or Termination - correspondence (intent & default letters); surety take over agreement
Pre-Bid Q and A
|  | 1.2 | Prime Contractor
xxxCSJxxx YYYYMMDD Form2795 - Form 2795 Contractor Staff Designation-use date of contractor signature for file name; this file is originally submitted at pre-con and is also part of the pre-con packet; any updates to the contractor staff designee's can be done with an email - save any updates using the date of new submittal
|  | 1.3 | Subcontractors - create sub folders as needed; use SM 3 digit subcontractor number which will match the SM Subcontractor Summary Report
SUB 001 "NAME" - identify if DBE after subcontractor name, i.e. SUB 001 JD Construction-DBE; include any other documentation as needed i.e. district checklist
xxxCSJxxx Sub 001 "Name-" Form2802 - Form 2802 Subcontractor Request for Approval- required for all subcontractors working on the project; including CSJ in file name assist when sharing documents within area office, district and division
xxxCSJxxx Sub 001 "Name" Contract - Fully executed contract with required special provisions between Prime and Subcontractor - required for all DBE subcontractors and one NON-DBE per project; see CCAM Chapter 10, Section 3
SUB 002 "NAME" - identify if DBE after subcontractor name, i.e. SUB 001 JD Construction-DBE; include any other documentation as needed i.e. district checklist
xxxCSJxxx Sub 002 "Name-" Form2802 - Form 2802 Subcontractor Request for Approval- required for all subcontractors working on the project; including CSJ in file name assist when sharing documents within area office, district and division
xxxCSJxxx Sub 002 "Name" Contract - Fully executed contract with required special provisions between Prime and Subcontractor - all DBE subcontracts are required to be on file and one NON-DBE per project; see CCAM Chapter 10, Section 3
|  | 1.4 | Certifications - identify by contractor using sub folders if applicable; i.e. Electricians, Welders, ACI Shotcrete Nozzleman, Mobile Retroreflectivity Operartor; JD Construction-Electrician
|  | 1.5 | Equipment - identify by prime or subcontractor using sub folders if needed; may require multiple; review contract specifications for requirements
Contractor - Haul Truck Measurements
Contractor - Water Truck Measurements
Contractor - Equipment OTHER
Contractor - Distribution Calibrations
Contractor - Asph Distributor Tank Volume Calibrations (may require multiple)
Contractor - Overload Permits
|  | 1.6 | ROW and Utilities - create subfoldres as need for all ROW and Utility correspondence
2 CONTRACT ADMINISTRATION
|  | 2.1 | Project Time
YYYYMMDD WBL - Work Begin Memo/Letter to DCO-CCAM Chapter 4, Section 4; notification of date contractor's work will begin; date of work begin is identical to SM WORK BEGIN DATE
YYYYMMDD TC "Request-Issue" - Time Credit Resquest-identify "Issue"; for naming convention use date of request
YYYYMMDD TC "Approval-Issue" - Time Credit Approval-identify "Issue"; for naming convention use date of approval
YYYYMMDD TR "Issue" - Time Resumption Letter-identify "Issue"; contractor must be notified in writing of date when time charges will resume on a project
xxxCSJxxx YYYYMMDD ACN - Anticipated Completion Notice to DCO - triggers DCO final inspections and other reviews if applicable
xxxCSJxxx YYYYMMDD AOA - Area Office Acceptance-when AE accepts and send acceptance notification to DCO and/or contractor; SiteManager Diary Charge = WORK ACCEPTED (letter to contractor is optional)
xxxCSJxxx YYYYMMDD FinalAcceptance - Project Final Acceptance-when DCO accepts the project; written notification to Contractor of project acceptance date; SiteManager Diary Charge = WORK COMPL & ACCEP; date is identical to SM ACCEPTED DATE
|  | 2.2 | Labor Compliance
Labor Interviews
YYYYMM Employee Name-Contractor Name - 3 labor interviews required per quarter; name by year and month interview was performed, employee name and contractor name
Additional Wage Rate Request
|  | 2.3 | DBE SBE OJT - create sub folders as applicable; DBE and OJT is documented in the DMS-Diversity Management System; use folder for filing any DBE, SBE, OJT documentation and correspondence as needed (good faith effort, CUF)
|  | 2.4 | Prompt Pay
xxxCSJxxx YYYYMM PP - Monthly Form 2177 submitted by contractor
xxxCSJxxx YYYYMM Final PP - Final Prompt Pay Report-use year and month report was submitted
xxxCSJxxx YYYYMM Qrtly PP Audit - Quarterly Audits- Form 2177A, minimum of one audit per quarter per project; quarter based on calendar year starting Jan 1st
|  | 2.5 | Bulletin Board Checklist
|  | 2.6 | Lane Closures
xxxCSJxxx YYYYMMDD LCR - Lane Closure Request (use date of request)
|  | 2.7 | General Correspondence
YYYYMMDD GC "SUBJECT" - any correspondence in date order; identify by SUBJECT; create sub folders if needed i.e. Default if applicable, School District, Letter of Concern, Bond Inquiry Status Request, Speed Reduction Minute Orders, pictures not related to pay items
YYYYMMDD Railroad "Description" - railroad documentation or correspdence; invoice, billing, executed ROE if applicable
YYYYMMDD TLDR "Description" - TDLR documentation or correspondence; request for final inspection and related if applicable
|  | 2.8 | Audits and Reviews - general project review, audit correspondence and supporting documentation; identify as appropriate
xxxCSJxxx YYYYMMDD AO Review - Area Office Review, name as 30, 60, 90
xxxCSJxxx YYYYMMDD DCO Audit - DCO Audits (if applicable)
xxxCSJxxx YYYYMMDD FHWA Audit - FHWA Audits (if applicable)
| 3 ENVIRONMENTAL |  |  |  | 3 ENVIRONMENTAL
|  | 3.1 | Environmental |  |  | 3.1 | Environmental
|  |  | Stage Gate |  |  |  | Stage Gate
|  |  |  | xxxCSJxxx YYYYMMDD Stge Chklst - Stage Gate Checklist Report (use date of report) |  |  |  | xxxCSJxxx YYYYMMDD Stge Chklst - Stage Gate Checklist Report (use date of report)
|  |  | SWP3 Binder and Attachments +1 Acre |  |  |  | SWP3 Binder and Attachments -1 Acre
|  |  |  | Section 1 Plan Sheets |  |  |  | Section 1 Plan Sheets
|  |  |  | 1.1 SWP3 Summary Sheets |  |  |  | 1.1 SWP3 Summary Sheets
|  |  |  | 1.1 SWP3 Summary Sheets xxxCSJxxx |  |  |  | 1.1 SWP3 Summary Sheets xxxCSJxxx
|  |  |  | 1.2 Location Map and Layouts |  |  |  | 1.2 Location Map and Layouts
|  |  |  | 1.2 Location Map xxxCSJxxx |  |  |  | 1.2 Location Map xxxCSJxxx
|  |  |  | 1.2 Environmental Mark Up Sheets xxxCSJxxx |  |  |  | 1.2 Environmental Mark Up Sheets xxxCSJxxx
|  |  |  | 1.3 Sed Basin Cal |  |  |  | Section 2 SWP3 Binder Attachments
|  |  |  | 1.3 Sediment Basin/Trap Cover Sheet |  |  |  | 2.3 Inspection Records
|  |  |  | 1.3 Sediment Basin/Trap Calcs |  |  |  | 2.3 Form 2118 Month 1 xxxCSJxxx
|  |  |  | 1.3 Sediment Basin/Trap Design |  |  |  | 2.3 Weekly Inspecition YYYYMMDD xxxCSJxxx
|  |  |  | Section 2 SWP3 Binder Attachments |  |  |  | 2.3 Weekly Inspecition YYYYMMDD xxxCSJxxx
|  |  |  | 2.1 TxDOT CSN NOI NOC NOT |  |  |  | 2.3 Form 2118 Month 2 xxxCSJxxx
|  |  |  | 2.1 TxDOT CSN xxxCSJxxx |  |  |  | 2.3 Weekly Inspecition YYYYMMDD xxxCSJxxx
|  |  |  | 2.1 TxDOT NOI xxxCSJxxx |  |  |  | 2.3 Weekly Inspecition YYYYMMDD xxxCSJxxx
|  |  |  | 2.1 TxDOT NOC xxxCSJxxx |  |  |  | 2.3b Dewatering Inspection Records
|  |  |  | 2.1 TxDOT NOT xxxCSJxxx |  |  |  | 2.3b Form xxxx Event 1 xxxCSJxxx
|  |  |  | 2.2 Contractor CSN NOI NOC NOT |  |  |  | 2.3b Contractor Dewatering Plan YYYYMMDD xxxCSJxxx
|  |  |  | 2.2 Contractor CSN xxxCSJxxx |  |  |  | 2.3b Daily Inspecition YYYYMMDD xxxCSJxxx
|  |  |  | 2.2 Contractor NOI xxxCSJxxx |  |  |  | 2.3b Daily Inspecition YYYYMMDD xxxCSJxxx
|  |  |  | 2.2 Contractor NOC xxxCSJxxx |  |  |  | 2.4 Inspector Qualification
|  |  |  | 2.2 Contractor NOT xxxCSJxxx |  |  |  | 2.4 Inspector 1 xxxCSJxxx
|  |  |  | 2.3 TxDOT MS4 Notification |  |  |  | 2.4 Inspector 2 xxxCSJxxx
|  |  |  | 2.3 TxDOT MS4 Notification List (from Word Template) xxxCSJxxx |  |  |  | 2.4 Inspector 3 xxxCSJxxx
|  |  |  | 2.3 TxDOT MS4 Notification Transmittal Letter xxxCSJxxx |  |  |  | 2.5 TxDOT Federal, State, and Local Compliance Documentation
|  |  |  | 2.4 Contractor MS4 Notification |  |  |  | 2.5 Cover Sheet (from Word Template) xxxCSJxxx
|  |  |  | 2.4 Contractor MS4 Notification List (from Word Template) xxxCSJxxx |  |  |  | 2.5 EPIC Sheet xxxCSJxxx
|  |  |  | 2.4 Contractor MS4 Notification Proof xxxCSJxxx |  |  |  | 2.5 Permit 1 xxxCSJxxx
|  |  |  | 2.5 Inspection Records |  |  |  | 2.5 Permit 2 xxxCSJxxx
|  |  |  | 2.5 Form 2118 Year 1 xxxCSJxxx |  |  |  | 2.6 Contractor Federal, State, and Local Compliance Documentation
|  |  |  | 2.5 Weekly Inspecition YYYYMMDD xxxCSJxxx |  |  |  | 2.6 Cover Sheet (from Word Template) xxxCSJxxx
|  |  |  | 2.5 Weekly Inspecition YYYYMMDD xxxCSJxxx |  |  |  | 2.6 PSL Diagram xxxCSJxxx
|  |  |  | 2.5 Form 2118 Year 2 xxxCSJxxx |  |  |  | 2.6 Batch Plant Permit xxxCSJxxx
2.5 Weekly Inspecition YYYYMMDD xxxCSJxxx
2.5 Weekly Inspecition YYYYMMDD xxxCSJxxx
2.5b Dewatering Inspection Records
2.5b Form xxxx Event 1 xxxCSJxxx
2.5b Contractor Dewatering Plan YYYYMMDD xxxCSJxxx
2.5b Daily Inspecition YYYYMMDD xxxCSJxxx
2.5b Daily Inspecition YYYYMMDD xxxCSJxxx
2.5b Form xxxx Event 2 xxxCSJxxx
2.5b Contractor Dewatering Plan YYYYMMDD xxxCSJxxx
2.5b Daily Inspection Date YYYYMMDD xxxCSJxxx
2.6 Inspector Qualification
2.6 Inspector 1 xxxCSJxxx
2.6 Inspector 2 xxxCSJxxx
2.6 Inspector 3 xxxCSJxxx
2.7 Delegation of Signature Authority Memo xxxCSJxxx
2.8 SWP3 Revision Log xxxCSJxxx
2.9 TxDOT Federal, State, and Local Compliance Documentation
2.9 Cover Sheet (from Word Template) xxxCSJxxx
2.9 EPIC Sheet xxxCSJxxx
2.9 Permit 1 xxxCSJxxx
2.9 Permit 2 xxxCSJxxx
2.10 Contractor Federal, State, and Local Compliance Documentation
2.10 Cover Sheet (from Word Template) xxxCSJxxx
2.10 PSL Diagram xxxCSJxxx
2.10 Batch Plant Permit xxxCSJxxx
2.11 Part III.A.1.c. Shared SWP3 Statement xxxCSJxxx
2.12 Copy of CGP xxxCSJxxx
4 ESTIMATES
Estimates (create one PDF packet of the estimate package to include supporting docuemtnation or create sub folders for each month using "YYYYMM")
xxxCSJxxx YYYYMM-Est01 - Monthly Progress Estimates (MM is the estimate month period)
xxxCSJxxx YYYYMM-Est02 - Monthly Progress Estimates (MM is the estimate month period)
5 CHANGE ORDERS
Change Orders - create sub folders for each change order; use two digit change order number for naming convention
CO 01
DIS_xxxCSJxxx_CO#01 - Complete copy of CO & supporting docs-include 3 digit district number (DIS) to assist with CST change order reviews (All Change Orders should include documentation of the following: form 2146 or equivalent, concurrance of reason code, federal participation, funding category, signed force account form 316, envirionmental clearance and form 1295 if applicable)
DIS_xxxCSJxxx_CO#01 Plan Sheets - final approved additional plan sheets if applicable
YYYYMMDD CO#01 "subject" - any and all Change Order working documents
CO 02 - follow same format used for CO 01 folder
DIS_xxxCSJxxx_CO#02 - Complete copy of CO & supporting docs-include 3 digit district number (DIS) to assist with CST change order reviews (All Change Orders should include documentation of the following: form 2146 or equivalent, concurrance of reason code, federal participation, funding category, signed force account form 316, envirionmental clearance and form 1295 if applicable)
DIS_xxxCSJxxx_CO#02 Plan Sheets - final approved additional plan sheets if applicable
YYYYMMDD CO#02 "subject" - any and all Change Order working documents
6 PROJECT DOCUMENTATION
|  | 6.1 | Pay Item Support - create sub folders for line numbers as needed; refer to Project Records Checklist for additional guidance
0060 "Line Item Description"
YYYYMMDD Line60 Calc Sheet - identify each file as a Pay Report/Drawing/Calculation/ Pictures/ Invoice/Material Verification/Tickets, etc.; use date of placement; date should match DWR date; matching dates will assist with audit trail
YYYYMMDD Line60 ConcTickets
0065 "Line Item Description"
YYYYMMDD Line65 Calc Sheet - identify each file as a Pay Report/Drawing/Calculation/ Pictures/ Invoice/Material Verification/Tickets, etc.; use date of placement; date should match DWR date; matching dates will assist with audit trail
YYYYMMDD Line65 ConcTickets
|  | 6.2 | Materials
xxxCSJxxx YYYYMMDD Sampling Checklist - Original Sampling Checklist at activation
xxxCSJxxx YYYYMMDD MSL - Material Sourcing Letter (may include several updates)
YYYYMMDD MD "MATERIAL" - Mix Designs correspondence if any; mix designs information is kept in SiteManager
Concrete Records
Testing Equipment Calibrations (if applicable)
Cylinder Log
Cylinder Pad Log
Bulk Material Verification Documents
Description-Vendor - for items that have high quantities of material verification documentation/invoices, combine all by creating sub folders as needed; using naming convention of description and vendor or supplier; i.e. Rebar-CMC Steel, RCP-Rinker
Form 2806 - If SP included in contract, Form 2806 must be on file as applicable; create sub folders as needed
|  | 6.3 | Schedules
YYYYMMDD Prelim Schedule - Preliminary Schedule (use schedule data date or date of submission)
YYYYMMDD Baseline - Baseline Schedule
YYYYMMDD Baseline Review - TxDOT Review/Baseline Checklist
YYYYMMDD Baseline Acceptance - Baseline Acceptance by TxDOT
YYYYMMDD TIA Notice - Notice of Potential Time Impact (create sub folders to organize any correspondence for TIA as needed)
YYYYMM JAN Update - use YYYYMMDD naming convention or create sub folders for each month; include monthly updates from contractor, TxDOT review, acceptance and any additional correspondence
YYYYMM Update - Progress Schedules
YYYYMM Review - CPM Review for Monthly Schedule Update
YYYYMM Acceptance - Progress Schedule Acceptance
|  | 6.4 | RFI - REQUEST FOR INFORMATION
YYYYMMDD RFI "Description" - create sub folders as needed by description and/or date of request
|  | 6.5 | Meetings - create sub folders if needed; pre-con, weekly, pre-placement
xxxCSJxxx YYYYMMDD Pre Con - Pre Construction Meeting agenda and supporting documentation FORM2796, other attachments include FORM2390, 2391, 2795 (use date of meeting for file name)
YYYYMMDD Meeting Minutes - Project Status Meeting Minutes-weekly, bi-weekly, monthly (use date of meeting for file name)
xxxCSJxxx YYYYMMDD "type" - Pre Placement Meeting - Hot Mix, Concrete Pavements,etc; can be single document or create sub folders as applicable
|  | 6.6 | Shop Drawings
Item Name - create sub folders as needed; use description of item for naming convention
7 FINAL DOCUMENTATION
a place in the project records to capture all of the Final Project Documents and/or reports. Items with * are required
| * | 1-xxxCSJxxx Final Plan Set
| * | 2-xxxCSJxxx Final DBE Report (copy, if applicable)
| * | 3-xxxCSJxxx Final Prompt Pay Report (copy)
| * | 4-xxxCSJxxx Final Estimate
| * | 5-xxxCSJxxx Material Certification Letter (include copy of email to MTD)
| * | 6-xxxCSJxxx Test Exception Letter (if applicable)
| * | 7-xxxCSJxxx Statement of Cost (if applicable)
| * | 8-xxxCSJxxx Legislative Letters (may be more than one)
| * | 9-xxxCSJxxx 2803 Project Evaluation (required starting November 2022)
Additional - Recommended - Good Practice to keep in this file
10-xxxCSJxxx Final Time Summary Report
11-xxxCSJxxx Change Order Summary Report
12-xxxCSJxxx Contract Line Item Report
13-xxxCSJxxx Overrun & Underrun
14-xxxCSJxxx Unpaid Installed Work Report (3% mob payment)
15-xxxCSJxxx Unauthorized Daily Work Report
16-xxxCSJxxx Failing Samples Report
17-xxxCSJxxx Final Sampling Checklist Report
18-xxxCSJxxx Xite Report (showing 0 deficiencies or items that coincide with test exception ltr)

## SEARCH
Enter search word above to filter folders. Delete entry to start new search.
FOLDER | DESCRIPTION | FOLDER | DESCRIPTION
#NAME? | #NAME? | 1 | CONTRACT DOCUMENTS
#NAME? | #NAME? | 1.1 | Contract Etc.
#NAME? | #NAME? | 1.1 | Plans
#NAME? | #NAME? | 1.1 | Proposal & Addendumns
#NAME? | #NAME? | 1.1 | Bid Tabs
#NAME? | #NAME? | 1.1 | Award
#NAME? | #NAME? | 1.1 | Authorization to Begin Work, ABW & Contract
#NAME? | #NAME? | 1.1 | AFA's Advance Funding Agreement
#NAME? | #NAME? | 1.1 | Pre-Bid Q&A
#NAME? | #NAME? | 1.1 | Default and/or Termination
#NAME? | #NAME? | 1.1 | Intent Letter
#NAME? | #NAME? | 1.1 | Default Letter
#NAME? | #NAME? | 1.2 | Prime Contractor 2795-Contractor Staff Designation
#NAME? | #NAME? | 1.3 | Subcontractors 2802 - Request for Subcontractor Approval
#NAME? | #NAME? | 1.4 | Certifications
#NAME? | #NAME? | 1.5 | Equipment - Water Truck, Haul Truck, Asphalt Distributor, Overload Permits
#NAME? | #NAME? | 1.6 | ROW, Utilities
#NAME? | #NAME? | 2 | CONTRACT ADMINISTRATION
#NAME? | #NAME? | 2.1 | Project Time
#NAME? | #NAME? | 2.1 | Work Begin Memo/Letter
#NAME? | #NAME? | 2.1 | Time Credit Day(s) Request Letter, Time Suspension
#NAME? | #NAME? | 2.1 | Time Credit Day(s) Approval Letter, Time Suspension
#NAME? | #NAME? | 2.1 | Time Charges Resume Letter
#NAME? | #NAME? | 2.1 | ACN Anticipated Completion Notice Memo
#NAME? | #NAME? | 2.1 | AOA Area Office Acceptance Letter
#NAME? | #NAME? | 2.1 | Final Acceptance Letter
#NAME? | #NAME? | 2.2 | Labor Compliance - Payrolls
#NAME? | #NAME? | 2.2 | Labor Interviews
#NAME? | #NAME? | 2.2 | Additional Wage Rate Request
#NAME? | #NAME? | 2.3 | DBE SBE OJT
#NAME? | #NAME? | 2.4 | Prompt Pay, prompt pay quarterly audit
#NAME? | #NAME? | 2.5 | Bulletin Board Checklist
#NAME? | #NAME? | 2.6 | Lane Closures
#NAME? | #NAME? | 2.7 | General Correspondence
#NAME? | #NAME? | 2.7 | TDLR
#NAME? | #NAME? | 2.7 | Railroad (Inv/billing; exectuted ROE)
#NAME? | #NAME? | 2.8 | AUDITS, Reviews - AO, DCO, FHWA
#NAME? | #NAME? | 3.1 | ENVIRONMENTAL
#NAME? | #NAME? | 3.1 | Stage Gate
#NAME? | #NAME? | 3.1 | SW3P
#NAME? | #NAME? | 3.1 | NOI, NOT
#NAME? | #NAME? | 3.1 | MS4
#NAME? | #NAME? | 3.1 | Form 2118
#NAME? | #NAME? | 4 | ESTIMATES
#NAME? | #NAME? | 5 | CHANGE ORDERS
#NAME? | #NAME? | 5 | Form 2146
#NAME? | #NAME? | 6 | PROJECT DOCUMENTATION
#NAME? | #NAME? | 6.1 | Pay Item Support (drawings, invoices, tickets, buy America, testing)
#NAME? | #NAME? | 6.1 | Material On Hand, MOH (file with associated MOH line number folder)
#NAME? | #NAME? | 6.1 | Invoices (file with associated line number folder)
#NAME? | #NAME? | 6.1 | Tickets (file with line number concrete, hot mix etc)
#NAME? | #NAME? | 6.2 | MATERIALS
#NAME? | #NAME? | 6.2 | sampling checklist (correspondence)
#NAME? | #NAME? | 6.2 | MPL Material Sourcing Letter (correspondence)
#NAME? | #NAME? | 6.2 | mix designs (correspondence)
#NAME? | #NAME? | 6.2 | concrete records (cyclinder logs)
#NAME? | #NAME? | 6.2 | Material Invoice (sub folders if needed)
#NAME? | #NAME? | 6.2 | Material Verfication Documentation (bulk-file invoice in sub folder by producer, vendor or type)
#NAME? | #NAME? | 6.2 | Form 2806 (BABA)
#NAME? | #NAME? | 6.3 | Schedules
#NAME? | #NAME? | 6.4 | RFI
#NAME? | #NAME? | 6.5 | Meetings (pre construction, weekly, pre-placement)
#NAME? | #NAME? | 6.6 | Shop Drawings
#NAME? | #NAME? | 7 | FINAL PROJECT DOCUMENTATION (* required)
#NAME? | #NAME? | 7 | *Final Plan Set
#NAME? | #NAME? | 7 | *Final DBE Report (copy)
#NAME? | #NAME? | 7 | *Final Prompt Pay Report (copy)
#NAME? | #NAME? | 7 | *Final Estimate
#NAME? | #NAME? | 7 | *Material Certification Letter (email copy to MTD)
#NAME? | #NAME? | 7 | *Test Exception Letter (if applicable)
#NAME? | #NAME? | 7 | *Statement of Cost (if applicable)
#NAME? | #NAME? | 7 | *legislative letters
#NAME? | #NAME? | 7 | *2803 Project Evaluation (Design Evaluation)
#NAME? | #NAME? | 7 | Final Time Summary Report
#NAME? | #NAME? | 7 | Change Order Summary Report
#NAME? | #NAME? | 7 | Contract Line Item Report
#NAME? | #NAME? | 7 | Overrun & Underrun
#NAME? | #NAME? | 7 | Unpaid Installed Work Report (3% mob payment)
#NAME? | #NAME? | 7 | Unauthorized Daily Work Report
#NAME? | #NAME? | 7 | Failing Samples Report
#NAME? | #NAME? | 7 | Sampling Checklist Report
#NAME? | #NAME? | 7 | Xite Report (showing 0 deficiencies or items that coincide with test exception ltr)