## OTOB
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [13 empty] | Highway Construction Projects Completed September 1, 2022–February 28, 2023
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | FEBRUARY | 28 | 2023 | 2022
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | CO BY THRD PRTY | AMOUNT PAID | UNDER OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | THIRD PARTY DAYS ADDED | UNDER OVER SCHEDULE | MONTH | MMM_YY | QUARTER FINALED | QUARTER | CONSULTANT DESIGN | A + B PROJECT | CEI PROJECT | PROJECT SIZE | FY_CMPL
LUFKIN | 0911-00-108 | ANGELINA | VA | 2022-09-01 | 311290.55 | 0 | 0 | 320507.67 | 9217.12 | 62 | 62 | 0 | 0 | 0 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUFKIN | 1408-01-027 | POLK | FM 1276 | 2022-09-01 | 261129.47 | 0 | 0 | 268516.89 | 7387.42 | 46 | 14 | 0 | 0 | -32 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0009-09-103 | HOPKINS | IH 30 | 2022-09-01 | 397137.5 | 0 | 0 | 369282.5 | -27855 | 70 | 32 | 0 | 0 | -38 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0009-09-106 | HOPKINS | IH 30 | 2022-09-01 | 3952539.25 | 0 | 0 | 4161381.75 | 208842.5 | 182 | 220 | 44 | 0 | 38 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0108-09-050 | HOPKINS | SH 19 | 2022-09-01 | 2754447.02 | 259314.72 | 0 | 3185622.18 | 431175.16 | 137 | 137 | 0 | 0 | 0 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0187-04-032 | AUSTIN | SH 36 | 2022-09-01 | 1049635.3 | 59038.64 | 0 | 1161701.54 | 112066.24 | 178 | 183 | 14 | 0 | 5 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0605-01-060 | MATAGORDA | FM 457 | 2022-09-01 | 41231131.02 | 853119.32 | 0 | 42304884.25 | 1073753.23 | 405 | 441 | 36 | 0 | 36 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
BEAUMONT | 0703-01-067 | TYLER | FM 92 | 2022-09-02 | 7554649.35 | 1504117.23 | 0 | 8906056.33 | 1351406.98 | 180 | 181 | 16 | 0 | 1 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0089-12-004 | JACKSON | SL 522 | 2022-09-02 | 679501.16 | 66220.21 | 0 | 759842.12 | 80340.96 | 90 | 110 | 32 | 0 | 20 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANGELO | 0907-00-193 | TOM GREEN | VA | 2022-09-06 | 4491789.5 | 382695.45 | 0 | 4852770.98 | 360981.48 | 444 | 365 | 0 | 0 | -79 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
BRYAN | 0049-12-115 | BRAZOS | SH 6 | 2022-09-07 | 1105702.15 | 114973.98 | 69118.85 | 1201883.73 | 27062.73 | 126 | 151 | 15 | 15 | 10 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ABILENE | 0317-01-037 | FISHER | FM 57 | 2022-09-08 | 18577370.54 | 1796745.36 | 0 | 19106250.4 | 528879.86 | 673 | 622 | 0 | 0 | -51 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
ATLANTA | 0610-03-096 | TITUS | IH 30 | 2022-09-08 | 1504038.23 | 837138.26 | 0 | 2746422.99 | 1242384.76 | 90 | 78 | 0 | 0 | -12 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 1418-01-012 | WALLER | FM 1489 | 2022-09-08 | 1597058.4 | 8478.12 | 0 | 1657809.75 | 60751.35 | 60 | 65 | 5 | 0 | 5 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AMARILLO | 0355-01-050 | LIPSCOMB | SH 15 | 2022-09-09 | 3368933 | 0 | 0 | 3466869.51 | 97936.51 | 281 | 267 | 0 | 0 | -14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CORPUS CHRISTI | 0101-04-113 | SAN PATRICIO | US 181 | 2022-09-09 | 2780023.75 | 66950 | 0 | 2647224.55 | -132799.2 | 224 | 248 | 30 | 0 | 24 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0912-72-536 | HARRIS | CR | 2022-09-12 | 6051944.84 | 241911.11 | 207519.49 | 6300563.14 | 41098.81 | 230 | 244 | 17 | 17 | -3 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 0229-03-037 | CRANE | US 385 | 2022-09-12 | 36634908.09 | 375868.78 | 0 | 37181961.15 | 547053.06 | 419 | 495 | 77 | 0 | 76 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
PARIS | 0901-29-094 | LAMAR | CS | 2022-09-12 | 499928.61 | 7705 | 0 | 542423.79 | 42495.18 | 96 | 73 | 0 | 0 | -23 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PHARR | 0255-09-094 | HIDALGO | UP 281 | 2022-09-13 | 23982430.46 | -740605.88 | 0 | 23757407.7 | -225022.76 | 440 | 440 | 0 | 0 | 0 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | MEDIUM | FY23
CORPUS CHRISTI | 1122-01-029 | KARNES | FM 791 | 2022-09-14 | 144496.85 | 0 | 0 | 143351.85 | -1145 | 34 | 20 | 0 | 0 | -14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CORPUS CHRISTI | 1422-01-009 | KARNES | FM 1354 | 2022-09-14 | 1326777.63 | 103608.65 | 0 | 1478419.12 | 151641.49 | 194 | 206 | 12 | 0 | 12 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUBBOCK | 0067-06-060 | HALE | IH 27 | 2022-09-14 | 228494.89 | 0 | 0 | 219595.87 | -8899.02 | 60 | 42 | 0 | 0 | -18 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PHARR | 0039-02-072 | HIDALGO | US 83 | 2022-09-14 | 2177828.79 | 47368.28 | 0 | 2257149.87 | 79321.08 | 90 | 301 | 135 | 0 | 211 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0113-07-074 | HAYS | US 290 | 2022-09-15 | 2276991.23 | -228354.63 | 0 | 2684102.67 | 407111.44 | 59 | 40 | 0 | 0 | -19 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0914-25-008 | LLANO | CR | 2022-09-15 | 1599439.5 | 66698.15 | 0 | 1675150.98 | 75711.48 | 96 | 95 | 0 | 0 | -1 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0046-01-064 | RED RIVER | US 82 | 2022-09-15 | 14202161.56 | 709842.97 | 0 | 15412667.82 | 1210506.26 | 367 | 353 | 20 | 0 | -14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
SAN ANGELO | 0830-03-013 | EDWARDS | RM 335 | 2022-09-16 | 999997.68 | 38966.04 | 0 | 1099532.22 | 99534.54 | 81 | 158 | 5 | 0 | 77 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-00-182 | BEXAR | VA | 2022-09-16 | 1921528.61 | 432122 | 0 | 2386225.53 | 464696.92 | 360 | 396 | 34 | 0 | 36 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CHILDRESS | 0042-06-074 | DONLEY | US 287 | 2022-09-19 | 3680420.35 | 17812.4 | 0 | 3554529.85 | -125890.5 | 184 | 312 | 17 | 0 | 128 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CHILDRESS | 0970-01-018 | BRISCOE | FM 378 | 2022-09-19 | 5420379.09 | 0 | 0 | 5663734.01 | 243354.92 | 54 | 24 | 0 | 0 | -30 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0918-00-353 | DALLAS | VA | 2022-09-19 | 1052807.67 | 9973.6 | 0 | 1062781.28 | 9973.61 | 90 | 87 | 4 | 0 | -3 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 0025-02-217 | BEXAR | IH 10 | 2022-09-19 | 1479046.42 | 104471.81 | 0 | 1543484.45 | 64438.03 | 130 | 314 | 5 | 0 | 184 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 2820-01-012 | FAYETTE | FM 2762 | 2022-09-19 | 6090094.35 | 56933.17 | 0 | 5930863.85 | -159230.5 | 240 | 200 | 0 | 0 | -40 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0173-05-041 | KAUFMAN | SH 34 | 2022-09-20 | 2104538.18 | 407029.17 | 0 | 2541127.85 | 436589.67 | 86 | 62 | 0 | 0 | -24 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-00-230 | BEXAR | VA | 2022-09-20 | 3053200.71 | 597547.37 | 0 | 3707913.18 | 654712.47 | 312 | 292 | 10 | 0 | -20 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WICHITA FALLS | 0514-04-014 | WICHITA | FM 1177 | 2022-09-20 | 2189864.65 | 0 | 0 | 2298516.02 | 108651.37 | 102 | 148 | 32 | 0 | 46 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ATLANTA | 0919-00-081 | CASS | VA | 2022-09-21 | 934909 | 0 | 0 | 858409.56 | -76499.44 | 57 | 54 | 0 | 0 | -3 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0500-03-606 | HARRIS | IH 45 | 2022-09-21 | 66590610.25 | 5747824.49 | 0 | 74407044.22 | 7816433.97 | 1237 | 1428 | 194 | 0 | 191 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | LARGE | FY23
LAREDO | 0022-07-031 | VAL VERDE | US 90 | 2022-09-21 | 7511303.55 | -372575.51 | 0 | 7865751.79 | 354448.24 | 200 | 198 | 0 | 0 | -2 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LAREDO | 0922-00-073 | WEBB | VA | 2022-09-21 | 1371914.57 | 6430.12 | 0 | 1373473.49 | 1558.92 | 153 | 165 | 10 | 0 | 12 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 3256-04-076 | HARRIS | SL 8 | 2022-09-22 | 415822.93 | 20138.36 | 0 | 454494.74 | 38671.81 | 60 | 46 | 0 | 0 | -14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0901-28-094 | HOPKINS | CR | 2022-09-25 | 247020.54 | 33920 | 0 | 271344.98 | 24324.44 | 64 | 44 | 0 | 0 | -20 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BEAUMONT | 0920-30-077 | ORANGE | CR | 2022-09-26 | 11399710.8 | 744683.82 | 0 | 12068811.44 | 669100.64 | 300 | 667 | 367 | 0 | 367 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
HOUSTON | 2523-02-069 | BRAZORIA | FM 2004 | 2022-09-27 | 1417776.24 | 39933.27 | 0 | 1426193.63 | 8417.39 | 35 | 34 | 0 | 0 | -1 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUBBOCK | 0067-04-056 | HALE | IH 27 | 2022-09-27 | 1478054.21 | 0 | 0 | 1433313.73 | -44740.48 | 78 | 62 | 0 | 0 | -16 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 0354-06-031 | ANDREWS | SH 115 | 2022-09-27 | 1156357.6 | 0 | 0 | 1177448.6 | 21091 | 125 | 122 | 0 | 0 | -3 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-00-201 | BEXAR | VA | 2022-09-27 | 1582979.25 | 48705.54 | 0 | 1598570.73 | 15591.48 | 240 | 194 | 2 | 0 | -46 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
TYLER | 0910-35-036 | WOOD | CS | 2022-09-27 | 339130.6 | 26875 | 0 | 328155.56 | -10975.04 | 180 | 100 | 0 | 0 | -80 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
TYLER | 0927-01-033 | SMITH | FM 344 | 2022-09-27 | 329522 | -12500 | 0 | 311472 | -18050 | 21 | 41 | 0 | 0 | 20 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0440-06-017 | TRAVIS | SH 130 | 2022-09-28 | 36726431.31 | 7957401.27 | 0 | 41520503.09 | 4794071.78 | 595 | 806 | 15 | 0 | 211 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
BEAUMONT | 0065-14-026 | HARDIN | BU 96-F | 2022-09-28 | 1167485.2 | 100707.53 | 0 | 1315781.47 | 148296.27 | 152 | 114 | 20 | 0 | -38 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0912-72-371 | HARRIS | VA | 2022-09-28 | 8619571.44 | 738415.22 | 608359.96 | 9335214.38 | 107282.98 | 500 | 397 | 0 | 0 | -103 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 2230-01-013 | BEXAR | FM 1560 | 2022-09-28 | 17810211.46 | 428901.4 | -247374.95 | 17984315.75 | 421479.24 | 932 | 749 | 0 | 0 | -183 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
WICHITA FALLS | 0156-05-061 | ARCHER | US 82 | 2022-09-28 | 7252069.49 | 0 | 0 | 7049712.73 | -202356.76 | 346 | 360 | 0 | 0 | 14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WICHITA FALLS | 0681-01-023 | WICHITA | FM 171 | 2022-09-28 | 1584998.82 | 19869.27 | 0 | 1527300.97 | -57697.85 | 151 | 250 | 71 | 0 | 99 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0015-09-203 | WILLIAMSON | IH 35 | 2022-09-29 | 399182.9 | -44000 | 0 | 359903.14 | -39279.76 | 31 | 17 | 0 | 0 | -14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 1899-01-018 | KENDALL | RM 1376 | 2022-09-29 | 10189262.85 | 1179453.84 | 0 | 10884678.03 | 695415.18 | 217 | 389 | 161 | 0 | 172 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
AUSTIN | 1903-01-012 | GILLESPIE | FM 2093 | 2022-09-30 | 3785506.61 | 16511.66 | 0 | 3823666.21 | 38159.6 | 180 | 239 | 90 | 0 | 59 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 1068-04-119 | DALLAS | IH 30 | 2022-09-30 | 37840877.84 | 7954173.56 | 0 | 45185387.69 | 7344509.85 | 543 | 846 | 306 | 0 | 303 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | MEDIUM | FY23
YOAKUM | 0913-17-039 | DEWITT | CR | 2022-09-30 | 1067538.13 | 0 | 0 | 1058539.84 | -8998.29 | 161 | 147 | 0 | 0 | -14 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0941-02-019 | DEWITT | FM 952 | 2022-09-30 | 1347305.19 | 0 | 0 | 1358889.59 | 11584.4 | 149 | 149 | 0 | 0 | 0 | SEPTEMBER | SEP-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0543-02-076 | FORT BEND | FM 359 | 2022-10-03 | 1393431.98 | 0 | 0 | 1529339.94 | 135907.96 | 45 | 45 | 0 | 0 | 0 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0026-01-027 | GONZALES | US 90 | 2022-10-03 | 2613600.86 | 256881.18 | 0 | 2799440.38 | 185839.52 | 135 | 158 | 28 | 0 | 23 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0088-04-070 | VICTORIA | US 59 | 2022-10-03 | 4506272.52 | -90963.15 | 0 | 4685432.85 | 179160.33 | 75 | 85 | 11 | 0 | 10 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ATLANTA | 0062-05-062 | MARION | US 59 | 2022-10-04 | 2827413.51 | 186615.84 | 0 | 3053844.49 | 226430.98 | 150 | 217 | 9 | 0 | 67 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ABILENE | 0668-02-022 | HOWARD | FM 700 | 2022-10-06 | 549093.98 | 0 | 0 | 547146.43 | -1947.55 | 47 | 43 | 0 | 0 | -4 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 2100-01-054 | TRAVIS | RM 2222 | 2022-10-06 | 23618552.64 | 2062276.31 | 91191.92 | 26254604.67 | 2544860.11 | 318 | 699 | 381 | 0 | 381 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
BRYAN | 0858-03-019 | BURLESON | FM 908 | 2022-10-06 | 2973230.5 | 235176.5 | 0 | 3344519.74 | 371289.24 | 320 | 273 | 0 | 0 | -47 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0045-19-053 | GRAYSON | US 82 | 2022-10-06 | 3461445 | 603352.27 | 0 | 4351437.55 | 889992.55 | 140 | 293 | 185 | 0 | 153 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WICHITA FALLS | 0013-02-023 | MONTAGUE | US 81 | 2022-10-06 | 7507421.92 | -1572037.44 | 0 | 5493611.77 | -2013810.15 | 50 | 106 | 0 | 0 | 56 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUBBOCK | 0905-00-104 | LUBBOCK | VA | 2022-10-07 | 3499999.99 | 0 | 0 | 3574982.37 | 74982.38 | 70 | 69 | 0 | 0 | -1 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 2190-01-007 | BASTROP | FM 2336 | 2022-10-11 | 3987883.56 | 268979 | 0 | 3976915.29 | -10968.27 | 162 | 159 | 0 | 0 | -3 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0430-01-057 | DALLAS | SH 352 | 2022-10-11 | 12469180.73 | 447989.71 | 18261.81 | 12231781.12 | -255661.42 | 427 | 466 | 41 | 0 | 39 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | Y | N | SMALL | FY23
LAREDO | 0017-08-114 | LA SALLE | IH 35 | 2022-10-13 | 6453181.63 | -173986.98 | 0 | 6296640.69 | -156540.94 | 214 | 105 | 0 | 0 | -109 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ATLANTA | 0138-11-032 | MARION | FM 248 | 2022-10-14 | 1138920.94 | 0 | 0 | 1135715.07 | -3205.87 | 200 | 168 | 0 | 0 | -32 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ATLANTA | 0222-01-058 | TITUS | SH 49 | 2022-10-14 | 11689370.97 | 407564.02 | 0 | 13102845.73 | 1413474.76 | 320 | 338 | 0 | 0 | 18 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BRYAN | 3138-01-029 | BRAZOS | FM 2347 | 2022-10-14 | 2417981.6 | 4019.1 | 0 | 2402111.97 | -15869.63 | 107 | 118 | 0 | 0 | 11 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0027-06-046 | FORT BEND | US 90A | 2022-10-14 | 24827885.13 | 1818240.53 | 0 | 27215230.97 | 2387345.84 | 680 | 739 | 66 | 0 | 59 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | Y | N | Y | MEDIUM | FY23
LUBBOCK | 0905-00-103 | LUBBOCK | VA | 2022-10-14 | 2185433.47 | 263543.23 | 0 | 2447154.5 | 261721.03 | 90 | 106 | 16 | 0 | 16 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WACO | 0231-03-152 | BELL | IH 14 | 2022-10-14 | 4573812.5 | 0 | 0 | 4598920.55 | 25108.05 | 210 | 144 | 0 | 0 | -66 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WACO | 1835-02-059 | BELL | FM 1741 | 2022-10-14 | 2447065.1 | 13230 | 0 | 2304413.28 | -142651.82 | 270 | 234 | 0 | 0 | -36 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AMARILLO | 0168-09-165 | RANDALL | IH 27 | 2022-10-17 | 6336098.66 | 31880.25 | 0 | 6588495.16 | 252396.5 | 76 | 78 | 4 | 0 | 2 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 0068-11-008 | MARTIN | FM 2212 | 2022-10-17 | 6937459.13 | 0 | 0 | 7268105.32 | 330646.19 | 46 | 21 | 0 | 0 | -25 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 1440-01-020 | FAYETTE | FM 957 | 2022-10-17 | 1368475.9 | 0 | 0 | 1329360.1 | -39115.8 | 120 | 143 | 23 | 0 | 23 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | Y | N | SMALL | FY23
ABILENE | 0053-15-024 | NOLAN | FM 608 | 2022-10-18 | 4261779.48 | -283459.45 | 0 | 4005729.36 | -256050.12 | 253 | 484 | 5 | 0 | 231 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
AMARILLO | 0041-05-053 | POTTER | US 87 | 2022-10-18 | 1149484.51 | 38708.23 | 0 | 1200113.46 | 50628.95 | 72 | 70 | 0 | 0 | -2 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0914-00-446 | TRAVIS | VA | 2022-10-18 | 2592102 | -474849.7 | 0 | 1905674.85 | -686427.15 | 271 | 265 | 0 | 0 | -6 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 1149-01-030 | TRAVIS | FM 812 | 2022-10-18 | 1170306.78 | 0 | 0 | 1246179.65 | 75872.87 | 33 | 22 | 0 | 0 | -11 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
HOUSTON | 0027-13-240 | HARRIS | IH 69 | 2022-10-18 | 544151.2 | 71596.14 | 0 | 574140.94 | 29989.74 | 35 | 12 | 0 | 0 | -23 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0271-09-023 | WALLER | US 90 | 2022-10-18 | 1784542.44 | -89873.04 | 0 | 1403404.17 | -381138.27 | 80 | 82 | 0 | 0 | 2 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0523-02-049 | WALLER | FM 362 | 2022-10-18 | 5288985.33 | -106498.38 | 0 | 5220993.8 | -67991.53 | 98 | 98 | 0 | 0 | 0 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AMARILLO | 0168-08-073 | RANDALL | US 60 | 2022-10-19 | 4103043.6 | 169895.11 | 0 | 4772599.06 | 669555.46 | 139 | 159 | 20 | 0 | 20 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0573-01-039 | BASTROP | SH 304 | 2022-10-19 | 7305240.14 | -55413.38 | 63788.37 | 7222415.41 | -146613.1 | 190 | 188 | 8 | 8 | -10 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0196-03-277 | DALLAS | IH 35E | 2022-10-19 | 19661568.87 | 811921.05 | 0 | 20747319.17 | 1085750.3 | 249 | 273 | 24 | 0 | 24 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | MEDIUM | FY23
DALLAS | 0196-06-033 | DALLAS | SL 354 | 2022-10-19 | 1440000 | 1134.5 | 0 | 1420181.22 | -19818.78 | 195 | 190 | 0 | 0 | -5 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0197-05-060 | KAUFMAN | US 175 | 2022-10-19 | 274544.15 | 0 | 0 | 277681.15 | 3137 | 60 | 44 | 0 | 0 | -16 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
EL PASO | 0374-07-028 | HUDSPETH | US 62 | 2022-10-19 | 2871945.66 | 836576.2 | 0 | 4252462.4 | 1380516.74 | 83 | 93 | 42 | 0 | 10 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BRYAN | 0675-07-096 | WALKER | IH 45 | 2022-10-20 | 119242718.11 | 3673111.44 | 0 | 125772949.35 | 6530231.24 | 1231 | 1018 | 3 | 0 | -213 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | Y | Y | LARGE | FY23
HOUSTON | 0912-72-336 | HARRIS | CR | 2022-10-20 | 11194639.23 | 3690583.02 | 3057738.11 | 16241268.81 | 1988891.47 | 537 | 797 | 260 | 259 | 1 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WICHITA FALLS | 0249-03-054 | ARCHER | US 281 | 2022-10-20 | 2498171.7 | 0 | 0 | 2831695.54 | 333523.84 | 51 | 48 | 0 | 0 | -3 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ABILENE | 0908-00-109 | TAYLOR | VA | 2022-10-21 | 2275431.82 | 149803.15 | 0 | 2526434.01 | 251002.19 | 60 | 87 | 30 | 0 | 27 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0015-08-141 | WILLIAMSON | IH 35 | 2022-10-21 | 12273229.93 | 1871778.62 | 0 | 13498079.08 | 1224849.15 | 390 | 553 | 81 | 0 | 163 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | Y | N | SMALL | FY23
BROWNWOOD | 0127-01-037 | EASTLAND | US 183 | 2022-10-21 | 2839911.02 | 135737.5 | 0 | 3138509.46 | 298598.44 | 73 | 56 | 12 | 0 | -17 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 0072-07-070 | BEXAR | IH 10 | 2022-10-21 | 34660389.39 | 305459.52 | 0 | 34778652.14 | 118262.75 | 419 | 526 | 53 | 0 | 107 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | Y | N | MEDIUM | FY23
EL PASO | 0167-01-117 | EL PASO | US 54 | 2022-10-24 | 1650010.6 | 125574.47 | 0 | 1944799.16 | 294788.56 | 92 | 206 | 117 | 0 | 114 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PARIS | 0081-10-048 | GRAYSON | US 377 | 2022-10-24 | 1740801.09 | -40735 | 0 | 1730788.25 | -10012.84 | 159 | 159 | 0 | 0 | 0 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ABILENE | 2270-01-023 | TAYLOR | FM 3438 | 2022-10-25 | 4152367.85 | 3861.55 | 0 | 4411589.17 | 259221.32 | 144 | 144 | 0 | 0 | 0 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CHILDRESS | 0098-02-028 | FOARD | SH 6 | 2022-10-25 | 3874626.92 | 0 | 0 | 3732430.83 | -142196.09 | 74 | 66 | 0 | 0 | -8 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0508-01-357 | HARRIS | IH 10 | 2022-10-25 | 5499459.69 | 121573.71 | 0 | 5415274.62 | -84185.07 | 142 | 139 | 0 | 0 | -3 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BEAUMONT | 0368-03-037 | JEFFERSON | SH 124 | 2022-10-27 | 362017.41 | 271.32 | 0 | 404195.65 | 42178.24 | 45 | 32 | 0 | 0 | -13 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0028-01-099 | HARRIS | UA 90 | 2022-10-27 | 1366270.54 | 409359.43 | 0 | 1731953.91 | 365683.37 | 64 | 77 | 13 | 0 | 13 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUFKIN | 0336-07-071 | SAN AUGUSTINE | SH 103 | 2022-10-27 | 8461461.01 | -368581.9 | 0 | 9671362.26 | 1209901.25 | 283 | 299 | 21 | 0 | 16 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUFKIN | 0694-01-031 | SABINE | FM 83 | 2022-10-27 | 1095146.5 | 6511.48 | 0 | 1344436.44 | 249289.94 | 114 | 113 | 0 | 0 | -1 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 0003-06-096 | REEVES | IH 20 | 2022-10-27 | 983847.25 | 3965.05 | 0 | 818888.32 | -164958.93 | 125 | 89 | 19 | 0 | -36 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CORPUS CHRISTI | 0916-29-015 | LIVE OAK | VA | 2022-10-28 | 587838.09 | 15473.24 | 3094.64 | 587922.98 | -3009.75 | 102 | 78 | 0 | 0 | -24 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 1685-01-110 | HARRIS | FM 1960 | 2022-10-28 | 3598843.23 | 30131.68 | 0 | 3476712.47 | -122130.76 | 115 | 114 | 0 | 0 | -1 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LAREDO | 0086-16-016 | WEBB | SL 20 | 2022-10-28 | 232954.8 | 0 | 0 | 226861.8 | -6093 | 40 | 37 | 0 | 0 | -3 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
BROWNWOOD | 0182-02-046 | COMANCHE | SH 36 | 2022-10-31 | 2320588.82 | 279288.84 | 0 | 2913997.21 | 593408.39 | 34 | 58 | 30 | 0 | 24 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
FORT WORTH | 1603-03-041 | TARRANT | FM 1709 | 2022-10-31 | 741662.8 | 20806.13 | 0 | 725697.45 | -15965.35 | 128 | 201 | 6 | 0 | 73 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0188-01-039 | FORT BEND | SH 36 | 2022-10-31 | 949219.81 | 200319.98 | 0 | 1135039.53 | 185819.72 | 34 | 28 | 0 | 0 | -6 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
HOUSTON | 0367-06-063 | GALVESTON | SH 87 | 2022-10-31 | 758074.28 | 165812.49 | 0 | 979642.71 | 221568.43 | 45 | 47 | 0 | 0 | 2 | OCTOBER | OCT-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BEAUMONT | 0920-00-134 | JEFFERSON | VA | 2022-11-01 | 540111.02 | 14273.01 | 0 | 574586.25 | 34475.23 | 100 | 114 | 0 | 0 | 14 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 0906-00-203 | ECTOR | VA | 2022-11-02 | 1267114 | 342448.86 | 0 | 1721755.44 | 454641.44 | 211 | 205 | 8 | 0 | -6 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 0906-00-242 | ECTOR | VA | 2022-11-02 | 2208069 | 46810.91 | 0 | 2140674.11 | -67394.89 | 266 | 170 | 0 | 0 | -96 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 2451-03-017 | REEVES | RM 652 | 2022-11-02 | 20145622.79 | 393542.38 | 0 | 20514131.84 | 368509.05 | 300 | 375 | 75 | 0 | 75 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
SAN ANGELO | 0158-02-092 | TOM GREEN | US 67 | 2022-11-03 | 653340.14 | 42905.26 | 0 | 648498.44 | -4841.7 | 62 | 53 | 0 | 0 | -9 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0918-47-279 | DALLAS | VA | 2022-11-04 | 2125611.75 | -185118 | 0 | 1733785.37 | -391826.38 | 200 | 204 | 0 | 0 | 4 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
SAN ANTONIO | 1890-01-046 | BEXAR | FM 1976 | 2022-11-04 | 16483392.88 | 3123529.24 | 238687.2 | 19133766.59 | 2411686.51 | 383 | 582 | 105 | 11 | 188 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | MEDIUM | FY23
YOAKUM | 1498-01-008 | FAYETTE | FM 1579 | 2022-11-04 | 1026049.2 | 0 | 0 | 996629.78 | -29419.42 | 90 | 99 | 9 | 0 | 9 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
FORT WORTH | 0364-01-157 | TARRANT | SH 121 | 2022-11-07 | 1474597.54 | 0 | 0 | 1317123.02 | -157474.52 | 167 | 305 | 0 | 0 | 138 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PHARR | 0039-04-129 | HIDALGO | BU 83-S | 2022-11-07 | 2216223.85 | 0 | 0 | 2107581.8 | -108642.05 | 200 | 210 | 11 | 0 | 10 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0091-06-060 | DALLAS | SH 289 | 2022-11-08 | 2257307.01 | 2444.99 | 0 | 2287156.34 | 29849.33 | 103 | 96 | 0 | 0 | -7 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUBBOCK | 0905-00-109 | LUBBOCK | VA | 2022-11-08 | 2816960 | 0 | 0 | 2741207.54 | -75752.46 | 88 | 87 | 0 | 0 | -1 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
PHARR | 1801-02-017 | CAMERON | FM 1847 | 2022-11-09 | 19989898.05 | 1136218.47 | 0 | 21245617.93 | 1255719.88 | 480 | 524 | 76 | 0 | 44 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
WACO | 0398-04-077 | BELL | SH 317 | 2022-11-09 | 355835.92 | 4680 | 0 | 368827.83 | 12991.91 | 30 | 24 | 0 | 0 | -6 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BRYAN | 0049-09-088 | BRAZOS | BS 6-R | 2022-11-10 | 847125.27 | 104065.14 | 0 | 944793.49 | 97668.22 | 11 | 14 | 0 | 0 | 3 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
LUFKIN | 0809-03-040 | SAN AUGUSTINE | US 96 | 2022-11-10 | 4885972 | 49100.38 | 0 | 5106614.16 | 220642.16 | 160 | 156 | 0 | 0 | -4 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 3136-01-191 | TRAVIS | SL 1 | 2022-11-12 | 1525579.26 | 158695.09 | 0 | 1807350.75 | 281771.49 | 64 | 75 | 45 | 0 | 11 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0115-04-056 | BASTROP | FM 20 | 2022-11-13 | 120169.5 | 0 | 0 | 122052.09 | 1882.59 | 33 | 33 | 0 | 0 | 0 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0912-00-621 | HARRIS | VA | 2022-11-14 | 1598404.74 | 53298.96 | 0 | 1549812.2 | -48592.54 | 132 | 137 | 5 | 0 | 5 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BROWNWOOD | 0231-01-057 | LAMPASAS | US 190 | 2022-11-15 | 387266.75 | 32140.88 | 0 | 437149.77 | 49883.02 | 51 | 51 | 0 | 0 | 0 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0089-03-091 | JACKSON | US 59 | 2022-11-15 | 12833114.25 | -372152.9 | 0 | 13592059.7 | 758945.45 | 165 | 118 | 0 | 0 | -47 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0027-06-051 | FORT BEND | US 90A | 2022-11-16 | 13229156.43 | 809147.77 | 0 | 14472054.54 | 1242898.11 | 315 | 315 | 0 | 0 | 0 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BEAUMONT | 0339-03-039 | HARDIN | SH 105 | 2022-11-17 | 645518.94 | 24901.55 | 0 | 714151.27 | 68632.33 | 45 | 85 | 5 | 0 | 40 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BEAUMONT | 0920-00-135 | JEFFERSON | VA | 2022-11-17 | 723760.69 | -18742.2 | 0 | 711750.6 | -12010.09 | 85 | 52 | 0 | 0 | -33 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 3050-02-025 | MONTGOMERY | FM 2978 | 2022-11-17 | 8195982.09 | 7083202.24 | 120789.59 | 15737911.02 | 7421139.34 | 276 | 551 | 287 | 15 | 260 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 3158-01-032 | MONTGOMERY | FM 3083 | 2022-11-17 | 9047341.21 | 274583.33 | 0 | 9216771.52 | 169430.31 | 170 | 406 | 0 | 0 | 236 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
BROWNWOOD | 0007-03-094 | EASTLAND | IH 20 | 2022-11-18 | 14844220.02 | -269055.12 | 0 | 14101864.09 | -742355.93 | 105 | 98 | 0 | 0 | -7 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
FORT WORTH | 2266-02-086 | TARRANT | SH 360 | 2022-11-18 | 53391000.01 | 4880181.65 | 103995.96 | 58259857.16 | 4764861.19 | 797 | 862 | 65 | 0 | 65 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | Y | N | Y | LARGE | FY23
LUBBOCK | 0905-21-004 | CROSBY | CR | 2022-11-18 | 1322304 | 46770 | 0 | 1373162 | 50858 | 213 | 136 | 0 | 0 | -77 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ODESSA | 2224-01-120 | ECTOR | SL 338 | 2022-11-18 | 1058413.8 | -140196.2 | 0 | 897034.38 | -161379.42 | 60 | 58 | 0 | 0 | -2 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
WICHITA FALLS | 0043-07-119 | WILBARGER | US 287 | 2022-11-18 | 5165943.81 | 0 | 0 | 5286487.62 | 120543.81 | 136 | 86 | 0 | 0 | -50 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0918-00-326 | DALLAS | VA | 2022-11-21 | 1649565.66 | 0 | 0 | 1649827.03 | 261.37 | 200 | 78 | 0 | 0 | -122 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
AUSTIN | 0914-00-400 | TRAVIS | VA | 2022-11-22 | 1358621.16 | 1599.5 | 0 | 1399661.63 | 41040.47 | 300 | 306 | 0 | 0 | 6 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
DALLAS | 0196-03-268 | DALLAS | IH 35E | 2022-11-22 | 78786038.51 | 11117435.18 | 0 | 93216634.9 | 14430596.39 | 618 | 1119 | 501 | 0 | 501 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | Y | Y | LARGE | FY23
DALLAS | 0581-01-159 | DALLAS | SL 12 | 2022-11-22 | 1924541.55 | 48644.02 | 0 | 1891784.72 | -32756.83 | 138 | 202 | 29 | 0 | 64 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
ABILENE | 0264-01-045 | NOLAN | SH 70 | 2022-11-28 | 4823267.55 | -598131.78 | 0 | 4326704.13 | -496563.42 | 235 | 114 | 0 | 0 | -121 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BEAUMONT | 0920-02-091 | LIBERTY | CR | 2022-11-28 | 777585.7 | 19409.59 | 0 | 797146.49 | 19560.79 | 86 | 131 | 5 | 0 | 45 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
HOUSTON | 0912-72-595 | HARRIS | CS | 2022-11-28 | 2787309 | 205669.71 | 132827.98 | 2943156.3 | 23019.32 | 276 | 208 | 10 | 10 | -78 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
TYLER | 0191-01-063 | SMITH | US 69 | 2022-11-28 | 16738120.33 | 82993.73 | 0 | 16815842.23 | 77721.9 | 430 | 429 | 0 | 0 | -1 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | Y | MEDIUM | FY23
TYLER | 0697-02-039 | HENDERSON | SH 334 | 2022-11-28 | 41269729.22 | 3182016.34 | 0 | 44394191.36 | 3124462.14 | 450 | 550 | 62 | 0 | 100 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | Y | Y | MEDIUM | FY23
TYLER | 0910-36-129 | CHEROKEE | CR | 2022-11-28 | 1943346.8 | -26705.19 | 0 | 1919168.64 | -24178.16 | 171 | 178 | 0 | 0 | 7 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
BRYAN | 0050-03-107 | GRIMES | SH 6 | 2022-11-29 | 990316.51 | 25220.74 | 0 | 940785.11 | -49531.4 | 171 | 90 | 0 | 0 | -81 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
CORPUS CHRISTI | 0326-05-003 | NUECES | BS 286A | 2022-11-29 | 2555405.95 | 53065.27 | 0 | 2406918.56 | -148487.39 | 114 | 118 | 4 | 0 | 4 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | N | SMALL | FY23
YOAKUM | 0266-08-013 | COLORADO | BS 71-F | 2022-11-29 | 4243334 | 1506585.47 | 0 | 5806379.39 | 1563045.39 | 116 | 232 | 116 | 0 | 116 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
AUSTIN | 0114-01-063 | TRAVIS | US 290 | 2022-11-30 | 1949774.04 | 74727.24 | 0 | 1769661.76 | -180112.28 | 52 | 31 | 0 | 0 | -21 | NOVEMBER | NOV-22 | 2019-01-01 | Q1 | N | N | Y | SMALL | FY23
YOAKUM | 0026-02-035 | FAYETTE | US 90 | 2022-12-01 | 140775.42 | 4979 | 0 | 147291.63 | 6516.21 | 45 | 30 | 0 | 0 | -15 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ODESSA | 2371-01-012 | WARD | PR 41 | 2022-12-02 | 233040 | 0 | 0 | 255183.41 | 22143.41 | 19 | 19 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0142-15-026 | KENDALL | IH 10 | 2022-12-02 | 12602401.7 | 127997.49 | 0 | 12366445.19 | -235956.51 | 227 | 282 | 55 | 0 | 55 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 1585-01-025 | TYLER | FM 1746 | 2022-12-05 | 3877452.1 | 294806.19 | 0 | 3920273.56 | 42821.46 | 210 | 177 | 2 | 0 | -33 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
TYLER | 0191-03-081 | SMITH | FM 2493 | 2022-12-05 | 14458790.48 | 265743.63 | 0 | 14450141.8 | -8648.68 | 506 | 458 | 0 | 0 | -48 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
AUSTIN | 0914-33-067 | HAYS | VA | 2022-12-07 | 345405.57 | -14453.26 | 0 | 288648 | -56757.57 | 13 | 13 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0111-03-031 | FORT BEND | FM 521 | 2022-12-07 | 34567384.22 | 2568155.42 | 0 | 36980032.67 | 2412648.45 | 529 | 619 | 100 | 0 | 90 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
FORT WORTH | 0313-07-020 | PARKER | FM 51 | 2022-12-08 | 1487924.5 | 6030 | 0 | 1482337.16 | -5587.34 | 150 | 182 | 13 | 0 | 32 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANGELO | 0158-02-084 | TOM GREEN | US 67 | 2022-12-08 | 37993285.39 | 1310173.9 | 0 | 39527927.25 | 1534641.86 | 625 | 782 | 257 | 0 | 157 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | MEDIUM | FY23
HOUSTON | 0389-12-092 | HARRIS | SH 146 | 2022-12-09 | 496374.53 | 0 | 0 | 518496.19 | 22121.66 | 40 | 37 | 0 | 0 | -3 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 0911-28-051 | HOUSTON | CR | 2022-12-09 | 1191638.8 | 0 | 0 | 1178887.55 | -12751.25 | 111 | 150 | 0 | 0 | 39 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 0269-04-039 | LAVACA | UA 77 | 2022-12-09 | 1216444.86 | -747.92 | 0 | 1188628.34 | -27816.52 | 75 | 133 | 58 | 0 | 58 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 2103-01-039 | WILLIAMSON | RM 2243 | 2022-12-11 | 466269.6 | 0 | 0 | 472873.3 | 6603.7 | 50 | 60 | 0 | 0 | 10 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0211-02-028 | LEE | US 77 | 2022-12-12 | 2887592.71 | -9527.9 | 0 | 2929955.99 | 42363.28 | 80 | 79 | 0 | 0 | -1 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 1378-01-047 | TRAVIS | RM 1431 | 2022-12-12 | 1213911.16 | 0 | 0 | 1284593.91 | 70682.75 | 68 | 84 | 0 | 0 | 16 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
CHILDRESS | 0042-12-082 | CHILDRESS | US 287 | 2022-12-12 | 2074852.7 | 57526.39 | 0 | 2129894.2 | 55041.5 | 182 | 215 | 19 | 0 | 33 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
CHILDRESS | 0098-11-005 | HARDEMAN | PR 62 | 2022-12-12 | 654248 | 8390.75 | 0 | 697964.45 | 43716.45 | 80 | 86 | 6 | 0 | 6 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
CHILDRESS | 1040-02-022 | HALL | FM 1041 | 2022-12-12 | 1177467.5 | 0 | 0 | 1174780.8 | -2686.7 | 119 | 119 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0912-72-348 | HARRIS | CS | 2022-12-12 | 2898014.26 | 94444.1 | 9163.81 | 2756707.1 | -150470.97 | 180 | 234 | 14 | 0 | 54 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
WACO | 0258-06-040 | BOSQUE | SH 6 | 2022-12-12 | 19873560.72 | 209898.68 | 0 | 20382023.83 | 508463.11 | 406 | 440 | 40 | 0 | 34 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | MEDIUM | FY23
AUSTIN | 0440-06-018 | TRAVIS | SH 130 | 2022-12-13 | 56174105.25 | 8282320.93 | 14159.96 | 65275531.21 | 9087266 | 476 | 558 | 113 | 0 | 82 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | Y | Y | LARGE | FY23
BROWNWOOD | 0127-02-148 | EASTLAND | US 183 | 2022-12-13 | 1372072.3 | 67612.85 | 0 | 1430420.25 | 58347.95 | 39 | 63 | 18 | 0 | 24 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BRYAN | 0506-01-105 | BRAZOS | FM 60 | 2022-12-13 | 13863443.8 | 1226535.34 | 0 | 15729467.42 | 1866023.62 | 396 | 377 | -17 | 0 | -19 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
CORPUS CHRISTI | 0073-07-001 | LIVE OAK | IH 37 | 2022-12-13 | 374428 | 7400.01 | 0 | 328573.45 | -45854.55 | 51 | 52 | 2 | 0 | 1 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0912-56-056 | WALLER | CR | 2022-12-13 | 560102.49 | -53957.04 | 0 | 493265.19 | -66837.3 | 120 | 111 | 0 | 0 | -9 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 1407-01-025 | NACOGDOCHES | FM 1275 | 2022-12-13 | 6199551.45 | 114837.2 | 0 | 6014876.41 | -184675.04 | 166 | 175 | 16 | 0 | 9 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PHARR | 0220-04-035 | CAMERON | US 281 | 2022-12-13 | 12496309.81 | 122764.99 | 0 | 12928730.53 | 432420.72 | 460 | 520 | 85 | 0 | 60 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0023-05-086 | UVALDE | US 90 | 2022-12-13 | 1296838.29 | -91677.6 | 0 | 1176693.46 | -120144.83 | 224 | 92 | 0 | 0 | -132 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0100-02-068 | BEXAR | US 181 | 2022-12-13 | 411502.94 | 1182.5 | 0 | 439593.43 | 28090.49 | 155 | 53 | 0 | 0 | -102 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0068-08-067 | HOWARD | US 87 | 2022-12-14 | 6899249.89 | 38675.22 | 0 | 7159704.18 | 260454.29 | 198 | 183 | 0 | 0 | -15 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 2032-03-013 | JONES | FM 600 | 2022-12-14 | 3551479.94 | 0 | 0 | 3711400.82 | 159920.88 | 154 | 152 | 0 | 0 | -2 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0919-03-060 | HARRISON | CR | 2022-12-14 | 481045.3 | 0 | 0 | 474560 | -6485.3 | 70 | 70 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0919-22-034 | MARION | CR | 2022-12-14 | 324588.61 | 0 | 0 | 306754.71 | -17833.9 | 64 | 67 | 0 | 0 | 3 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0188-09-042 | FORT BEND | FM 723 | 2022-12-14 | 2399431.61 | 43895.3 | 0 | 2327668.51 | -71763.1 | 151 | 153 | 2 | 0 | 2 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0838-03-024 | FORT BEND | FM 361 | 2022-12-14 | 7225989.16 | 13711.26 | 0 | 7756177.04 | 530187.88 | 180 | 180 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANTONIO | 0024-07-063 | BEXAR | US 90 | 2022-12-14 | 2885970.95 | 182068.62 | 0 | 3079965.28 | 193994.33 | 125 | 122 | 0 | 0 | -3 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0015-13-378 | TRAVIS | IH 35 | 2022-12-15 | 42617265.21 | 6079308 | 0 | 50644839.97 | 8027574.76 | 594 | 816 | 183 | 0 | 222 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
BEAUMONT | 0882-02-059 | ORANGE | FM 1006 | 2022-12-15 | 403662 | 33430 | 0 | 427650.85 | 23988.85 | 39 | 63 | 35 | 0 | 24 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 2845-01-022 | COLLIN | FM 455 | 2022-12-15 | 4616813.51 | 4293.05 | 0 | 4506375.04 | -110438.47 | 276 | 266 | 0 | 0 | -10 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 3236-02-012 | COLLIN | FM 3133 | 2022-12-15 | 5929503.19 | 73588.86 | 0 | 5393763.47 | -535739.72 | 369 | 343 | 0 | 0 | -26 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0543-02-065 | FORT BEND | FM 359 | 2022-12-15 | 18950219.54 | 569852.81 | 37839.81 | 20107076.72 | 1119017.37 | 300 | 285 | 0 | 0 | -15 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | MEDIUM | FY23
LUFKIN | 0063-06-099 | SHELBY | US 96 | 2022-12-15 | 3364209.01 | 44241.97 | 0 | 3352138.28 | -12070.73 | 304 | 307 | 1 | 0 | 3 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PARIS | 0901-29-096 | LAMAR | VA | 2022-12-15 | 2262253.23 | 0 | 0 | 2334847.57 | 72594.34 | 125 | 120 | 0 | 0 | -5 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 0420-02-047 | JACKSON | SH 172 | 2022-12-15 | 1200898 | 17767.48 | 0 | 1206285.48 | 5387.48 | 210 | 177 | 0 | 0 | -33 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0334-03-021 | LEE | FM 696 | 2022-12-16 | 2187752.94 | 35491.23 | 0 | 2206446.48 | 18693.54 | 184 | 182 | 2 | 0 | -2 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 1202-01-020 | WILLIAMSON | FM 972 | 2022-12-16 | 8984216.45 | -218049.04 | 0 | 8453554.23 | -530662.22 | 450 | 516 | 7 | 0 | 66 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 0047-04-036 | COLLIN | SH 5 | 2022-12-16 | 14495345.49 | 0 | 0 | 13802386.25 | -692959.24 | 223 | 213 | 0 | 0 | -10 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 2352-02-023 | DENTON | FM 2449 | 2022-12-16 | 5902974.49 | 235185.18 | 0 | 5933636.48 | 30661.99 | 301 | 275 | 5 | 0 | -26 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0902-00-204 | TARRANT | VA | 2022-12-16 | 3553920 | 88945.95 | 0 | 3642865.95 | 88945.95 | 365 | 365 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 1685-05-115 | HARRIS | SH 6 | 2022-12-16 | 1616649.76 | 13518 | 0 | 1980486.76 | 363837 | 53 | 70 | 0 | 0 | 17 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
WICHITA FALLS | 0134-01-025 | YOUNG | SH 251 | 2022-12-16 | 2299229 | 428750 | 0 | 2703928.6 | 404699.6 | 253 | 326 | 40 | 0 | 73 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0151-06-149 | TRAVIS | US 183 | 2022-12-19 | 5815911.25 | 1184117.71 | 323767.62 | 6964455.75 | 824776.88 | 112 | 213 | 101 | 0 | 101 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
BEAUMONT | 0920-38-253 | JEFFERSON | PW | 2022-12-19 | 151736.3 | 49165.17 | 0 | 200372.73 | 48636.43 | 13 | 25 | 6 | 0 | 12 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 1096-01-065 | HARDIN | FM 770 | 2022-12-19 | 2206601.53 | 84440.69 | 0 | 2039009.27 | -167592.26 | 128 | 137 | 3 | 0 | 9 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0322-01-051 | BASTROP | SH 95 | 2022-12-20 | 1850411.75 | 7101.13 | 0 | 1841554.48 | -8857.27 | 118 | 115 | 0 | 0 | -3 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 0275-01-180 | POTTER | IH 40 | 2022-12-21 | 50440638.56 | 1543453.67 | 0 | 52265796.36 | 1825157.8 | 696 | 962 | 178 | 0 | 266 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | LARGE | FY23
DALLAS | 2374-04-049 | DALLAS | IH 20 | 2022-12-21 | 54241512.3 | 2557354.8 | 0 | 56103869.52 | 1862357.22 | 791 | 1033 | 243 | 0 | 242 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | Y | N | N | LARGE | FY23
EL PASO | 2326-01-029 | EL PASO | FM 2529 | 2022-12-21 | 1569799.2 | 38240 | 0 | 1644427.58 | 74628.38 | 190 | 189 | 0 | 0 | -1 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0079-05-061 | ERATH | US 67 | 2022-12-21 | 11670677.76 | 1319126.7 | 0 | 11395608.4 | -275069.36 | 115 | 100 | 0 | 0 | -15 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 1605-02-023 | TARRANT | FM 1886 | 2022-12-21 | 1656779.12 | 417430.04 | 0 | 2120333.81 | 463554.69 | 107 | 114 | 5 | 0 | 7 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANTONIO | 0915-00-199 | BEXAR | VA | 2022-12-21 | 282660.55 | 0 | 0 | 1247404.32 | 964743.77 | 105 | 74 | 0 | 0 | -31 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0060-02-034 | BOWIE | SH 8 | 2022-12-22 | 7775365.15 | 353195.7 | 0 | 7361204.27 | -414160.88 | 64 | 51 | 0 | 0 | -13 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0530-01-007 | BASTROP | PR 1A | 2022-12-22 | 941090.5 | 52115.68 | 0 | 883801.98 | -57288.52 | 58 | 73 | 17 | 0 | 15 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0914-00-401 | TRAVIS | VA | 2022-12-22 | 1378704 | 187461.46 | 0 | 1529199.67 | 150495.67 | 300 | 229 | 0 | 0 | -71 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 0065-14-028 | HARDIN | BU 96-F | 2022-12-22 | 10965722.02 | -903401.28 | 0 | 9561917.65 | -1403804.37 | 136 | 91 | 0 | 0 | -45 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 1744-02-013 | JACKSON | FM 1862 | 2022-12-22 | 5207582.11 | -31594.77 | 0 | 5011429.6 | -196152.51 | 165 | 152 | 0 | 0 | -13 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0072-06-074 | KENDALL | IH 10 | 2022-12-26 | 18335085.15 | 1201323.96 | 0 | 19936804.5 | 1601719.35 | 603 | 685 | 82 | 0 | 82 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
AMARILLO | 2494-01-015 | POTTER | RM 2381 | 2022-12-27 | 2407611.82 | 4000 | 0 | 2316634.06 | -90977.76 | 174 | 135 | 0 | 0 | -39 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0919-00-091 | CASS | Various | 2022-12-27 | 167042 | 0 | 0 | 165492 | -1550 | 20 | 4 | 0 | 0 | -16 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0204-02-033 | WILLIAMSON | US 79 | 2022-12-27 | 874836.85 | 42518.6 | 0 | 955369.59 | 80532.74 | 143 | 115 | 0 | 0 | -28 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PARIS | 1495-01-009 | HUNT | FM 1566 | 2022-12-27 | 3969724.28 | 5709.75 | 0 | 3908569.63 | -61154.65 | 246 | 416 | 0 | 0 | 170 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
WICHITA FALLS | 0013-13-005 | MONTAGUE | SH 101 | 2022-12-27 | 8024250.28 | 0 | 0 | 8100128.11 | 75877.83 | 63 | 65 | 0 | 0 | 2 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0974-02-017 | CALLAHAN | FM 604 | 2022-12-28 | 12420200.96 | 726933.48 | 0 | 13180927.13 | 760726.17 | 103 | 99 | 0 | 0 | -4 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 1526-01-019 | SCURRY | FM 1606 | 2022-12-28 | 2902279.05 | 0 | 0 | 2935581.46 | 33302.41 | 238 | 259 | 0 | 0 | 21 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
EL PASO | 0002-07-054 | HUDSPETH | IH 10 | 2022-12-28 | 2841820.2 | 38356.11 | 0 | 2973664.55 | 131844.35 | 240 | 152 | 0 | 0 | -88 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANTONIO | 0016-05-119 | COMAL | IH 35 | 2022-12-28 | 24566550.72 | 2039295.38 | 0 | 27420566.68 | 2854015.96 | 441 | 739 | 240 | 0 | 298 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | Y | Y | MEDIUM | FY23
SAN ANTONIO | 0511-02-026 | COMAL | RM 32 | 2022-12-28 | 1044625.23 | 0 | 0 | 1077971.8 | 33346.57 | 192 | 192 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-14-046 | WILSON | CR | 2022-12-28 | 522735.85 | 32943.61 | 0 | 547999.24 | 25263.39 | 116 | 135 | 22 | 0 | 19 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-14-047 | WILSON | CR | 2022-12-28 | 577070.2 | -0.01 | 0 | 584481.38 | 7411.18 | 115 | 134 | 0 | 0 | 19 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUBBOCK | 0905-00-102 | LUBBOCK | VA | 2022-12-29 | 1005150.6 | 0 | 0 | 1069734.1 | 64583.5 | 90 | 79 | 0 | 0 | -11 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 0911-00-076 | ANGELINA | VA | 2022-12-29 | 5294835.55 | 17456.04 | 0 | 5103022.81 | -191812.74 | 382 | 367 | 4 | 0 | -15 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0484-01-025 | JONES | FM 707 | 2022-12-30 | 2265797.7 | 0 | 0 | 2243827.38 | -21970.32 | 129 | 100 | 0 | 0 | -29 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0902-38-120 | PARKER | CR | 2022-12-30 | 1069862.2 | 0 | 0 | 1055181.11 | -14681.09 | 124 | 121 | 0 | 0 | -3 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | Y | N | N | SMALL | FY23
PHARR | 1804-01-078 | HIDALGO | SS 115 | 2022-12-30 | 338037.6 | 34800 | 0 | 353723.73 | 15686.13 | 75 | 75 | 0 | 0 | 0 | DECEMBER | DEC-22 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PARIS | 3370-01-008 | HOPKINS | FM 3389 | 2023-01-01 | 3763142.18 | 72485.61 | 0 | 3865347.42 | 102205.24 | 286 | 278 | 0 | 0 | -8 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ODESSA | 0463-06-028 | WINKLER | SH 302 | 2023-01-02 | 63338504.77 | -1916232.8 | 0 | 64686108.75 | 1347603.98 | 489 | 500 | 12 | 0 | 11 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | LARGE | FY23
ODESSA | 0906-00-230 | ECTOR | VA | 2023-01-02 | 1741329 | 0 | 0 | 1725144.51 | -16184.49 | 281 | 283 | 0 | 0 | 2 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0663-02-010 | TAYLOR | FM 707 | 2023-01-03 | 1084713.4 | -28460 | 0 | 948741.25 | -135972.15 | 130 | 130 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUBBOCK | 0053-01-130 | LUBBOCK | US 84 | 2023-01-03 | 1595824.73 | 0 | 0 | 1563645.61 | -32179.12 | 17 | 9 | 0 | 0 | -8 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 0176-02-127 | ANGELINA | US 59 | 2023-01-03 | 281620 | 0 | 0 | 267997.6 | -13622.4 | 80 | 80 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANGELO | 0907-13-012 | RUNNELS | CR | 2023-01-03 | 2384074.17 | 59123.03 | 0 | 2401846.32 | 17772.15 | 216 | 254 | 15 | 0 | 38 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
BROWNWOOD | 0708-01-032 | EASTLAND | FM 101 | 2023-01-05 | 413274.25 | 2684 | 0 | 397303.25 | -15971 | 68 | 31 | 0 | 0 | -37 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
WICHITA FALLS | 0224-03-060 | MONTAGUE | US 287 | 2023-01-05 | 3203181 | 202245.6 | 0 | 3729012.5 | 525831.5 | 51 | 41 | 0 | 0 | -10 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0902-20-110 | WISE | CR | 2023-01-06 | 769194.6 | 15521.96 | 0 | 802383.98 | 33189.38 | 107 | 92 | 0 | 0 | -15 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 0911-04-087 | POLK | CR | 2023-01-06 | 1594107 | -28185.91 | 0 | 1545162.21 | -48944.79 | 148 | 140 | 0 | 0 | -8 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 3417-02-024 | WILLIAMSON | FM 734 | 2023-01-08 | 1965251.62 | 14826.95 | 0 | 2279158.1 | 313906.48 | 62 | 56 | 0 | 0 | -6 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
FORT WORTH | 3516-01-019 | PARKER | FM 3325 | 2023-01-09 | 714693.59 | 6776.52 | 0 | 643415.05 | -71278.54 | 28 | 41 | 13 | 0 | 13 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUBBOCK | 0052-01-044 | PARMER | US 70 | 2023-01-09 | 3220733.83 | 230680.32 | 0 | 3322208.65 | 101474.82 | 118 | 144 | 60 | 0 | 26 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUBBOCK | 0905-00-118 | LUBBOCK | VA | 2023-01-09 | 451441.8 | 85230 | 0 | 742893.11 | 291451.31 | 60 | 74 | 20 | 0 | 14 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BROWNWOOD | 0480-08-027 | SAN SABA | FM 45 | 2023-01-10 | 5068391.33 | 37971.9 | 0 | 5117454.92 | 49063.59 | 306 | 355 | 50 | 0 | 49 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
CHILDRESS | 0043-02-077 | HARDEMAN | US 287 | 2023-01-10 | 2452566.08 | 0 | 0 | 2562876.72 | 110310.64 | 28 | 28 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0011-01-038 | TAYLOR | SH 351 | 2023-01-11 | 4596548 | 35839.92 | 0 | 4177120.13 | -419427.87 | 193 | 336 | 0 | 0 | 143 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 1198-01-022 | BURNET | RM 963 | 2023-01-11 | 7444233.3 | 302694.02 | 0 | 7187517.08 | -256716.22 | 454 | 495 | 43 | 0 | 41 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 0091-06-059 | DALLAS | SH 289 | 2023-01-11 | 1235537.08 | 0 | 0 | 1268103.48 | 32566.4 | 300 | 243 | 0 | 0 | -57 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0912-00-580 | HARRIS | VA | 2023-01-11 | 877513.25 | -21562.65 | 7502.1 | 826498.78 | -58516.57 | 140 | 140 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 0379-02-032 | POTTER | SH 136 | 2023-01-12 | 9215103.34 | 175078.82 | 0 | 9650151.37 | 435048.03 | 409 | 186 | 3 | 0 | -223 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
WICHITA FALLS | 0043-09-144 | WICHITA | IH 44 | 2023-01-12 | 3356260.98 | 600508.9 | 0 | 4321372.24 | 965111.26 | 68 | 122 | 54 | 0 | 54 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0265-10-032 | BASTROP | SL 150 | 2023-01-13 | 1115938.48 | 183639.03 | 0 | 1171961.88 | 56023.4 | 24 | 24 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
AUSTIN | 1539-02-034 | TRAVIS | FM 1626 | 2023-01-13 | 2285064.75 | 22557.36 | 0 | 2130498.39 | -154566.36 | 103 | 81 | 0 | 0 | -22 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 0173-04-060 | KAUFMAN | SH 34 | 2023-01-13 | 1399629.03 | 202417.3 | 0 | 1449415.17 | 49786.14 | 166 | 209 | 16 | 0 | 43 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 0697-03-029 | KAUFMAN | FM 429 | 2023-01-13 | 6206913.08 | 518754.76 | 0 | 6223403.73 | 16490.65 | 226 | 238 | 12 | 0 | 12 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0014-03-101 | JOHNSON | IH 35W | 2023-01-13 | 1069599.97 | 0 | 0 | 1091307.53 | 21707.56 | 180 | 112 | 0 | 0 | -68 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ODESSA | 0003-06-097 | REEVES | IH 20 | 2023-01-13 | 7405997.27 | 1573228.88 | 0 | 7070066.34 | -335930.93 | 48 | 37 | 10 | 0 | -11 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PHARR | 0698-03-099 | HIDALGO | FM 88 | 2023-01-13 | 4998520.95 | -70557.5 | 0 | 5477774.09 | 479253.14 | 98 | 136 | 0 | 0 | 38 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0914-33-078 | HAYS | VA | 2023-01-14 | 1519610 | 571076.75 | 745108.9 | 2018342.7 | -246376.2 | 95 | 147 | 70 | 10 | 42 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0296-01-038 | SCURRY | US 180 | 2023-01-17 | 7417904.36 | 18634.75 | 0 | 8075643.75 | 657739.39 | 151 | 145 | 0 | 0 | -6 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-11-032 | KENDALL | VA | 2023-01-17 | 723891.2 | -57729.63 | 0 | 533168.25 | -190722.95 | 85 | 84 | 0 | 0 | -1 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
TYLER | 0191-02-068 | CHEROKEE | US 69 | 2023-01-17 | 802060.04 | 23973.6 | 0 | 783245.98 | -18814.06 | 80 | 77 | 0 | 0 | -3 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
TYLER | 0198-07-014 | CHEROKEE | SH 204 | 2023-01-17 | 13705298.28 | -218238.26 | 0 | 13047264.96 | -658033.32 | 206 | 206 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
PARIS | 0221-03-070 | RED RIVER | US 271 | 2023-01-18 | 4563506.49 | -445390.47 | 0 | 4375124.17 | -188382.32 | 96 | 98 | 3 | 0 | 2 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 0904-00-197 | POTTER | IH 40 | 2023-01-19 | 4796527 | -187978.1 | 0 | 4782891.6 | -13635.4 | 200 | 187 | 15 | 0 | -13 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0110-02-027 | MONTGOMERY | SH 75 | 2023-01-19 | 5663719.67 | 527885.95 | 0 | 6089518.11 | 425798.44 | 145 | 390 | 77 | 0 | 245 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 1685-05-108 | HARRIS | SH 6 | 2023-01-19 | 2492972.1 | 533995.63 | 0 | 3291523.02 | 798550.92 | 525 | 524 | 0 | 0 | -1 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 1375-01-011 | CALDWELL | FM 1322 | 2023-01-20 | 4094875.14 | 2555.83 | 0 | 3973148.63 | -121726.51 | 80 | 77 | 0 | 0 | -3 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 0064-04-043 | SAN AUGUSTINE | SH 21 | 2023-01-20 | 11757209.31 | -1046104.58 | 0 | 9628674.44 | -2128534.87 | 122 | 112 | 0 | 0 | -10 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0096-09-080 | HARRISON | US 80 | 2023-01-23 | 2903146.62 | 148200.18 | 0 | 3075871.82 | 172725.2 | 111 | 111 | 0 | 0 | 0 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANGELO | 0907-00-170 | TOM GREEN | VA | 2023-01-23 | 6779028.06 | -452651.4 | 0 | 6383057.79 | -395970.27 | 412 | 609 | 0 | 0 | 197 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
YOAKUM | 0432-01-065 | CALHOUN | SH 185 | 2023-01-23 | 1252351.57 | 1978.66 | 0 | 1164141.23 | -88210.34 | 75 | 74 | 0 | 0 | -1 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0720-03-134 | HARRIS | SH 249 | 2023-01-24 | 3339515.8 | 1531658.54 | 0 | 4825437.16 | 1485921.36 | 360 | 393 | 70 | 0 | 33 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 3158-01-031 | MONTGOMERY | FM 3083 | 2023-01-24 | 13080676.41 | 694135.38 | 0 | 13379379.05 | 298702.64 | 378 | 795 | 85 | 0 | 417 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PHARR | 0039-17-198 | HIDALGO | IH 2 | 2023-01-24 | 9929404.5 | -425680.76 | 0 | 10049323.27 | 119918.77 | 68 | 126 | 10 | 0 | 58 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
WACO | 3534-01-012 | BELL | SH 201 | 2023-01-24 | 1874463.14 | -130983.66 | 0 | 1902345.1 | 27881.96 | 90 | 73 | 0 | 0 | -17 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
ATLANTA | 0222-01-056 | TITUS | SH 49 | 2023-01-25 | 3739806.75 | 98573.2 | 0 | 3764658.87 | 24852.12 | 257 | 255 | 0 | 0 | -2 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
LUFKIN | 0911-00-117 | ANGELINA | VA | 2023-01-25 | 505300 | 73137.2 | 0 | 579740.27 | 74440.27 | 50 | 126 | 90 | 0 | 76 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
TYLER | 0910-00-120 | SMITH | VA | 2023-01-25 | 471301.78 | -10931.6 | 0 | 475221.09 | 3919.31 | 91 | 140 | 9 | 0 | 49 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 0904-00-195 | POTTER | VA | 2023-01-26 | 3940370.9 | 38309.2 | 0 | 3978467.4 | 38096.5 | 171 | 268 | 20 | 0 | 97 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
PARIS | 0730-01-011 | RED RIVER | FM 195 | 2023-01-26 | 867803.7 | 15610.38 | 0 | 886157.58 | 18353.88 | 160 | 209 | 25 | 0 | 49 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 1048-03-011 | ELLIS | FM 780 | 2023-01-27 | 6868176.57 | 283963.75 | 0 | 6742189.52 | -125987.05 | 263 | 275 | 12 | 0 | 12 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
EL PASO | 2552-03-058 | EL PASO | SL 375 | 2023-01-27 | 32640631.27 | -556616.27 | 0 | 32603922.32 | -36708.95 | 445 | 778 | 148 | 0 | 333 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | MEDIUM | FY23
TYLER | 0495-03-065 | VAN ZANDT | IH 20 | 2023-01-27 | 3490252.77 | 122587.4 | 0 | 4025655 | 535402.23 | 190 | 251 | 107 | 0 | 61 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | Y | N | SMALL | FY23
WACO | 0231-03-147 | BELL | IH 14 | 2023-01-27 | 3098000 | 1120970.25 | 0 | 4403599.52 | 1305599.52 | 240 | 306 | 66 | 0 | 66 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0389-13-061 | HARRIS | SH 146 | 2023-01-30 | 1750062 | 189902.27 | 0 | 2158811.65 | 408749.65 | 105 | 96 | 0 | 0 | -9 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-00-232 | BEXAR | VA | 2023-01-30 | 1637297 | 17450.57 | 11537.87 | 1715884.31 | 67049.44 | 320 | 132 | 0 | 0 | -188 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-12-625 | BEXAR | CS | 2023-01-30 | 1494379.75 | 31040.7 | 0 | 1594277.28 | 99897.53 | 296 | 93 | 0 | 0 | -203 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
WICHITA FALLS | 0156-04-125 | WICHITA | US 82 | 2023-01-30 | 7059433.85 | 97613.11 | 0 | 7170404.24 | 110970.39 | 102 | 122 | 7 | 0 | 20 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 0346-02-016 | JACKSON | SH 111 | 2023-01-30 | 1235556.27 | 8909.18 | 0 | 1222627.44 | -12928.83 | 45 | 29 | 0 | 0 | -16 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BROWNWOOD | 0007-06-084 | EASTLAND | IH 20 | 2023-01-31 | 75522594.12 | 4113271.05 | 0 | 83170947.74 | 7648353.62 | 914 | 1251 | 337 | 0 | 337 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | Y | Y | LARGE | FY23
FORT WORTH | 0257-06-027 | ERATH | SH 6 | 2023-01-31 | 5364691 | 1279055.77 | 0 | 6682240.66 | 1317549.66 | 288 | 367 | 80 | 0 | 79 | JANUARY | JAN-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0919-13-018 | PANOLA | CR | 2023-02-01 | 489997.75 | 0 | 0 | 483891.98 | -6105.77 | 64 | 57 | 0 | 0 | -7 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ODESSA | 0906-00-218 | ECTOR | VA | 2023-02-01 | 866887.83 | 0 | 0 | 886956.31 | 20068.48 | 55 | 59 | 0 | 0 | 4 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ODESSA | 1870-01-035 | ECTOR | FM 2020 | 2023-02-01 | 8342144.9 | -15390 | 0 | 8576959.82 | 234814.92 | 232 | 249 | 0 | 0 | 17 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
BEAUMONT | 0065-02-056 | JASPER | US 96 | 2023-02-03 | 104464.3 | 11819.67 | 0 | 117014.97 | 12550.67 | 17 | 16 | 4 | 0 | -1 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 0499-02-031 | NEWTON | SH 12 | 2023-02-03 | 1509217.56 | -294324.75 | 0 | 1270023.26 | -239194.3 | 47 | 63 | 4 | 0 | 16 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 0432-01-064 | CALHOUN | SH 185 | 2023-02-03 | 1937924.62 | -88691.49 | 0 | 1780602.9 | -157321.72 | 143 | 135 | 0 | 0 | -8 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 0025-06-056 | GONZALES | UA 90 | 2023-02-04 | 2603773.77 | 157386.92 | 0 | 2693036.83 | 89263.06 | 138 | 138 | 0 | 0 | 0 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
YOAKUM | 0287-03-032 | GONZALES | SH 80 | 2023-02-04 | 8087778.91 | 36338.63 | 0 | 8174013.63 | 86234.72 | 257 | 257 | 0 | 0 | 0 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 3278-01-003 | BLANCO | RM 473 | 2023-02-06 | 3837576.3 | 342243.35 | 0 | 4198484.67 | 360908.37 | 180 | 228 | 49 | 0 | 48 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANGELO | 0070-02-091 | TOM GREEN | US 87 | 2023-02-06 | 9737925.71 | 298086.03 | 0 | 9744575.12 | 6649.41 | 113 | 152 | 35 | 0 | 39 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANGELO | 0907-00-198 | TOM GREEN | VA | 2023-02-06 | 2812849.2 | 0 | 0 | 2812658.2 | -191 | 94 | 106 | 0 | 0 | 12 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 0951-01-075 | LIBERTY | SH 105 | 2023-02-07 | 517178.94 | 0 | 0 | 532432.15 | 15253.21 | 28 | 61 | 18 | 0 | 33 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
EL PASO | 0374-04-035 | HUDSPETH | US 62 | 2023-02-07 | 1312912.61 | 22368.16 | 0 | 1357410.52 | 44497.91 | 100 | 117 | 17 | 0 | 17 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0179-02-087 | BRAZORIA | SH 35 | 2023-02-07 | 10077739.5 | 1142464.23 | 0 | 12149866.57 | 2072127.07 | 170 | 168 | 0 | 0 | -2 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0914-33-064 | HAYS | CR | 2023-02-08 | 1535478.5 | 32134.58 | 0 | 1486601.42 | -48877.08 | 50 | 56 | 6 | 0 | 6 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 0307-01-149 | JEFFERSON | SH 87 | 2023-02-08 | 2734996.75 | 756717.53 | 0 | 3617344.72 | 882347.97 | 180 | 178 | 0 | 0 | -2 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 1464-01-018 | CHAMBERS | FM 1663 | 2023-02-08 | 736393.5 | 58194.18 | 0 | 737890.41 | 1496.91 | 40 | 75 | 10 | 0 | 35 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0598-02-118 | BRAZORIA | SH 288 | 2023-02-08 | 9211640.25 | 55660.43 | 0 | 9026555.56 | -185084.69 | 183 | 149 | 0 | 0 | -34 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0914-00-452 | TRAVIS | VA | 2023-02-09 | 3887917.5 | -666561.4 | 0 | 3054085.37 | -833832.13 | 285 | 342 | 4 | 0 | 57 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 0173-01-050 | ELLIS | SH 34 | 2023-02-10 | 1371422.7 | 527624.15 | 0 | 1835080.49 | 463657.79 | 131 | 207 | 37 | 0 | 76 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0134-06-052 | WISE | FM 1810 | 2023-02-10 | 10846609.87 | -328634.38 | 0 | 10326106.58 | -520503.29 | 320 | 409 | 89 | 0 | 89 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANTONIO | 0142-09-044 | KENDALL | RM 473 | 2023-02-10 | 3777154.65 | 128905.66 | 0 | 3845415.7 | 68261.05 | 227 | 222 | 0 | 0 | -5 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 0053-07-040 | SCURRY | US 84 | 2023-02-13 | 3245689.67 | 115282.9 | 0 | 3158567.84 | -87121.83 | 141 | 151 | 11 | 0 | 10 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 0090-09-006 | OLDHAM | BI 40-- | 2023-02-13 | 7204392 | 622230.28 | 0 | 8071385.78 | 866993.78 | 258 | 351 | 70 | 0 | 93 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0259-02-051 | SOMERVELL | US 67 | 2023-02-13 | 13062197.13 | 2798981.4 | 0 | 15130396.57 | 2068199.44 | 281 | 364 | 103 | 0 | 83 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
ODESSA | 0005-04-076 | MARTIN | IH 20 | 2023-02-13 | 30634104.46 | 2946365.39 | 0 | 35068048.55 | 4433944.09 | 494 | 514 | 40 | 0 | 20 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
ODESSA | 1188-02-089 | MIDLAND | SL 250 | 2023-02-13 | 22509209.87 | 2954792.32 | 0 | 25175545.3 | 2666335.43 | 438 | 477 | 78 | 0 | 39 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
SAN ANTONIO | 0025-02-160 | BEXAR | IH 10 | 2023-02-13 | 108886144.24 | 7193747.72 | 0 | 119497407.5 | 10611263.26 | 700 | 791 | 97 | 0 | 91 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | Y | Y | LARGE | FY23
YOAKUM | 0446-01-048 | LAVACA | US 90A | 2023-02-13 | 793103.5 | 21432 | 0 | 805941.55 | 12838.05 | 90 | 200 | 8 | 0 | 110 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0265-04-069 | BASTROP | SH 21 | 2023-02-14 | 1972086.96 | 0 | 0 | 2209472.64 | 237385.68 | 54 | 49 | 0 | 0 | -5 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANTONIO | 0915-00-229 | BEXAR | VA | 2023-02-14 | 916531.15 | 0 | 0 | 922833.68 | 6302.53 | 256 | 237 | 0 | 0 | -19 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0259-01-036 | ERATH | US 67 | 2023-02-15 | 15651725.24 | 3409823.31 | 0 | 18372617.31 | 2720892.07 | 214 | 263 | 62 | 0 | 49 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
HOUSTON | 0110-05-132 | HARRIS | IH 45 | 2023-02-15 | 1723384.19 | 106959.85 | 0 | 1860528.38 | 137144.19 | 75 | 71 | 29 | 0 | -4 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0976-03-112 | GALVESTON | FM 518 | 2023-02-15 | 1902321.25 | 10934.61 | 0 | 1882185.71 | -20135.54 | 188 | 147 | 0 | 0 | -41 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0392-02-097 | UPSHUR | US 259 | 2023-02-16 | 1983306.25 | 106706.48 | 0 | 2125155.45 | 141849.2 | 57 | 96 | 4 | 0 | 39 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ATLANTA | 0919-03-063 | HARRISON | CS | 2023-02-16 | 309959.6 | 102922.25 | 0 | 487074.37 | 177114.77 | 39 | 38 | 0 | 0 | -1 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
EL PASO | 2121-06-054 | HUDSPETH | IH 10 | 2023-02-16 | 1895554.8 | 266650.7 | 0 | 2222308.25 | 326753.45 | 52 | 47 | 0 | 0 | -5 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0179-03-034 | BRAZORIA | SH 35 | 2023-02-16 | 5289598.34 | 595910.04 | 0 | 5774904.34 | 485306 | 85 | 194 | 13 | 0 | 109 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
WICHITA FALLS | 1837-01-013 | ARCHER | FM 1954 | 2023-02-16 | 4925489.02 | 346164.75 | 0 | 5764517.17 | 839028.15 | 212 | 228 | 50 | 0 | 16 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 1201-01-014 | WILLIAMSON | FM 970 | 2023-02-17 | 5125069.16 | 432100.05 | 0 | 5557607.57 | 432538.41 | 386 | 406 | 7 | 0 | 20 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
DALLAS | 0918-47-148 | DALLAS | CS | 2023-02-17 | 1766278.5 | 0 | 0 | 1804210.03 | 37931.53 | 165 | 166 | 9 | 0 | 1 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0902-38-129 | PARKER | CS | 2023-02-17 | 919705.12 | 115986.68 | 0 | 1086194.31 | 166489.19 | 98 | 130 | 52 | 0 | 32 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 2635-01-038 | POTTER | SL 335 | 2023-02-21 | 10715637.22 | -66085.36 | 0 | 11487174.04 | 771536.82 | 99 | 186 | 17 | 0 | 87 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AUSTIN | 0016-03-103 | HAYS | IH 35 | 2023-02-21 | 31736977.23 | 3858714.59 | 0 | 36608682.97 | 4871705.74 | 531 | 577 | 67 | 0 | 46 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
BRYAN | 0675-07-101 | WALKER | IH 45 | 2023-02-21 | 116878722.89 | 4082644.07 | 0 | 123422417.8 | 6543694.91 | 840 | 961 | 121 | 0 | 121 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | Y | Y | LARGE | FY23
LUFKIN | 0911-28-049 | HOUSTON | CR | 2023-02-21 | 1693606.18 | 0 | 0 | 1678759.05 | -14847.13 | 152 | 182 | 0 | 0 | 30 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0017-04-043 | ATASCOSA | IH 35 | 2023-02-21 | 14999998.31 | 1545863.32 | 0 | 16581156.15 | 1581157.84 | 205 | 203 | 0 | 0 | -2 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
SAN ANTONIO | 0915-15-097 | KERR | CR | 2023-02-22 | 596018.13 | -9232.71 | 0 | 579852.84 | -16165.29 | 120 | 108 | 0 | 0 | -12 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
AMARILLO | 0275-01-215 | POTTER | IH 40 | 2023-02-23 | 4539711.25 | 412227.57 | 0 | 4985314.61 | 445603.36 | 383 | 424 | 28 | 0 | 41 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ABILENE | 1872-02-019 | HOWARD | FM 846 | 2023-02-24 | 995017.15 | 0 | 0 | 999078.27 | 4061.12 | 24 | 19 | 0 | 0 | -5 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
BEAUMONT | 0508-04-162 | JEFFERSON | SH 73 | 2023-02-24 | 18747291.34 | 619957.5 | 0 | 19602419.97 | 855128.63 | 410 | 515 | 0 | 0 | 105 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | MEDIUM | FY23
LUFKIN | 0177-02-095 | SAN JACINTO | US 59 | 2023-02-24 | 1479910.36 | 0 | 0 | 1487365.49 | 7455.13 | 25 | 63 | 40 | 0 | 38 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
FORT WORTH | 0013-06-047 | WISE | US 81 | 2023-02-27 | 2749994.33 | 69313.8 | 0 | 2956899.68 | 206905.35 | 171 | 171 | 0 | 0 | 0 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
ODESSA | 0005-03-079 | MIDLAND | BI 20-E | 2023-02-27 | 11162709.03 | 87412.41 | 0 | 10630860.86 | -531848.17 | 230 | 240 | 35 | 0 | 10 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
SAN ANTONIO | 0521-05-118 | BEXAR | IH 410 | 2023-02-27 | 73929401.71 | 5197980.38 | 0 | 79313296.17 | 5383894.46 | 1000 | 1163 | 179 | 0 | 163 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | Y | N | N | LARGE | FY23
WICHITA FALLS | 0043-05-110 | WILBARGER | US 70 | 2023-02-27 | 8701328.89 | 162441.19 | 0 | 8728444.02 | 27115.13 | 263 | 309 | 41 | 0 | 46 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | SMALL | FY23
CORPUS CHRISTI | 0916-26-022 | GOLIAD | CR | 2023-02-28 | 459835.5 | 0 | 0 | 445821.58 | -14013.92 | 86 | 76 | 0 | 0 | -10 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | N | SMALL | FY23
HOUSTON | 0050-08-087 | HARRIS | US 290 | 2023-02-28 | 135455755.98 | 28856592.62 | 667578.12 | 167766338.85 | 31643004.75 | 1052 | 1669 | 628 | 0 | 617 | FEBRUARY | FEB-23 | 2019-04-01 | Q2 | N | N | Y | LARGE | FY23

## LINE_GRAPH_DATA (hidden)
COUNTIFS(FINL,">="&B4-DAY(B4)+1,FINL,"<="&EOMONTH(B4,0))
FY 2021 Monthly Measures | [9 empty] | YTD
Month | Total Contracts | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO | BUD > 10% | On Budget | BUD_CO > 10% | On Budget W/CO | Time > 10% | On Time | Time_CO > 10% | On Time W/CO
SEP-22 | 62 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
OCT-22 | 60 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
NOV-22 | 45 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
DEC-22 | 84 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
JAN-23 | 64 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
FEB-23 | 58 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
MAR-23 | 0 | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #VALUE! | #N/A | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A
APR-23 | 0 | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #VALUE! | #N/A | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A
MAY-23 | 0 | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #VALUE! | #N/A | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A
JUN-23 | 0 | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #VALUE! | #N/A | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A
JUL-23 | 0 | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #VALUE! | #N/A | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A
AUG-23 | 0 | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #VALUE! | #N/A | #N/A | #VALUE! | #N/A | #N/A | #N/A | #N/A
FY23 | 373 | #VALUE! | #VALUE! | 0 | 0% | 0 | 0% | 0 | 0% | #VALUE! | #VALUE! | 0 | 0% | 0 | 0% | 0 | 0%
|  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0!

## Summary Previous FYs (hidden)
CONSTRUCTION SUMMARY PERFORMANCE REPORT | [12 empty] | 5- YEAR AVERAGES
FY | Projects Accepted | Percent On Budget | Percent On Time | Percent On Time Previous | Projects Awarded | Awarded Amounts Billions | Estimated Amounts Billions | Amounts Over / (Under) the Estimate | Percent Over the Estimate | Dollars per Project | Awarded Amounts | Estimated Amounts | Awarded Amounts | Estimated Amounts | Percent Over the Estimate | Projects Accepted | Projects Awarded
2009 | 802 | 83.92% | 57.11% | 72.57% | 699 | 3.0857 | 3.6429 | -0.5572 | -15.3% | 4414461.6445 | 3085708689.49 | 3642907501.26
2010 | 797 | 84.69% | 65.5% | 77.42% | 1063 | 3.2459 | 3.6441 | -0.39818 | -10.93% | 3053502.9899 | 3245873678.22 | 3644056349
2011 | 872 | 88.99% | 68.17% | 77.18% | 870 | 3.497 | 3.7036 | -0.20654 | -5.577% | 4019586.1947 | 3497039989.43 | 3703575068.62
2012 | 772 | 87.95% | 67.62% | 76.55% | 685 | 2.9722 | 3.0097 | -0.037491 | -1.246% | 4338962.4606 | 2972189285.54 | 3009680367 | 3.2002 | 3.5001 | -8.567% | 810.75 | 829.25
2013 | 682 | 86.07% | 63.49% | N/A | 797 | 4.2752 | 4.2598 | 0.015356 | 0.3605% | 5364094.8547 | 4275183599.18 | 4259827109.53 | 3.4152 | 3.652 | -6.484% | 785 | 822.8
2014 | 636 | 86.48% | 68.08% | N/A | 757 | 3.8596 | 3.9509 | -0.091307 | -2.311% | 5098575.683 | 3859621792 | 3950928942.48 | 3.57 | 3.7136 | -3.868% | 751.8 | 834.4
2015 | 607 | 86.16% | 63.92% | N/A | 856 | 4.3749 | 4.3622 | 0.012684 | 0.2908% | 5110843.7065 | 4374882212.76 | 4362198207.53 | 3.7958 | 3.8572 | -1.593% | 713.8 | 793
2016 | 711 | 83.4% | 63.29% | N/A | 737 | 4.3375 | 4.4843 | -0.14682 | -3.274% | 5885376.9172 | 4337522787.99 | 4484341769.73 | 3.9639 | 4.0134 | -1.234% | 681.6 | 766.4
2017 | 864 | 80.9% | 62.73% | N/A | 779 | 4.7365 | 5.0552 | -0.31875 | -6.305% | 6080199.4759 | 4736475391.74 | 5055222420.56 | 4.3167 | 4.4225 | -2.392% | 700 | 785.2
2018 | 859 | 83.82% | 64.96% | N/A | 825 | 5.7327 | 5.8693 | -0.13661 | -2.328% | 6948682.4486 | 5732663020.12 | 5869277068.62 | 4.6082 | 4.7444 | -2.87% | 735.4 | 790.8
2019 | 718 | 94.57% | 85.79% | N/A | 895 | 6.5145 | 6.3033 | 0.21118 | 3.35% | 7278753.2179 | 6514484130 | 6303301439 | 4.9259 | 5.0042 | -1.564% | 732.5 | 808.1667
2020 | 373 | #VALUE! | 0% |  |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  |  | 5.1392 | 5.2149 | -1.451% | 688.6667 | 818.4