## Project Information
Utility Conflict Management (UCM) - Project Information
Category | Item | Information
General Project Description | Project Owner | TxDOT
District
Project Name
Project Control CSJ
ROW CSJ
Project Scope
Project Limits
Project Length (miles)
Estimated Construction Cost
Project Timeline | 30% Schematic Completed Date
60% Schematic Completed Date
90% Schematic Completed Date
100% Schematic Completed Date
30% PS&E Completed Date
60% PS&E Completed Date
90% PS&E Completed Date
100% PS&E Completed Date
Ready-to-let (RTL) Date
Letting Date
Environmental Review Type
Environmental Approval Date
NOPCs Sent Date
NORAs Sent Date
Utility Records Research Completed Date
Visible Utility Investigation Completed Date
Geophysical Investigation Completed Date
Utility Exposure Completed Date
QLD (Y/N)
QLC (Y/N)
QLB (Y/N)
QLA (Y/N)
ROW Authorization Date
ROW Acquisition Completed Date
Project Management | Schematic TxDOT Project Manager
Schematic TxDOT Designer
Schematic TxDOT Utility Coordinator
Schematic Prime Consultant
Schematic Prime Consultant Project Manager
Schematic Prime Consultant Designer
Schematic Utility Coordination Consultant
Schematic Utility Coordination Consultant PM
Schematic Utility Investigation Consultant
Schematic Utility Investigation Consultant PM
PS&E TxDOT Project Manager
PS&E TxDOT Designer
PS&E TxDOT Utility Coordinator
PS&E Prime Consultant
PS&E Prime Consultant Project Manager
PS&E Prime Consultant Designer
PS&E Utility Coordination Consultant
PS&E Utility Coordination Consultant PM
PS&E Utility Investigation Consultant
PS&E Utility Investigation Consultant PM
Construction TxDOT Project Manager
Construction TxDOT Utility Coordinator
Construction Contractor
Construction Contractor Project Manager
Construction Management Consultant
Construction Management Consultant PM
Construction Utility Coordination Consultant
Construction Utility Coordination Consultant PM

## Utility Inventory
Utility Conflict Management (UCM) - Utility Inventory
Utility Feature ID | Utility Owner | Utility Function | Utility Type | Utility Subtype | Utility Feature | Delivery Classification | Size | Material | Operational Status | Station Origin | Start Station | Start Offset | End Station | End Offset | From Latitude | From Longitude | To Latitude | To Longitude | Height/ Depth (ft) | Placement Relative to Ground Level | Alignment Type | Placement Relative to Existing ROW | Property Interest Type | Utility Records Completed Date | Visible Utility Investigation Completed Date | Geophysical Investigation Completed Date | Utility Exposure Completed Date | QLD (Y/N) | QLC (Y/N) | QLB (Y/N) | QLA (Y/N)

## Utility Conflicts
Utility Conflict Management (UCM) - Utility Conflicts
Utility Conflict ID | Utility Layout/ Sheet No. | Utility Owner | Utility Owner Contact Name | Utility Owner Contact Phone and Email | Utility Feature ID | Utility Function | Utility Type | Utility Subtype | Utility Feature | Size | Material | Utility Conflict Description | Station Origin | Start Station | Start Offset | End Station | End Offset | From Latitude | From Longitude | To Latitude | To Longitude | Height/ Depth (ft) | Placement Relative to Ground Level | Alignment Type | Placement Relative to Existing ROW | Property Interest Type | Parcel U-Number | Parcel Acquisition Status | Utility Investigation Completed | Utility Investigation Needed | Test Hole No. | Next Action | Resolution Strategy Selected (from Resolution Alternatives) | Reimbursable (Y/N) | High Priority (Y/N) | Utility Conflict Status | Status Achieved Date | Estimated Resolution Date | Comment

## Resolution Alternatives
Utility Conflict Management (UCM) - Analysis of Utility Conflict Resolution Alternatives
Utility Conflict ID(s) | Alternative No. | Alternative Description | Alternative Advantages | Alternative Disadvantages | Impact on Project Delivery Time | Total Cost to DOT ($) | Total Cost to Utility Owner ($) | Total Cost ($) | Feasible (Y/N) | Selected (Y/N)

## Utility Conflict List-Print
Utility Conflict Management (UCM) - Utility Conflicts
| Project Owner: | TxDOT |  | District: | 0 | [7 empty] | Prepared By:
| Project Control CSJ: | 0 | [10 empty] | Reviewed By:
| Project Name: | 0 |  | 0 | [8 empty] | Date:
Utility Conflict ID | Utility Layout/ Sheet No. | Utility Owner/Contact Name | Utility Type and Feature | Size/Material | Utility Conflict Description | Start Station | Start Offset | End Station | End Offset | Util. Inv. Compl. | Util. Inv. Needed | Test Hole No. | Next Action/Resolution Strategy Selected | High Priority (Y/N) | Utility Conflict Status | Estimated Resolution Date
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0
0 | 0 | / |  | / | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | 0 | 0 | 0

## Drop-Down Lists
District | Environmental Review Type | Utility Function | Utility Type | Utility Subtype | Feature | Delivery Classification | Operational Status | Material | Alignment Type | Placement Relative to Existing ROW | Property Interest Type | Placement Relative to Ground Level | Utility Investigation Quality Level | Utility Conflict Status | Parcel Acquisition Status | Yes/No
Abilene | Categorical Exclusion | Private | Communications | Alarm | Air Release Valve | Distribution | Proposed | Aluminum | Longitudinal | Inside | None (permit) | Aboveground | QLA | Identified | ROW map prepared | Y
Amarillo | Environmental Assessment | Public | Electric | Cable Television | Antenna | Gathering | In Service | Asbestos Cement | Crossing | Outside | Easement | Underground | QLB | Confirmed | ROW authorization | N
Atlanta | Environmental Impact Statement | Unknown | Non-Potable Water | Chemical | Cable | Service | Out of service | Brick | Mixed | Mixed | Lease | Submerged | QLC | Resolved | Appraisal requested
Austin |  |  | Petroleum and Gaseous Materials | Combined Sewer | Catch Basin | Transmission | Abandoned in place | Clay |  |  | Fee simple | Mixed | QLD | Cleared | Title requested
Beaumont |  |  | Potable Water | Compressed Air | Cathodic Test Station | Other | Backup | Coaxial Cable |  |  | Other |  |  |  | Negotiation in progress
Brownwood |  |  | Wastewater | Cooling and Heating | Clean Out | Unknown | Under Construction | Composite |  |  | Unknown |  |  |  | Parcel in possession
Bryan |  |  |  | Crude Oil | Conduit |  | Removed | Concrete | [6 empty] | Agreement
Childress |  |  |  | Fiber optic | Culvert |  | Unknown | Corrugated Metal | [6 empty] | Settlement
Corpus Christi |  |  |  | Gasoline | Culvert End |  |  | Corrugated Plastic | [6 empty] | Condemnation
Dallas |  |  |  | Irrigation | Drain |  |  | Copper
El Paso |  |  |  | Natural Gas | Duct |  |  | Ductile Iron
Fort Worth |  |  |  | Other Petroleum | Duct Bank |  |  | Fiberglass
Houston |  |  |  | Raw Water | Gathering Line |  |  | Fiber Optic
Laredo |  |  |  | Reclaimed Water | Generator |  |  | Galvanized Steel
Lubbock |  |  |  | Recycled Water | Guy Anchor |  |  | High Density Polyethylene (HDPE)
Lufkin |  |  |  | Salt Water | Guy Pole |  |  | Other
Odessa |  |  |  | Sanitary Sewer | Guy Wire |  |  | Plastic
Paris |  |  |  | Slurry | Hand Hole |  |  | Polyethylene (PE)
Pharr |  |  |  | Steam | Hydrant |  |  | Polypropylene (PP)
San Angelo |  |  |  | Storm Sewer | Inlet |  |  | Polystyrene (PS)
San Antonio |  |  |  | Street Lighting | Inverted Siphon |  |  | Polyvinyl Chloride (PVC)
Tyler |  |  |  | Telephone | Junction Box |  |  | Reinforced Concrete
Waco |  |  |  |  | Lid |  |  | Steel
Wichita Falls |  |  |  |  | Lift Station |  |  | Terracotta
Yoakum |  |  |  |  | Light |  |  | Tile
[5 empty] | Line |  |  | Twisted Pair Copper
[5 empty] | Line Clean Out |  |  | Wood
[5 empty] | Manhole |  |  | Wrapped Steel
Marker Sign
Marker Post
Meter
Meter Box
Outlet
Panel
Pedestal
Pipe End
Pole
Pressure Reducing Station
Pull Box
Pump
Pump Station
Push Brace
Reducer
Riser
Splice Box
Stub Out
Tank
Thrust Block
Tower
Tracer
Transformer
Tunnel
Undefined Utility Point
Vault
Valve
Valve Box
Vent
Wire

## Data Dictionary
Table | Column | Description
Projects | Project Owner | Owner of the transportation project (i.e., TxDOT)
| District | TxDOT district name
| Project Name | Project title or short project description
| Project Control CSJ | Project control section job number
| ROW CSJ | Right-of-Way control section job number
| Project Scope | Project scope
| Project Limits | Project limits
| Project Length | Project length (in miles)
| Estimated Construction Cost | Estimated project construction cost
| 30% Schematic Completed Date | Date that 30% schematic was completed
| 60% Schematic Completed Date | Date that 60% schematic was completed
| 90% Schematic Completed Date | Date that 90% schematic was completed
| 100% Schematic Completed Date | Date that 100% schematic was completed
| 30 PS&E Completed Date | Date that 30% PS&E was completed
| 60 PS&E Completed Date | Date that 60% PS&E was completed
| 90 PS&E Completed Date | Date that 90% PS&E was completed
| 100 PS&E Completed Date | Date that 100% PS&E was completed
| Ready-to-let (RTL) Date | Project ready-to-let date
| Letting Date | Project letting date
| Environmental Review Type | Type of environmental review (see Drop-Down Lists tab)
| Environmental Approval Date | Date the environmental review was approved
| ROW Authorization Date | Date that right-of-way acquisition was approved
| NOPCs Sent Date | Date that Notices of Proposed Construction were sent to utility owners
| NORAs Sent Date | Date that Notices of Required Accommodation were sent to utility owners
| Utility Records Research Completed Date | Date that utility records research was completed
| Visible Utility Investigation Completed Date | Date that investigation of visible utility features was completed
| Geophysical Investigation Completed Date | Date that geophysical utility investigation was completed
| Utility Exposure Investigation Completed Date | Date that utility investigation using test holes was completed
| QLD (Y/N) | Was QLD achieved in accordance with ASCE 38 (Y=Yes, N=No)
| QLC (Y/N) | Was QLC achieved in accordance with ASCE 38 (Y=Yes, N=No)
| QLB (Y/N) | Was QLB achieved in accordance with ASCE 38 (Y=Yes, N=No)
| QLA (Y/N) | Was QLA achieved in accordance with ASCE 38 (Y=Yes, N=No)
| ROW Authorization Date | Date that authorization to acquire right-of-way was obtained
| ROW Acquisition Completed Date | Date that all right-of-way parcels are acquired
| Schematic TxDOT Project Manager | Schematic-level project manager at TxDOT
| Schematic TxDOT Designer | Schematic-level designer at TxDOT
| Schematic TxDOT Utility Coordinator | Schematic-level utility coordinator at TxDOT
| Schematic Prime Consultant | Schematic-level prime consultant (company name)
| Schematic Prime Consultant Project Manager | Schematic-level prime consultant project manager
| Schematic Prime Consultant Designer | Schematic-level prime consultant designer
| Schematic Utility Coordination Consultant | Schematic-level utility coordination consultant (company name)
| Schematic Utility Coordination Consultant PM | Schematic-level utility coordination consultant project manager
| Schematic Utility Investigation Consultant | Schematic-level utility investigation consultant (company name)
| Schematic Utility Investigation Consultant PM | Schematic-level utility investigation consultant project manager
| Schematic TxDOT Project Manager | PS&E-level project manager at TxDOT
| Schematic TxDOT Designer | PS&E-level designer at TxDOT
| Schematic TxDOT Utility Coordinator | PS&E-level utility coordinator at TxDOT
| Schematic Prime Consultant | PS&E-level prime consultant (company name)
| Schematic Prime Consultant Project Manager | PS&E-level prime consultant project manager
| Schematic Prime Consultant Designer | PS&E-level prime consultant designer
| Schematic Utility Coordination Consultant | PS&E-level utility coordination consultant (company name)
| Schematic Utility Coordination Consultant PM | PS&E-level utility coordination consultant project manager
| Schematic Utility Investigation Consultant | PS&E-level utility investigation consultant (company name)
| Schematic Utility Investigation Consultant PM | PS&E-level utility investigation consultant project manager
| Construction TxDOT Project Manager | Construction project manager at TxDOT
| Construction TxDOT Utility Coordinator | Construction utility coordinator at TxDOT
| Construction Contractor | Construction contractor (company name)
| Construction Contractor Project Manager | Construction contractor project manager
| Construction Management Consultant | Construction management consultant (company name)
| Construction Management Consultant PM | Construction management consultant project manager
| Construction Utility Coordination Consultant | Construction utility coordination consultant (company name)
| Construction Utility Coordination Consultant PM | Construction utility coordination consultant project manager
Utility Inventory | Utility Feature ID | Utility feature identifier
| Utility Owner | Name of utility owner
| Utility Function | Type of utility function (see Drop-Down Lists tab)
| Utility Type | Type of utility service that a utility feature carries (see Drop-Down Lists tab)
| Utility Subtype | Type of utility service at a finer level of disaggregation than utility type (see Drop-Down Lists tab)
| Utility Feature | Utility system feature or component (see Drop-Down Lists tab)
| Delivery Classification | Primary category or purpose of service of the utility feature (see Drop-Down Lists tab)
| Size | Size of utility feature (e.g., 8 inches)
| Material | Material of utility feature (see Drop-Down Lists tab)
| Operational Status | Operational status of the utility feature (see Drop-Down Lists tab)
| Station Origin | Location or reference where stations begin
| Start Station | Station where utility feature starts. Example: 241+22.35.
| Start Offset | Offset associated with the start station. Example: 57.24 (L).
| End Station | Station where the utility feature ends. Example: 241+35.50
| End Offset | Offset associated with the end station. Example: 57.40 (L).
| From Latitude | Latitude where the utility conflict starts (in decimal degrees)
| From Longitude | Longitude where the utility conflict starts (in decimal degrees)
| To Latitude | Latitude where the utility conflict ends (in decimal degrees)
| To Longitude | Longitude where the utility conflict ends (in decimal degrees)
| Height/Depth | Height (or depth) of utility feature in conflict with respect to the existing grade (in feet)
| Placement Relative to Ground Level | Relative position of utility feature in conflict with respect to the existing grade (see Drop-Down Lists tab)
| Alignment Type | Primary alignment of utility feature with respect to roadway centerline (see Drop-Down Lists tab)
| Placement Relative to Existing ROW | Relative position of utility feature with respect to the right-of-way line (see Drop-Down Lists tab)
| Property Interest Type | Type of property interest by utility feature (see Drop-Down Lists tab)
| Utility Records Completed Date | Date that utility records research was completed
| Visible Utility Investigation Completed Date | Date that investigation of visible utility features was completed
| Geophysical Investigation Completed Date | Date that geophysical utility investigation was completed
| Utility Exposure Investigation Completed Date | Date that utility investigation using test holes was completed
| QLD (Y/N) | Was QLD achieved in accordance with ASCE 38 (Y=Yes, N=No)
| QLC (Y/N) | Was QLC achieved in accordance with ASCE 38 (Y=Yes, N=No)
| QLB (Y/N) | Was QLB achieved in accordance with ASCE 38 (Y=Yes, N=No)
| QLA (Y/N) | Was QLA achieved in accordance with ASCE 38 (Y=Yes, N=No)
Utility Conflicts | Utility Conflict ID | Utility conflict ID (unique within the transportation project)
| Utility Layout/Sheet No. | Number of utility layout or sheet that shows the conflict
| Utility Owner | Name of utility owner
| Utility Owner Contact Name | Name of utility owner's point of contact
| Utility Owner Contact Phone and Email | Phone and email address of utility owner's point of contact
| Utility Feature ID | Utility feature identifier
| Utility Function | Type of utility function (see Drop-Down Lists tab)
| Utility Type | Type of utility service that a utility feature carries (see Drop-Down Lists tab)
| Utility Subtype | Type of utility service at a finer level of disaggregation than utility type (see Drop-Down Lists tab)
| Utility Feature | Utility system feature or component (see Drop-Down Lists tab)
| Size | Size of utility feature (e.g., 8 inches)
| Material | Material of utility feature (see Drop-Down Lists tab)
| Utility Conflict Description | Description of the utility conflict
| Station Origin | Location or reference where stations begin
| Start Station | Station where the utility conflict starts. Example: 241+22.35.
| Start Offset | Offset associated with the start station. Example: 57.24 (L).
| End Station | Station where the utility conflict ends. Example: 241+35.50
| End Offset | Offset associated with the end station. Example: 57.40 (L).
| From Latitude | Latitude where the utility conflict starts (in decimal degrees)
| From Longitude | Longitude where the utility conflict starts (in decimal degrees)
| To Latitude | Latitude where the utility conflict ends (in decimal degrees)
| To Longitude | Longitude where the utility conflict ends (in decimal degrees)
| Height/Depth | Height (or depth) of utility feature in conflict with respect to the existing grade (in feet)
| Placement Relative to Ground Level | Relative position of utility feature in conflict with respect to the existing grade (see Drop-Down Lists tab)
| Alignment Type | Primary alignment of utility feature with respect to roadway centerline (see Drop-Down Lists tab)
| Placement Relative to Existing ROW | Relative position of utility feature with respect to the right-of-way line (see Drop-Down Lists tab)
| Property Interest Type | Type of property interest by utility feature (see Drop-Down Lists tab)
| Parcel U-Number | U-number associated with parcel that needs to be acquired where existing utility feature is located
| Parcel Acquisition Status | Status of parcel acquisition (see Drop-Down Lists tab)
| Utility Investigation Completed | Quality level of utility investigation that has been completed (e.g., QLD) (see Drop-Down Lists tab)
| Utility Investigation Needed | Quality level of additional utility investigation needed (e.g., QLB) (see Drop-Down Lists tab)
| Test Hole No. | Unique identifer of test hole that has been conducted to confirm depth of utility feature in conflict
| Next Action | Next step in the utility conflict management process
| Resolution Strategy Selected | Strategy that was selected to resolve the utility conflict
| Reimbursable (Y/N) | Is utility relocation is reimbursable (Y=Yes, N=No)
| High Priority (Y/N) | Is there a high priority to resolve the utility conflict (Y=Yes, N=No)
| Utility Conflict Status | Status of utility conflict (see Drop-Down Lists tab)
| Status Achieved Date | Date that utility conflict status was achieved
| Estimated Resolution Date | Date that utility conflict is anticipated to be resolved
| Comment | Comment
Resolution Alternatives | Utility Conflict ID(s) | IDs of all utility conflicts analyzed together for the set of resolution alternatives being considered
| Alternative Number | Utility conflict resolution alternative number
| Alternative Description | Description of utility conflict resolution alternative
| Alternative Advantages | Potential advantages associated with the utility conflict resolution alternative
| Alternative Disadvantages | Potential disadvantages associated with the utility conflict resolution alternative
| Impact on Project Delivery Time (Months) | Total potential impact of the utility conflict resolution alternative on project delivery time (in months)
| Total Cost to DOT | Total estimated cost to TxDOT if alternative is selected (including engineering and construction costs)
| Total Cost to Utility Owner | Total estimated cost to utility owner if alternative is selected (including engineering and construction costs)
| Total Cost | Sum of all estimated costs
| Feasible (Y/N) | Is utility conflict resolution alternative feasible (Y=Yes, N=No)
| Selected (Y/N) | Is utility conflict resolution alternative selected (Y=Yes, N=No)
Utility Conflict List-Print | Owner | Owner of the transportation project (i.e., TxDOT)
| District | District namer
| Project Control CSJ | Project control section job number
| Project Name | Project title or short project description
| Prepared by | Name of person who prepared or updated utility conflict list
| Reviewed by | Name of person who reviewed utility conflict list
| Date | Date the utility conflict list was last updated or reviewed
| Utility Conflict ID | Utility conflict ID (unique within the transportation project)
| Utility Layout/Sheet No. | Number of utility layout or sheet that shows the conflict
| Utility Owner/Contact Name | Name of utility owner and point of contact who has responsibility for utility facility in conflict
| Utility Type and Feature | Utility type and feature (see Drop-Down Lists tab)
| Size/Material | Size and material of utility facility in conflict. Example: 8" (PVC).
| Utility Conflict Description | Description of the utility conflict
| Start Station | Station where the utility conflict starts. Example: 241+22.35.
| Start Offset | Offset associated with the start station. Example: 57.24 (L).
| End Station | Station where the utility conflict ends. Example: 241+35.50
| End Offset | Offset associated with the end station. Example: 57.40 (L).
| Utility Investigation Completed | Quality level of utility investigation that has been completed (e.g., QLD) (see Drop-Down Lists tab)
| Utility Investigation Needed | Quality level of additional utility investigation needed (e.g., QLB) (see Drop-Down Lists tab)
| Test Hole No. | Unique identifer of test hole that has been conducted to confirm depth of utility feature in conflict
| Next Action/Resolution Strategy Selected | Next action to resolve utility conflict and resolution strategy selected
| High Priority (Y/N) | Is there a high priority to resolve the utility conflict (Y=Yes, N=No)
| Utility Conflict Status | Status of utility conflict (see Drop-Down Lists tab)
| Estimated Resolution Date | Date that utility conflict is anticipated to be resolved