## OTOB
Required Reporting per Texas Transportation Code §201.812 –
BUDGET = CONTRACT AWARD PLUS CHANGE ORDERS | [13 empty] | Highway Construction Projects Completed September 1, 2023–February 29, 2024
SCHEDULE = CONTRACT DAYS PLUS DAYS ADDED |  |  |  | FEBRUARY | 29 | 2024 | 2023
DISTRICT | CCSJ | COUNTY | HIGHWAY | DATE FINAL ESTIMATE PAID | CONTRACT AWARD AMOUNT | CHANGE ORDERS | CO BY THRD PRTY | AMOUNT PAID | UNDER OVER BUDGET | CONTRACT DAYS | CHARGED DAYS | DAYS ADDED | THIRD PARTY DAYS ADDED | UNDER OVER SCHEDULE
WACO | 0014-07-101 | HILL | SH 81 | 2023-09-01 | 3020549.2 | 164471.56 | 0 | 3218846.25 | 198297.05 | 75 | 75 | 0 | 0 | 0
AMARILLO | 0226-05-067 | DEAF SMITH | US 385 | 2023-09-03 | 5447354.4 | -122444.72 | 0 | 5792909.96 | 345555.56 | 91 | 120 | 21 | 0 | 29
AUSTIN | 0914-00-450 | TRAVIS | VA | 2023-09-04 | 5650620 | -1381686.72 | 0 | 4209423.38 | -1441196.62 | 160 | 234 | 79 | 0 | 74
EL PASO | 0374-02-122 | EL PASO | US 62 | 2023-09-06 | 103530 | 0 | 0 | 102486 | -1044 | 40 | 33 | 0 | 0 | -7
WACO | 0320-01-078 | BELL | SS 290 | 2023-09-06 | 384376 | -19500 | 0 | 395722.99 | 11346.99 | 75 | 53 | 0 | 0 | -22
YOAKUM | 0269-03-035 | LAVACA | US 77A | 2023-09-06 | 2082955.47 | 26693.76 | 0 | 1992284.45 | -90671.02 | 330 | 434 | 104 | 0 | 104
YOAKUM | 0913-00-108 | DEWITT | Various | 2023-09-06 | 665410.86 | 0 | 0 | 685718.81 | 20307.95 | 37 | 24 | 0 | 0 | -13
YOAKUM | 2350-01-070 | VICTORIA | SL 463 | 2023-09-06 | 571189.5 | 0 | 0 | 575668.5 | 4479 | 101 | 79 | 0 | 0 | -22
ABILENE | 0005-05-113 | HOWARD | IH 20 | 2023-09-07 | 6309354.48 | 3043.32 | 0 | 6366817.92 | 57463.44 | 48 | 34 | 0 | 0 | -14
ABILENE | 0974-06-016 | CALLAHAN | FM 604 | 2023-09-07 | 3777685.88 | 0 | 0 | 3854188.77 | 76502.89 | 183 | 143 | 0 | 0 | -40
FORT WORTH | 0080-02-061 | ERATH | US 377 | 2023-09-07 | 437790 | 417716.27 | 0 | 914012.2 | 476222.2 | 22 | 79 | 11 | 0 | 57
DALLAS | 0918-47-247 | DALLAS | CS | 2023-09-08 | 1374730 | 0 | 0 | 1374256.72 | -473.28 | 300 | 297 | 0 | 0 | -3
DALLAS | 0918-47-398 | DALLAS | Various | 2023-09-08 | 1681430.44 | 83633.68 | 0 | 1850112.83 | 168682.39 | 68 | 62 | 0 | 0 | -6
HOUSTON | 1257-01-053 | FORT BEND | FM 1092 | 2023-09-08 | 2396293.69 | -144245.87 | 0 | 2724070.51 | 327776.82 | 126 | 126 | 0 | 0 | 0
HOUSTON | 2898-01-012 | WALLER | FM 2855 | 2023-09-08 | 5061781.12 | -94392.79 | 0 | 4862466.24 | -199314.88 | 150 | 145 | 0 | 0 | -5
HOUSTON | 1685-05-128 | HARRIS | SH 6 | 2023-09-11 | 387860.68 | 80632.45 | 0 | 493561.61 | 105700.93 | 35 | 31 | 0 | 0 | -4
LUBBOCK | 0052-07-072 | LUBBOCK | US 84 | 2023-09-11 | 538624.6 | 0 | 0 | 535800.43 | -2824.17 | 80 | 72 | 0 | 0 | -8
LUBBOCK | 0439-01-025 | CASTRO | SH 194 | 2023-09-11 | 383370.2 | 44420 | 0 | 430899.12 | 47528.92 | 20 | 10 | 0 | 0 | -10
PARIS | 1487-01-008 | FANNIN | FM 1552 | 2023-09-11 | 1844734.62 | 5964.48 | 0 | 1925892.39 | 81157.77 | 96 | 122 | 0 | 0 | 26
SAN ANGELO | 0907-00-199 | TOM GREEN | Various | 2023-09-12 | 1784037.16 | 66836 | 0 | 1850876.16 | 66839 | 39 | 42 | 0 | 0 | 3
SAN ANTONIO | 0017-05-095 | MEDINA | IH 35 | 2023-09-12 | 2442867.71 | -97596.21 | 0 | 2385528.53 | -57339.18 | 466 | 477 | 11 | 0 | 11
PHARR | 0039-02-068 | HIDALGO | US 83 | 2023-09-13 | 6096123 | 230230.23 | 0 | 5837343.53 | -258779.47 | 320 | 338 | 27 | 0 | 18
AUSTIN | 0914-00-418 | TRAVIS | VA | 2023-09-14 | 2145700 | 417731.3 | 0 | 544901.24 | -1600798.76 | 730 | 13 | 0 | 0 | -717
BRYAN | 0186-06-091 | WASHINGTON | US 290 | 2023-09-14 | 1649907.2 | 38173.67 | 0 | 1654960.95 | 5053.75 | 86 | 105 | 0 | 0 | 19
SAN ANGELO | 0907-14-010 | COKE | CR | 2023-09-15 | 659587 | 6577.6 | 0 | 635599.34 | -23987.66 | 84 | 74 | 0 | 0 | -10
PHARR | 0684-02-014 | CAMERON | FM 511 | 2023-09-18 | 1147081.1 | 87839.13 | 0 | 1333910.17 | 186829.07 | 131 | 140 | 19 | 0 | 9
AUSTIN | 0016-02-149 | HAYS | IH 35 | 2023-09-19 | 13264542.3 | 617198.44 | 34160.43 | 14024549 | 725846.27 | 379 | 383 | 119 | 0 | 4
WACO | 0909-00-067 | MCLENNAN | Various | 2023-09-19 | 1849402.79 | 15913.52 | 0 | 1688054.17 | -161348.62 | 105 | 55 | 0 | 0 | -50
WACO | 0909-36-181 | BELL | CS | 2023-09-19 | 451322 | -2126.7 | 0 | 411969.04 | -39352.96 | 90 | 56 | 0 | 0 | -34
BEAUMONT | 0200-08-059 | TYLER | US 69 | 2023-09-20 | 1846631.83 | -434276.22 | 0 | 1630624.92 | -216006.91 | 82 | 79 | 0 | 0 | -3
BRYAN | 0917-00-051 | BRAZOS | VA | 2023-09-20 | 183906 | 30160 | 0 | 209695.08 | 25789.08 | 45 | 17 | 0 | 0 | -28
FORT WORTH | 0008-03-089 | PARKER | IH 20 | 2023-09-20 | 3921685.61 | 2539234.17 | 0 | 7041948.02 | 3120262.41 | 192 | 628 | 415 | 0 | 436
LUFKIN | 0390-05-006 | SAN AUGUSTINE | FM 2558 | 2023-09-20 | 1485266.77 | 0 | 0 | 1427751.37 | -57515.4 | 159 | 221 | 65 | 0 | 62
CORPUS CHRISTI | 0916-00-224 | NUECES | Various | 2023-09-21 | 2367405.63 | 130415.55 | 0 | 2291285.55 | -76120.08 | 62 | 98 | 27 | 0 | 36
AUSTIN | 1197-01-021 | HAYS | RM 150 | 2023-09-22 | 3601690.88 | 290835.66 | 0 | 4109049.14 | 507358.26 | 215 | 166 | 0 | 0 | -49
HOUSTON | 0912-00-644 | HARRIS | VA | 2023-09-22 | 1273417.93 | -574197.23 | 0 | 604086.32 | -669331.61 | 181 | 340 | 159 | 0 | 159
ODESSA | 0228-06-081 | ECTOR | US 385 | 2023-09-22 | 25331611.54 | 1174095.01 | 0 | 27534729.62 | 2203118.08 | 291 | 452 | 171 | 0 | 161
AUSTIN | 0152-03-062 | CALDWELL | US 183 | 2023-09-25 | 1315225 | 370073.47 | 0 | 1778911.14 | 463686.14 | 117 | 140 | 25 | 0 | 23
HOUSTON | 0271-16-160 | HARRIS | IH 610 | 2023-09-25 | 645779.25 | 1149137.02 | 0 | 2039717.89 | 1393938.64 | 208 | 87 | 0 | 0 | -121
SAN ANGELO | 2574-01-049 | TOM GREEN | CS | 2023-09-25 | 538601 | 24146 | 0 | 609953.5 | 71352.5 | 132 | 130 | 0 | 0 | -2
YOAKUM | 0913-21-052 | MATAGORDA | CR | 2023-09-25 | 648611.35 | 0 | 0 | 636160.69 | -12450.66 | 60 | 51 | 0 | 0 | -9
AMARILLO | 0275-01-205 | POTTER | IH 40 | 2023-09-26 | 15820658.82 | 971467.95 | 0 | 17412230.13 | 1591571.31 | 440 | 468 | 46 | 0 | 28
HOUSTON | 0598-02-119 | BRAZORIA | SH 288 | 2023-09-26 | 4797528.55 | 80207.9 | 80207.9 | 5122493.38 | 244756.93 | 171 | 182 | 23 | 23 | -12
ABILENE | 0650-01-034 | NOLAN | SH 153 | 2023-09-27 | 5924739.06 | 136210.94 | 0 | 6145786.77 | 221047.71 | 235 | 294 | 15 | 0 | 59
AUSTIN | 3210-01-019 | HAYS | FM 2770 | 2023-09-27 | 1394023.95 | 80014.86 | 0 | 1294734.24 | -99289.71 | 80 | 39 | 0 | 0 | -41
SAN ANTONIO | 0017-06-091 | FRIO | IH 35 | 2023-09-27 | 1300000 | 0 | 0 | 1330730.45 | 30730.45 | 56 | 44 | 0 | 0 | -12
AMARILLO | 2635-05-001 | RANDALL | SL 335 | 2023-09-28 | 45797690.54 | 675267.16 | 0 | 46071009.59 | 273319.05 | 764 | 871 | 87 | 0 | 107
AUSTIN | 0440-06-025 | TRAVIS | SH 130 | 2023-09-29 | 459288.6 | 3000 | 0 | 527541.26 | 68252.66 | 66 | 57 | 0 | 0 | -9
ATLANTA | 0062-04-051 | CASS | US 59 | 2023-10-02 | 504893.32 | 45082.16 | 0 | 522045.87 | 17152.55 | 90 | 81 | 0 | 0 | -9
AUSTIN | 0152-03-061 | CALDWELL | US 183 | 2023-10-02 | 5467487.08 | 0 | 0 | 5102910.86 | -364576.22 | 95 | 65 | 0 | 0 | -30
BEAUMONT | 2701-02-025 | ORANGE | FM 3247 | 2023-10-02 | 1011890.95 | -13352.25 | 0 | 1090559.61 | 78668.66 | 26 | 25 | 0 | 0 | -1
LUFKIN | 0176-02-125 | ANGELINA | BU 59G | 2023-10-02 | 1363053.76 | 31752 | 0 | 1397581.82 | 34528.06 | 95 | 92 | 4 | 0 | -3
LUFKIN | 0911-40-029 | TRINITY | VA | 2023-10-02 | 975968 | -3783.04 | 0 | 933915.37 | -42052.63 | 146 | 278 | 21 | 0 | 132
PHARR | 0255-08-108 | HIDALGO | IH 69C | 2023-10-02 | 9148469.99 | -97547.83 | 0 | 9021148.62 | -127321.37 | 192 | 142 | 0 | 0 | -50
TYLER | 0910-00-132 | SMITH | VA | 2023-10-02 | 402135.93 | -1704.91 | 0 | 355055.87 | -47080.06 | 49 | 20 | 0 | 0 | -29
AMARILLO | 0904-00-200 | POTTER | Various | 2023-10-03 | 781620.71 | 0 | 0 | 756098.59 | -25522.12 | 56 | 27 | 0 | 0 | -29
AUSTIN | 0511-03-013 | HAYS | RM 32 | 2023-10-03 | 1073849.51 | -28279.33 | 0 | 952581.79 | -121267.72 | 85 | 57 | 0 | 0 | -28
BEAUMONT | 1194-02-019 | HARDIN | FM 943 | 2023-10-03 | 1940016.09 | 0 | 0 | 1875235.37 | -64780.72 | 130 | 113 | 0 | 0 | -17
EL PASO | 0924-00-144 | EL PASO | VA | 2023-10-03 | 1343419.6 | 0 | 0 | 1366363.6 | 22944 | 200 | 273 | 0 | 0 | 73
PHARR | 1427-01-040 | HIDALGO | FM 1423 | 2023-10-03 | 5388775.4 | 78779.22 | 0 | 6182443.36 | 793667.96 | 100 | 112 | 15 | 0 | 12
YOAKUM | 0143-08-099 | DEWITT | US 87 | 2023-10-03 | 1692978.61 | 0 | 0 | 1623440.54 | -69538.07 | 45 | 21 | 0 | 0 | -24
YOAKUM | 0153-02-043 | GONZALES | US 183 | 2023-10-03 | 3013760 | -8007 | 0 | 2927761.5 | -85998.5 | 171 | 186 | 0 | 0 | 15
YOAKUM | 0420-02-051 | JACKSON | SH 172 | 2023-10-03 | 2881195.6 | 0 | 0 | 2852621.49 | -28574.11 | 90 | 58 | 0 | 0 | -32
YOAKUM | 0913-09-053 | WHARTON | CR | 2023-10-03 | 629675 | 18430 | 0 | 645721.4 | 16046.4 | 75 | 93 | 4 | 0 | 18
YOAKUM | 1113-01-028 | DEWITT | FM 766 | 2023-10-03 | 8812355.55 | -11351.32 | 0 | 8836952.07 | 24596.52 | 260 | 218 | 0 | 0 | -42
AMARILLO | 0238-04-038 | DALLAM | US 54 | 2023-10-04 | 8285085.51 | -73299.62 | 0 | 8851740.3 | 566654.79 | 127 | 103 | 0 | 0 | -24
AMARILLO | 0490-04-045 | ROBERTS | SH 70 | 2023-10-04 | 23349233.82 | 1181769.67 | 0 | 26743617.08 | 3394383.26 | 178 | 266 | 29 | 0 | 88
PARIS | 2277-01-010 | RAINS | FM 275 | 2023-10-04 | 4114424.46 | 0 | 0 | 4068225.83 | -46198.63 | 330 | 281 | 0 | 0 | -49
BEAUMONT | 0389-02-052 | CHAMBERS | SH 146 | 2023-10-05 | 1117845.7 | 189494.97 | 0 | 1336669.2 | 218823.5 | 162 | 295 | 117 | 0 | 133
PHARR | 0331-03-021 | CAMERON | FM 1421 | 2023-10-05 | 3309036.52 | 0 | 0 | 3431089.4 | 122052.88 | 76 | 76 | 0 | 0 | 0
AUSTIN | 0914-18-111 | BASTROP | CR | 2023-10-06 | 964123.3 | -82400 | 0 | 841628.33 | -122494.97 | 93 | 87 | 0 | 0 | -6
FORT WORTH | 0550-02-050 | ERATH | FM 8 | 2023-10-06 | 6087434.1 | 1009511.28 | 0 | 6594420.47 | 506986.37 | 214 | 204 | 0 | 0 | -10
FORT WORTH | 1990-01-020 | ERATH | FM 205 | 2023-10-06 | 9896354.05 | 932293.92 | 0 | 10358974.41 | 462620.36 | 234 | 332 | 93 | 0 | 98
DALLAS | 0918-46-299 | DENTON | CS | 2023-10-09 | 2851250.8 | 26400 | 0 | 2857466.29 | 6215.49 | 165 | 151 | 0 | 0 | -14
BRYAN | 0917-17-074 | GRIMES | CR | 2023-10-11 | 597985.3 | 0 | 0 | 625445.41 | 27460.11 | 81 | 81 | 0 | 0 | 0
PARIS | 0045-12-087 | RED RIVER | US 82 | 2023-10-11 | 2627582.9 | -9051.77 | 0 | 2528604.04 | -98978.86 | 218 | 223 | 14 | 0 | 5
PARIS | 0045-20-018 | FANNIN | US 82 | 2023-10-11 | 71637885.73 | 709724 | 0 | 75379203.72 | 3741317.99 | 928 | 949 | 0 | 0 | 21
PARIS | 0901-28-093 | HOPKINS | CR | 2023-10-11 | 608037.35 | 0 | 0 | 599130.55 | -8906.8 | 128 | 110 | 0 | 0 | -18
DALLAS | 1012-02-042 | COLLIN | FM 545 | 2023-10-12 | 8250437.86 | 14372.85 | 0 | 7886829.53 | -363608.33 | 450 | 437 | 0 | 0 | -13
WACO | 0836-02-078 | BELL | SH 195 | 2023-10-12 | 709467.86 | -44144.59 | 0 | 674492.09 | -34975.77 | 30 | 23 | 0 | 0 | -7
WACO | 0909-36-189 | BELL | CS | 2023-10-12 | 81987 | -5000 | 0 | 69144 | -12843 | 21 | 6 | 0 | 0 | -15
WICHITA FALLS | 0815-01-051 | COOKE | FM 372 | 2023-10-12 | 4347377.45 | 0 | 0 | 4862140.02 | 514762.57 | 85 | 72 | 0 | 0 | -13
DALLAS | 0092-06-108 | NAVARRO | IH 45 | 2023-10-13 | 3870961.8 | 203705 | 0 | 4309920.67 | 438958.87 | 249 | 249 | 20 | 0 | 0
AUSTIN | 0114-03-107 | TRAVIS | US 290 | 2023-10-16 | 505421.58 | 13894.5 | 0 | 513046.69 | 7625.11 | 44 | 31 | 0 | 0 | -13
BRYAN | 0049-09-094 | BRAZOS | BS 6R | 2023-10-16 | 2897017.81 | 81356.34 | 0 | 3110082.82 | 213065.01 | 65 | 54 | 0 | 0 | -11
HOUSTON | 0271-15-097 | HARRIS | IH 610 | 2023-10-16 | 3481497.4 | 2370424.61 | 0 | 5941358.06 | 2459860.66 | 272 | 265 | 0 | 0 | -7
LUBBOCK | 0294-02-023 | GAINES | US 180 | 2023-10-16 | 48813789.58 | 16651.91 | 0 | 49375604.54 | 561814.96 | 412 | 445 | 43 | 0 | 33
AUSTIN | 0273-04-046 | WILLIAMSON | US 183 | 2023-10-17 | 6654421.8 | -108835.2 | 0 | 6971723.11 | 317301.31 | 314 | 222 | 0 | 0 | -92
BROWNWOOD | 0054-09-042 | MILLS | US 84 | 2023-10-17 | 501967 | 13000 | 0 | 515022 | 13055 | 90 | 78 | 0 | 0 | -12
BRYAN | 1145-02-022 | LEON | FM 811 | 2023-10-17 | 9543192.09 | -351408.55 | 0 | 9295429.44 | -247762.65 | 278 | 286 | 4 | 0 | 8
HOUSTON | 0912-72-654 | HARRIS | Various | 2023-10-17 | 2085476.35 | 0 | 0 | 2146987.48 | 61511.13 | 37 | 58 | 21 | 0 | 21
AUSTIN | 0573-01-034 | BASTROP | SH 304 | 2023-10-18 | 9387685.84 | 129413.31 | 0 | 9245815.42 | -141870.42 | 193 | 188 | 0 | 0 | -5
YOAKUM | 0026-02-034 | FAYETTE | US 90 | 2023-10-18 | 2724321.52 | 22724.99 | 0 | 2742650.44 | 18328.92 | 175 | 163 | 0 | 0 | -12
YOAKUM | 0323-02-034 | FAYETTE | SH 95 | 2023-10-18 | 15550417.41 | -172833.21 | 0 | 15129055.16 | -421362.25 | 300 | 327 | 27 | 0 | 27
AUSTIN | 1201-02-025 | WILLIAMSON | FM 487 | 2023-10-19 | 2349410.23 | -259607.5 | 0 | 2083064.72 | -266345.51 | 74 | 43 | 0 | 0 | -31
DALLAS | 2374-03-096 | DALLAS | IH 20 | 2023-10-19 | 7163236.67 | 255442.32 | 0 | 7858479.35 | 695242.68 | 209 | 218 | 8 | 0 | 9
LUFKIN | 2893-01-018 | SHELBY | FM 947 | 2023-10-19 | 2185617.71 | 102189.68 | 0 | 2198960.97 | 13343.26 | 80 | 77 | 30 | 0 | -3
WACO | 0184-05-005 | CORYELL | BS 36E | 2023-10-19 | 1274745.89 | 92918.41 | 0 | 1391927.28 | 117181.39 | 60 | 68 | 0 | 0 | 8
AUSTIN | 0015-13-419 | TRAVIS | IH 35 | 2023-10-20 | 8677684.54 | 689124.57 | 0 | 9531573.3 | 853888.76 | 85 | 112 | 45 | 0 | 27
BEAUMONT | 0200-10-090 | HARDIN | US 69 | 2023-10-20 | 250000 | 0 | 0 | 250000 | 0 | 7 | 2 | 0 | 0 | -5
BEAUMONT | 0920-02-096 | LIBERTY | VA | 2023-10-20 | 388841.5 | 18705 | 0 | 356928.06 | -31913.44 | 99 | 117 | 20 | 0 | 18
PHARR | 0102-07-045 | BROOKS | SH 285 | 2023-10-22 | 11330610.73 | 67925 | 0 | 12063582.43 | 732971.7 | 138 | 296 | 158 | 0 | 158
AUSTIN | 1539-02-026 | TRAVIS | FM 1626 | 2023-10-23 | 10089973.35 | 146768.65 | 271511.74 | 10122527.27 | -238957.82 | 273 | 438 | 1 | 0 | 165
AUSTIN | 3136-01-196 | TRAVIS | SL 1 | 2023-10-24 | 1239172.95 | 71273.92 | 0 | 1258871.18 | 19698.23 | 25 | 23 | 0 | 0 | -2
LUFKIN | 2589-01-023 | ANGELINA | FM 2497 | 2023-10-24 | 5264189.37 | 54000 | 0 | 5339939.67 | 75750.3 | 145 | 324 | 159 | 0 | 179
ATLANTA | 0010-06-044 | TITUS | US 67 | 2023-10-25 | 10814286.76 | -51401.22 | 0 | 9723857.88 | -1090428.88 | 80 | 64 | 0 | 0 | -16
FORT WORTH | 1181-04-052 | JOHNSON | FM 917 | 2023-10-25 | 913114.46 | 0 | 0 | 699054.93 | -214059.53 | 64 | 63 | 0 | 0 | -1
ABILENE | 1155-03-011 | HOWARD | FM 1785 | 2023-10-26 | 8834075.61 | 116181.4 | 0 | 8826393.09 | -7682.52 | 324 | 318 | 0 | 0 | -6
AUSTIN | 0016-02-168 | HAYS | IH 35 | 2023-10-26 | 1151607.24 | 46693.95 | 0 | 1235717.85 | 84110.61 | 39 | 17 | 0 | 0 | -22
EL PASO | 0002-04-033 | HUDSPETH | SH 20 | 2023-10-26 | 3364597.35 | 690121.05 | 0 | 4018372.97 | 653775.62 | 180 | 100 | 0 | 0 | -80
YOAKUM | 0913-27-089 | VICTORIA | CS | 2023-10-26 | 62074.07 | 0 | 0 | 60074.07 | -2000 | 15 | 6 | 0 | 0 | -9
FORT WORTH | 0171-05-081 | TARRANT | SH 199 | 2023-10-27 | 65461507.43 | 22290867.67 | 3532091.7 | 88807685.78 | 19814086.65 | 919 | 2074 | 1155 | 0 | 1155
FORT WORTH | 0343-04-044 | ERATH | SH 108 | 2023-10-27 | 6936074.51 | 1488357.99 | 279196.22 | 8228038.19 | 1012767.46 | 278 | 406 | 156 | 0 | 128
FORT WORTH | 0422-03-084 | JOHNSON | US 67 | 2023-10-27 | 524586.5 | 0 | 0 | 413919.84 | -110666.66 | 64 | 111 | 45 | 0 | 47
SAN ANTONIO | 0517-03-035 | MCMULLEN | SH 16 | 2023-10-27 | 40124534.52 | -2221713.32 | 0 | 38353484.55 | -1771049.97 | 524 | 824 | 26 | 0 | 300
SAN ANTONIO | 0915-00-241 | BEXAR | Various | 2023-10-27 | 3546574.1 | 0 | 0 | 3169621.13 | -376952.97 | 165 | 151 | 0 | 0 | -14
SAN ANTONIO | 0915-17-073 | COMAL | CS | 2023-10-27 | 629837.17 | 87161.5 | 0 | 761423.43 | 131586.26 | 53 | 62 | 10 | 0 | 9
AUSTIN | 0914-05-213 | WILLIAMSON | CS | 2023-10-30 | 96975.55 | 41300.4 | 0 | 148034.1 | 51058.55 | 44 | 21 | 0 | 0 | -23
YOAKUM | 0089-19-013 | VICTORIA | BU 59-T | 2023-10-30 | 238957.94 | 18868.57 | 0 | 299591.54 | 60633.6 | 60 | 58 | 0 | 0 | -2
AMARILLO | 0168-07-049 | DEAF SMITH | US 60 | 2023-10-31 | 5647434.2 | 10200 | 0 | 5722521.36 | 75087.16 | 181 | 326 | 0 | 0 | 145
FORT WORTH | 0172-01-054 | TARRANT | BU 287P | 2023-10-31 | 1188709.84 | 50869.97 | 0 | 1322018.49 | 133308.65 | 151 | 163 | 16 | 0 | 12
PARIS | 0189-01-012 | RED RIVER | SH 37 | 2023-11-01 | 7781705.26 | 822978.23 | 0 | 9299857.78 | 1518152.52 | 223 | 242 | 19 | 0 | 19
WICHITA FALLS | 1356-01-029 | COOKE | FM 1201 | 2023-11-01 | 4085240.88 | 441436.2 | 0 | 4661844.91 | 576604.03 | 153 | 181 | 32 | 0 | 28
AMARILLO | 0379-03-026 | POTTER | SH 136 | 2023-11-02 | 6694352.15 | -41228.89 | 0 | 6612817.35 | -81534.8 | 207 | 239 | 0 | 0 | 32
ATLANTA | 0569-04-020 | HARRISON | SH 43 | 2023-11-03 | 2545187.72 | 5468.19 | 0 | 2967798.06 | 422610.34 | 128 | 299 | 2 | 0 | 171
LUBBOCK | 0053-01-131 | LUBBOCK | SS 331 | 2023-11-03 | 1570806.75 | 67067 | 0 | 1472585.73 | -98221.02 | 73 | 73 | 0 | 0 | 0
YOAKUM | 0265-07-051 | FAYETTE | SH 71 | 2023-11-05 | 1588831.86 | 38000 | 0 | 2025131.56 | 436299.7 | 75 | 98 | 23 | 0 | 23
YOAKUM | 0267-03-030 | FAYETTE | FM 609 | 2023-11-05 | 3404043.82 | 120891.3 | 0 | 3551667.81 | 147623.99 | 135 | 106 | 0 | 0 | -29
DALLAS | 0009-02-065 | DALLAS | SH 78 | 2023-11-06 | 2049364.32 | 123394.15 | 0 | 1969357.95 | -80006.37 | 102 | 158 | 0 | 0 | 56
ATLANTA | 1020-01-057 | BOWIE | FM 559 | 2023-11-07 | 225789.76 | 0 | 0 | 222878.14 | -2911.62 | 70 | 45 | 0 | 0 | -25
AUSTIN | 0914-00-475 | TRAVIS | Various | 2023-11-07 | 1109148.53 | -123399.47 | 0 | 1018003.01 | -91145.52 | 126 | 70 | 0 | 0 | -56
BROWNWOOD | 2786-01-018 | LAMPASAS | FM 2657 | 2023-11-07 | 2365646.87 | 5121.31 | 0 | 2313756.1 | -51890.77 | 50 | 45 | 0 | 0 | -5
ABILENE | 0263-01-021 | KENT | US 380 | 2023-11-09 | 10460911.96 | -75644.16 | 0 | 10559112.2 | 98200.24 | 103 | 103 | 0 | 0 | 0
AUSTIN | 2689-01-029 | TRAVIS | FM 2304 | 2023-11-09 | 2730040.2 | -196565.74 | 0 | 2433984.33 | -296055.87 | 57 | 23 | 0 | 0 | -34
BROWNWOOD | 0923-17-088 | COMANCHE | CR | 2023-11-09 | 1969718.25 | -1737.56 | 0 | 1979451.09 | 9732.84 | 225 | 235 | 0 | 0 | 10
DALLAS | 0280-02-040 | COLLIN | SH 78 | 2023-11-09 | 15143487.86 | 1064665.43 | 0 | 16488605.68 | 1345117.82 | 328 | 558 | 181 | 0 | 230
DALLAS | 0918-47-341 | DALLAS | CS | 2023-11-09 | 985988.81 | -26508.68 | 28366.94 | 941592.59 | -72763.16 | 57 | 92 | 0 | 0 | 35
PARIS | 1475-01-015 | HOPKINS | FM 1536 | 2023-11-09 | 3845345.39 | 178088.29 | 0 | 3951967.09 | 106621.7 | 192 | 190 | 0 | 0 | -2
CORPUS CHRISTI | 1121-01-022 | KARNES | FM 792 | 2023-11-10 | 1472197.11 | 148689.64 | 0 | 1626386.74 | 154189.63 | 93 | 93 | 38 | 0 | 0
FORT WORTH | 0444-02-023 | JACK | SH 114 | 2023-11-10 | 12812480.29 | 43126.6 | 0 | 11903276.11 | -909204.18 | 148 | 148 | 0 | 0 | 0
WICHITA FALLS | 0903-15-105 | COOKE | CR | 2023-11-13 | 1461248 | 0 | 0 | 1418448.91 | -42799.09 | 153 | 196 | 0 | 0 | 43
DALLAS | 1290-02-023 | ROCKWALL | SH 276 | 2023-11-14 | 2748754 | 120901.92 | 0 | 3015054.42 | 266300.42 | 68 | 68 | 0 | 0 | 0
HOUSTON | 0051-04-067 | GALVESTON | SH 87 | 2023-11-14 | 10994229.67 | 1670383.77 | 203228.44 | 12374440.06 | 1176981.95 | 210 | 359 | 70 | 0 | 149
HOUSTON | 0051-06-018 | HARRIS | SH 3 | 2023-11-14 | 2198720.36 | 130368.52 | 0 | 2430729.34 | 232008.98 | 72 | 65 | 0 | 0 | -7
LUBBOCK | 0130-05-086 | LUBBOCK | SH 114 | 2023-11-15 | 193635 | 49953.79 | 0 | 246363.59 | 52728.59 | 25 | 20 | 0 | 0 | -5
LUBBOCK | 0302-01-023 | PARMER | SH 86 | 2023-11-15 | 196115 | 0 | 0 | 193315 | -2800 | 44 | 26 | 0 | 0 | -18
SAN ANTONIO | 0073-02-080 | BEXAR | US 281 | 2023-11-15 | 4316413.23 | 347668.51 | 0 | 4667730.13 | 351316.9 | 123 | 223 | 67 | 0 | 100
SAN ANTONIO | 1167-01-011 | UVALDE | FM 1052 | 2023-11-15 | 1021333.41 | 0 | 0 | 956434.44 | -64898.97 | 47 | 47 | 0 | 0 | 0
BEAUMONT | 0028-15-056 | ORANGE | SH 87 | 2023-11-16 | 537329.15 | 741464.8 | 0 | 1397019.82 | 859690.67 | 41 | 161 | 123 | 0 | 120
BRYAN | 0166-03-033 | FREESTONE | SH 75 | 2023-11-16 | 4091805.2 | 214787.53 | 0 | 4814897.61 | 723092.41 | 259 | 247 | 0 | 0 | -12
DALLAS | 0196-02-131 | DENTON | IH 35E | 2023-11-16 | 2796046.88 | -189051.81 | 0 | 2608390.02 | -187656.86 | 71 | 74 | 3 | 0 | 3
FORT WORTH | 0902-00-312 | TARRANT | Various | 2023-11-16 | 4103210 | -4005.51 | 0 | 3425398.75 | -677811.25 | 365 | 365 | 0 | 0 | 0
PARIS | 0009-06-054 | HUNT | SH 66 | 2023-11-17 | 1642031.5 | 9134.3 | 0 | 1610341.43 | -31690.07 | 115 | 102 | 0 | 0 | -13
PARIS | 0135-06-039 | HUNT | US 380 | 2023-11-17 | 548338.8 | 7244.52 | 0 | 554701.33 | 6362.53 | 94 | 45 | 0 | 0 | -49
PARIS | 0510-04-013 | FANNIN | FM 898 | 2023-11-17 | 12209809.54 | -293901.34 | 0 | 12045610.92 | -164198.62 | 533 | 546 | 13 | 0 | 13
PHARR | 0039-02-063 | HIDALGO | CS | 2023-11-17 | 95994022.83 | 2393316.49 | 0 | 99972949.81 | 3978926.98 | 851 | 799 | 0 | 0 | -52
WACO | 0014-17-078 | HILL | FM 1242 | 2023-11-17 | 4783740.08 | 27081.56 | 0 | 4994930.68 | 211190.6 | 45 | 87 | 0 | 0 | 42
AUSTIN | 0115-04-055 | BASTROP | FM 20 | 2023-11-20 | 2547556.2 | 143767.93 | 0 | 2779331.86 | 231775.66 | 153 | 145 | 0 | 0 | -8
AUSTIN | 0807-01-032 | BASTROP | FM 535 | 2023-11-20 | 1577805.18 | 35572.83 | 0 | 1574162.56 | -3642.62 | 37 | 32 | 0 | 0 | -5
BROWNWOOD | 0923-00-069 | BROWN | Various | 2023-11-20 | 1992104.15 | -26644.09 | 0 | 1954077.07 | -38027.08 | 85 | 54 | 0 | 0 | -31
WACO | 0808-02-012 | FALLS | FM 413 | 2023-11-20 | 995631.79 | 140622.71 | 0 | 1140640.07 | 145008.28 | 75 | 84 | 30 | 0 | 9
WACO | 1054-01-009 | BOSQUE | FM 219 | 2023-11-20 | 5391495.03 | -301672.9 | 0 | 4818391.16 | -573103.87 | 120 | 130 | 0 | 0 | 10
WACO | 3521-01-022 | MCLENNAN | FM 2837 | 2023-11-20 | 290913.25 | -7538.08 | 0 | 279516.49 | -11396.76 | 45 | 41 | 0 | 0 | -4
ABILENE | 0033-04-072 | JONES | US 83 | 2023-11-21 | 5224759.64 | 56.75 | 0 | 5528548.9 | 303789.26 | 114 | 104 | 0 | 0 | -10
AUSTIN | 0286-01-057 | HAYS | SH 80 | 2023-11-22 | 7150482.88 | 50010.13 | 0 | 7461140.1 | 310657.22 | 210 | 187 | 0 | 0 | -23
CHILDRESS | 1235-01-012 | WHEELER | FM 1046 | 2023-11-22 | 6062196.88 | 282781.36 | 0 | 6396366.83 | 334169.95 | 170 | 210 | 30 | 0 | 40
DALLAS | 0197-03-054 | KAUFMAN | US 175 | 2023-11-27 | 12972960.9 | 1147989.66 | 0 | 13756419.48 | 783458.58 | 531 | 475 | 0 | 0 | -56
TYLER | 0910-00-121 | SMITH | Various | 2023-11-27 | 1937247.25 | 135346.05 | 0 | 2254109.06 | 316861.81 | 75 | 81 | 0 | 0 | 6
TYLER | 0910-07-089 | GREGG | Various | 2023-11-27 | 198617 | 0 | 0 | 199019 | 402 | 51 | 40 | 0 | 0 | -11
DALLAS | 0918-00-327 | DALLAS | VA | 2023-11-29 | 410372.07 | 0 | 0 | 428959.97 | 18587.9 | 95 | 88 | 0 | 0 | -7
WACO | 0055-06-036 | CORYELL | US 84 | 2023-11-29 | 341320 | 0 | 0 | 338541.33 | -2778.67 | 45 | 43 | 0 | 0 | -2
ABILENE | 0982-07-013 | HASKELL | FM 1720 | 2023-11-30 | 9371183.62 | 133199.66 | 0 | 8989553.48 | -381630.14 | 588 | 593 | 18 | 0 | 5
EL PASO | 0924-06-649 | EL PASO | VA | 2023-11-30 | 485120 | 51698.15 | 0 | 529583.15 | 44463.15 | 105 | 117 | 8 | 0 | 12
PARIS | 0045-11-044 | LAMAR | US 82 | 2023-11-30 | 1751101 | 16799.69 | 0 | 1792897.89 | 41796.89 | 79 | 74 | 0 | 0 | -5
SAN ANTONIO | 0100-03-086 | WILSON | US 181 | 2023-11-30 | 4783311.04 | 0 | 0 | 4435985.12 | -347325.92 | 192 | 87 | 0 | 0 | -105
AMARILLO | 0030-01-035 | OCHILTREE | US 83 | 2023-12-01 | 5571551.15 | 531729.15 | 0 | 6528088.3 | 956537.15 | 83 | 76 | 5 | 0 | -7
AUSTIN | 2211-01-026 | WILLIAMSON | RM 2338 | 2023-12-01 | 7570067.83 | 383964.08 | 0 | 8134925.6 | 564857.77 | 171 | 227 | 0 | 0 | 56
CHILDRESS | 0133-03-047 | KNOX | US 82 | 2023-12-01 | 2268300 | 97807.38 | 0 | 2366107.4 | 97807.4 | 240 | 381 | 146 | 0 | 141
DALLAS | 0581-02-151 | DALLAS | SL 12 | 2023-12-01 | 4659680.71 | 714945.57 | 0 | 4818244.23 | 158563.52 | 106 | 113 | 10 | 0 | 7
EL PASO | 0001-03-058 | EL PASO | SH 20 | 2023-12-01 | 3024946.56 | 132459.26 | 0 | 3469570.84 | 444624.28 | 280 | 275 | 25 | 0 | -5
EL PASO | 0002-06-059 | HUDSPETH | IH 10 | 2023-12-01 | 3140241 | 107501 | 6854.6 | 3191289 | 44193.4 | 220 | 204 | 0 | 0 | -16
EL PASO | 2121-04-124 | EL PASO | IH 10 | 2023-12-01 | 1536929.63 | 0 | 0 | 1577953.5 | 41023.87 | 36 | 23 | 0 | 0 | -13
ODESSA | 1183-01-014 | REEVES | FM 2119 | 2023-12-04 | 62350992.24 | 2100732.43 | 0 | 60322906.84 | -2028085.4 | 664 | 650 | 0 | 0 | -14
WACO | 2311-01-044 | MCLENNAN | FM 3051 | 2023-12-04 | 1210047.16 | 21061.42 | 0 | 1193084.6 | -16962.56 | 30 | 29 | 0 | 0 | -1
WICHITA FALLS | 1837-01-014 | ARCHER | FM 1954 | 2023-12-04 | 5282463.13 | 50470.46 | 0 | 5280441.79 | -2021.34 | 187 | 265 | 0 | 0 | 78
HOUSTON | 0110-03-085 | MONTGOMERY | SH 75 | 2023-12-05 | 3455793.59 | 8550.67 | 0 | 3821728.29 | 365934.7 | 53 | 58 | 5 | 0 | 5
LUFKIN | 0911-00-113 | ANGELINA | Various | 2023-12-05 | 439626 | 380087.33 | 0 | 868110.83 | 428484.83 | 106 | 122 | 46 | 0 | 16
PHARR | 0038-04-069 | ZAPATA | US 83 | 2023-12-07 | 549124.05 | 24707.95 | 0 | 567388.29 | 18264.24 | 100 | 94 | 0 | 0 | -6
ABILENE | 0034-02-050 | TAYLOR | US 83 | 2023-12-11 | 1760153.98 | -896 | 0 | 1841744.02 | 81590.04 | 56 | 29 | 0 | 0 | -27
BEAUMONT | 0932-01-090 | JEFFERSON | FM 365 | 2023-12-11 | 14655685.45 | 2116882.98 | 0 | 17086458.45 | 2430773 | 472 | 609 | 168 | 0 | 137
CORPUS CHRISTI | 0372-03-010 | SAN PATRICIO | BU 77T | 2023-12-11 | 777278.6 | 52970 | 0 | 817522.17 | 40243.57 | 58 | 63 | 12 | 0 | 5
CORPUS CHRISTI | 0447-05-075 | REFUGIO | FM 774 | 2023-12-11 | 2846446.81 | 0 | 0 | 2747123.47 | -99323.34 | 131 | 328 | 16 | 0 | 197
LAREDO | 0922-33-194 | WEBB | CR | 2023-12-11 | 1492184 | -21026.85 | 0 | 1471525.03 | -20658.97 | 78 | 68 | 0 | 0 | -10
FORT WORTH | 0902-90-057 | TARRANT | CS | 2023-12-12 | 1420252 | 18634.55 | 111856.09 | 1429370.31 | -102737.78 | 128 | 141 | 27 | 0 | 13
AUSTIN | 0016-01-133 | TRAVIS | SL 275 | 2023-12-13 | 1318917.45 | 104322.34 | 0 | 1552155.69 | 233238.24 | 118 | 107 | 0 | 0 | -11
AUSTIN | 0152-01-080 | TRAVIS | US 183 | 2023-12-13 | 2851509.1 | 3310.72 | 0 | 3353362.08 | 501852.98 | 180 | 210 | 21 | 0 | 30
AUSTIN | 0265-04-062 | BASTROP | SH 21 | 2023-12-13 | 50359853.46 | 1277736.87 | 0 | 53370091.19 | 3010237.73 | 785 | 913 | 128 | 0 | 128
BEAUMONT | 0920-13-036 | TYLER | CR | 2023-12-13 | 659766 | -45210 | 0 | 629815 | -29951 | 66 | 50 | 0 | 0 | -16
DALLAS | 0918-47-250 | DALLAS | CS | 2023-12-13 | 1403403.9 | 0 | 0 | 1347340.84 | -56063.06 | 300 | 269 | 0 | 0 | -31
HOUSTON | 0051-02-101 | HARRIS | SH 3 | 2023-12-13 | 13951959.6 | 18102.37 | 0 | 14445858.62 | 493899.02 | 600 | 626 | 22 | 0 | 26
WACO | 0209-01-073 | MCLENNAN | SL 2 | 2023-12-13 | 2132685.6 | 716752 | 0 | 2880742.24 | 748056.64 | 120 | 138 | 12 | 0 | 18
WACO | 0231-02-062 | CORYELL | BU 190E | 2023-12-13 | 4762516.85 | -275566.01 | 0 | 4213413.81 | -549103.04 | 300 | 410 | 44 | 0 | 110
WACO | 0258-08-037 | MCLENNAN | SH 6 | 2023-12-13 | 770035.18 | 11145.27 | 0 | 784545.97 | 14510.79 | 60 | 83 | 2 | 0 | 23
WICHITA FALLS | 0903-15-084 | COOKE | CR | 2023-12-13 | 2136179.06 | 0 | 0 | 2092198.84 | -43980.22 | 246 | 385 | 0 | 0 | 139
DALLAS | 1567-01-042 | DENTON | FM 720 | 2023-12-14 | 2648123.85 | 102361.46 | 0 | 2808996.51 | 160872.66 | 119 | 110 | 0 | 0 | -9
CORPUS CHRISTI | 0359-02-005 | GOLIAD | SH 119 | 2023-12-15 | 9793592.86 | 110496.26 | 0 | 10064229.33 | 270636.47 | 298 | 320 | 22 | 0 | 22
DALLAS | 0048-03-050 | ELLIS | US 77 | 2023-12-15 | 21683270.74 | 1037749.93 | 91256.61 | 22184888.59 | 410361.24 | 603 | 848 | 0 | 0 | 245
DALLAS | 0172-05-125 | ELLIS | US 287 | 2023-12-15 | 2840168.14 | 50647.68 | 0 | 2786604.36 | -53563.78 | 375 | 250 | 0 | 0 | -125
EL PASO | 2552-03-059 | EL PASO | SL 375 | 2023-12-15 | 1991402.25 | -25425.85 | 0 | 2009709.17 | 18306.92 | 32 | 35 | 5 | 0 | 3
LAREDO | 0018-06-211 | WEBB | IH 35 | 2023-12-15 | 402429.75 | 9879.98 | 0 | 402062.67 | -367.08 | 83 | 94 | 13 | 0 | 11
DALLAS | 0280-03-004 | COLLIN | BS 78-D | 2023-12-18 | 9596783.18 | 339762.57 | 0 | 9413913.73 | -182869.45 | 504 | 497 | 0 | 0 | -7
SAN ANTONIO | 0301-03-027 | FRIO | SH 85 | 2023-12-18 | 18027137.64 | -2210070.57 | 0 | 15894124.77 | -2133012.87 | 421 | 418 | -1 | 0 | -3
YOAKUM | 1090-05-018 | CALHOUN | FM 1593 | 2023-12-18 | 4811547.64 | -105208 | 0 | 4605789.9 | -205757.74 | 105 | 75 | 0 | 0 | -30
HOUSTON | 0050-09-095 | HARRIS | US 290 | 2023-12-20 | 1648298.34 | 1076842.47 | 0 | 2738107.27 | 1089808.93 | 135 | 135 | 0 | 0 | 0
LAREDO | 0018-04-063 | WEBB | IH 35 | 2023-12-20 | 11076278.32 | 416188.3 | 0 | 12085548.14 | 1009269.82 | 268 | 223 | 0 | 0 | -45
LUBBOCK | 0052-02-038 | BAILEY | US 70 | 2023-12-20 | 1422921.54 | 0 | 0 | 1374858.81 | -48062.73 | 12 | 12 | 0 | 0 | 0
LUBBOCK | 0052-05-047 | LAMB | US 84 | 2023-12-20 | 2196605.1 | 0 | 0 | 2216757.6 | 20152.5 | 167 | 128 | 0 | 0 | -39
LUBBOCK | 0783-01-107 | LUBBOCK | SL 289 | 2023-12-20 | 2477822 | -82575 | 0 | 2324816.43 | -153005.57 | 124 | 39 | 0 | 0 | -85
LUFKIN | 0809-04-057 | SAN AUGUSTINE | US 96 | 2023-12-20 | 3768563.09 | 310181.99 | 0 | 4105390.72 | 336827.63 | 102 | 171 | 66 | 0 | 69
PHARR | 0329-01-023 | JIM HOGG | FM 649 | 2023-12-20 | 3295335.75 | 0 | 0 | 3362174.21 | 66838.46 | 68 | 43 | 0 | 0 | -25
WACO | 0909-22-195 | MCLENNAN | Various | 2023-12-20 | 258695 | 6184.89 | 0 | 280470.7 | 21775.7 | 15 | 16 | 1 | 0 | 1
DALLAS | 0995-01-026 | NAVARRO | FM 637 | 2023-12-21 | 2712401.6 | 4850.3 | 0 | 2517853.28 | -194548.32 | 331 | 322 | 0 | 0 | -9
EL PASO | 0167-01-113 | EL PASO | US 54 | 2023-12-21 | 91166598.4 | 13306139.8 | 46745.62 | 111420129.92 | 20206785.9 | 722 | 1044 | 322 | 0 | 322
SAN ANTONIO | 0017-03-066 | BEXAR | IH 35 | 2023-12-21 | 319940 | 0 | 0 | 319710 | -230 | 62 | 36 | 0 | 0 | -26
WICHITA FALLS | 0249-03-055 | ARCHER | US 281 | 2023-12-21 | 10600584.04 | 0 | 0 | 10906347.55 | 305763.51 | 60 | 59 | 0 | 0 | -1
AUSTIN | 1535-01-015 | TRAVIS | FM 1625 | 2023-12-22 | 755872 | 451937.34 | 0 | 1216488.02 | 460616.02 | 16 | 16 | 16 | 0 | 0
BEAUMONT | 0368-04-033 | JEFFERSON | SH 124 | 2023-12-22 | 2659519.15 | 65196.78 | 0 | 2807982.45 | 148463.3 | 134 | 131 | 10 | 0 | -3
DALLAS | 0197-03-076 | KAUFMAN | US 175 | 2023-12-22 | 1587185.65 | -10611.46 | 0 | 1637031.54 | 49845.89 | 160 | 206 | 3 | 0 | 46
PHARR | 0921-02-445 | HIDALGO | CR | 2023-12-22 | 1554168.79 | 2246.16 | 0 | 1523851.02 | -30317.77 | 248 | 126 | 0 | 0 | -122
SAN ANGELO | 0035-03-054 | CONCHO | US 83 | 2023-12-22 | 16983573.32 | -87425.88 | 0 | 17244988.6 | 261415.28 | 72 | 68 | 0 | 0 | -4
WACO | 0015-01-252 | MCLENNAN | IH 35 | 2023-12-22 | 1969296.39 | -286187.9 | 0 | 1605401.14 | -363895.25 | 60 | 51 | 0 | 0 | -9
BEAUMONT | 0920-13-037 | TYLER | CR | 2023-12-27 | 746699.95 | 67750.01 | 0 | 835048.51 | 88348.56 | 60 | 109 | 4 | 0 | 49
BRYAN | 0315-05-026 | BRAZOS | SH 105 | 2023-12-27 | 23601410.92 | 10148535.65 | 0 | 33820093.8 | 10218682.88 | 443 | 893 | 458 | 0 | 450
HOUSTON | 0720-03-137 | HARRIS | SH 249 | 2023-12-27 | 2179891.9 | 312575.56 | 0 | 2629269.21 | 449377.31 | 284 | 275 | 0 | 0 | -9
WACO | 0093-05-053 | LIMESTONE | SH 14 | 2023-12-27 | 202509.15 | 0 | 0 | 199009.15 | -3500 | 30 | 39 | 0 | 0 | 9
AMARILLO | 0238-02-038 | HARTLEY | US 54 | 2023-12-28 | 35223786.9 | 1660204.64 | 0 | 39864465.5 | 4640678.6 | 465 | 640 | 36 | 0 | 175
AUSTIN | 0337-03-019 | WILLIAMSON | FM 1331 | 2023-12-28 | 173551.29 | 29625.22 | 0 | 203494.39 | 29943.1 | 43 | 24 | 0 | 0 | -19
BRYAN | 0456-01-047 | FREESTONE | FM 27 | 2023-12-28 | 14892846.02 | 81036.34 | 0 | 15250519.84 | 357673.82 | 330 | 456 | 72 | 0 | 126
TYLER | 0138-02-038 | RUSK | SH 42 | 2023-12-28 | 1527949.3 | 0 | 0 | 1599584.21 | 71634.91 | 24 | 22 | 0 | 0 | -2
TYLER | 0910-16-165 | SMITH | CS | 2023-12-28 | 233589 | 0 | 0 | 223177.95 | -10411.05 | 34 | 29 | 0 | 0 | -5
WACO | 0909-28-035 | BOSQUE | CR | 2023-12-28 | 799353.2 | 0 | 0 | 816263.4 | 16910.2 | 90 | 90 | 0 | 0 | 0
BROWNWOOD | 0923-06-086 | BROWN | CR | 2023-12-29 | 1592990.5 | -60 | 0 | 1595930.31 | 2939.81 | 148 | 139 | 0 | 0 | -9
DALLAS | 0095-03-107 | KAUFMAN | US 80 | 2023-12-29 | 21784893.28 | 593746.44 | 0 | 21326722.5 | -458170.78 | 248 | 245 | 0 | 0 | -3
DALLAS | 0918-46-330 | DENTON | Various | 2023-12-29 | 1094339 | 36303.21 | 0 | 1163304.44 | 68965.44 | 182 | 180 | 0 | 0 | -2
EL PASO | 0001-01-063 | EL PASO | SH 20 | 2023-12-29 | 2433661.19 | 182409.29 | 0 | 2512609.6 | 78948.41 | 193 | 215 | 22 | 0 | 22
SAN ANTONIO | 0915-00-200 | BEXAR | VA | 2023-12-29 | 477879.25 | 10631.25 | 0 | 508876.73 | 30997.48 | 144 | 181 | 30 | 0 | 37
ATLANTA | 0218-03-087 | CASS | US 59 | 2024-01-02 | 7622162.45 | 45143.28 | 0 | 7201695.02 | -420467.43 | 89 | 82 | 2 | 0 | -7
ATLANTA | 0218-04-119 | CASS | US 59 | 2024-01-02 | 11842462.04 | 0 | 0 | 10999681.75 | -842780.29 | 136 | 103 | 0 | 0 | -33
BRYAN | 1145-01-044 | LEON | FM 1511 | 2024-01-02 | 2035077.89 | -48180.33 | 0 | 1930988.99 | -104088.9 | 320 | 374 | 0 | 0 | 54
ODESSA | 0887-01-039 | MIDLAND | FM 307 | 2024-01-02 | 4744172.07 | 420977.71 | 0 | 5612068.89 | 867896.82 | 241 | 385 | 125 | 0 | 144
LUBBOCK | 0052-03-030 | BAILEY | US 84 | 2024-01-03 | 19522385.4 | 42574.4 | 0 | 19120011.69 | -402373.71 | 61 | 61 | 0 | 0 | 0
LUFKIN | 0911-00-106 | ANGELINA | VA | 2024-01-03 | 4121118.8 | 42225 | 0 | 3770544.13 | -350574.67 | 203 | 329 | 48 | 0 | 126
YOAKUM | 0515-01-071 | JACKSON | FM 616 | 2024-01-03 | 3684181.71 | 0 | 0 | 3655428.04 | -28753.67 | 180 | 102 | 0 | 0 | -78
AUSTIN | 0265-05-089 | BASTROP | SH 71 | 2024-01-04 | 1108815.55 | 0 | 0 | 1005384.26 | -103431.29 | 57 | 31 | 0 | 0 | -26
AUSTIN | 0573-01-041 | BASTROP | SH 304 | 2024-01-05 | 2515580.84 | 20675.52 | 0 | 2613826.25 | 98245.41 | 61 | 61 | 6 | 0 | 0
PHARR | 0684-03-022 | CAMERON | FM 1732 | 2024-01-05 | 6603453.6 | 221692.69 | 0 | 6888444.79 | 284991.19 | 350 | 342 | 0 | 0 | -8
SAN ANTONIO | 0915-00-234 | BEXAR | VA | 2024-01-05 | 1384853.99 | 85264.97 | 0 | 1406273.04 | 21419.05 | 152 | 139 | 0 | 0 | -13
ATLANTA | 0919-00-084 | CASS | Various | 2024-01-08 | 1889109.54 | 0 | 0 | 1933438.55 | 44329.01 | 66 | 98 | 0 | 0 | 32
LAREDO | 0022-06-052 | VAL VERDE | US 90 | 2024-01-09 | 6003079.86 | 77842.3 | 0 | 6444400.33 | 441320.47 | 110 | 104 | 0 | 0 | -6
SAN ANTONIO | 0024-04-068 | MEDINA | US 90 | 2024-01-09 | 3156212.6 | -67992.1 | 0 | 3044679.29 | -111533.31 | 68 | 67 | 0 | 0 | -1
ATLANTA | 0218-04-126 | CASS | US 59 | 2024-01-10 | 2198711.21 | -106028.79 | 0 | 2397049.12 | 198337.91 | 70 | 105 | 38 | 0 | 35
BEAUMONT | 0593-01-130 | LIBERTY | SH 105 | 2024-01-10 | 856006.94 | 48034.23 | 0 | 992763.85 | 136756.91 | 61 | 68 | 7 | 0 | 7
AUSTIN | 0286-01-061 | HAYS | SH 21 | 2024-01-11 | 1208195.86 | 274583.17 | 0 | 1555034.88 | 346839.02 | 40 | 32 | 0 | 0 | -8
AUSTIN | 0337-01-043 | WILLIAMSON | SH 29 | 2024-01-11 | 5548287.93 | 1333964.46 | 0 | 6591287.34 | 1042999.41 | 419 | 427 | 8 | 0 | 8
AUSTIN | 0471-02-079 | HAYS | SH 21 | 2024-01-11 | 2808195.5 | -196946.56 | 0 | 2966053.66 | 157858.16 | 64 | 29 | 0 | 0 | -35
LUBBOCK | 0067-02-074 | SWISHER | IH 27 | 2024-01-11 | 16314227.44 | -185660 | 0 | 17434138.07 | 1119910.63 | 63 | 70 | 14 | 0 | 7
DALLAS | 0817-01-024 | DENTON | FM 428 | 2024-01-12 | 8828849.78 | 746791.1 | 0 | 8450115.15 | -378734.63 | 440 | 472 | 33 | 0 | 32
LUBBOCK | 0905-00-117 | LUBBOCK | Various | 2024-01-12 | 881211.8 | 0 | 0 | 937701.8 | 56490 | 90 | 46 | 0 | 0 | -44
AUSTIN | 0113-07-071 | HAYS | US 290 | 2024-01-16 | 714499.94 | -1085.29 | 0 | 708724.74 | -5775.2 | 31 | 10 | 0 | 0 | -21
AUSTIN | 0366-01-082 | HAYS | SL 82 | 2024-01-16 | 406670.13 | -137423 | 0 | 252115.11 | -154555.02 | 14 | 11 | 0 | 0 | -3
AUSTIN | 0285-03-062 | HAYS | RM 12 | 2024-01-17 | 5093342.85 | 111416.2 | 0 | 4917384.39 | -175958.46 | 175 | 158 | 0 | 0 | -17
EL PASO | 2552-02-035 | EL PASO | SL 375 | 2024-01-18 | 3808795.44 | 20840.16 | 0 | 3726782.45 | -82012.99 | 156 | 192 | 45 | 0 | 36
SAN ANTONIO | 0915-00-210 | BEXAR | VA | 2024-01-18 | 2758844.47 | 137347.47 | 0 | 2812057.87 | 53213.4 | 322 | 698 | 203 | 0 | 376
BROWNWOOD | 0079-01-038 | BROWN | US 67 | 2024-01-19 | 3046555.05 | 98117.64 | 0 | 3792895.24 | 746340.19 | 131 | 216 | 82 | 0 | 85
BROWNWOOD | 1780-01-009 | MILLS | FM 1047 | 2024-01-19 | 1685450.98 | -2071.24 | 0 | 1740617.96 | 55166.98 | 134 | 134 | 0 | 0 | 0
WACO | 0185-05-003 | BELL | US 190 | 2024-01-19 | 4600000 | 214542.34 | 0 | 5112035.94 | 512035.94 | 60 | 57 | 0 | 0 | -3
WICHITA FALLS | 0822-01-021 | COOKE | FM 371 | 2024-01-22 | 7175268.12 | 29881.84 | 0 | 7312761.67 | 137493.55 | 260 | 252 | 0 | 0 | -8
AUSTIN | 0914-05-174 | WILLIAMSON | CR | 2024-01-23 | 769807.3 | -29849.28 | 0 | 738845.28 | -30962.02 | 85 | 75 | 0 | 0 | -10
CORPUS CHRISTI | 0916-00-233 | NUECES | VA | 2024-01-23 | 8086089.5 | 512722.16 | 0 | 8047825.08 | -38264.42 | 168 | 264 | 96 | 0 | 96
FORT WORTH | 0362-07-009 | PALO PINTO | FM 2951 | 2024-01-23 | 4867458.16 | 409026.62 | 0 | 5239077.03 | 371618.87 | 256 | 455 | 139 | 0 | 199
HOUSTON | 0271-17-178 | HARRIS | IH 610 | 2024-01-23 | 1794234.32 | -161718.5 | 0 | 1230353.79 | -563880.53 | 90 | 87 | 0 | 0 | -3
BROWNWOOD | 0011-09-075 | STEPHENS | US 180 | 2024-01-24 | 14954532.77 | 145887.11 | 0 | 14175054.68 | -779478.09 | 105 | 119 | 16 | 0 | 14
CORPUS CHRISTI | 0088-01-069 | BEE | US 59 | 2024-01-24 | 15920070.97 | 536951.88 | 0 | 16418463.54 | 498392.57 | 204 | 358 | 42 | 0 | 154
CORPUS CHRISTI | 0100-05-184 | KARNES | US 181 | 2024-01-24 | 6543322.7 | 592247.26 | 243000 | 7139803.73 | 353481.03 | 210 | 569 | 359 | 0 | 359
EL PASO | 0358-05-018 | BREWSTER | SH 118 | 2024-01-24 | 5327450.03 | 498911.76 | 0 | 6010586.85 | 683136.82 | 40 | 69 | 11 | 0 | 29
EL PASO | 0415-03-022 | JEFF DAVIS | SH 166 | 2024-01-24 | 9596240.05 | 757712.4 | 0 | 10278115.35 | 681875.3 | 60 | 78 | 20 | 0 | 18
EL PASO | 1046-01-030 | EL PASO | FM 659 | 2024-01-24 | 12904066.05 | 253763.17 | -185023.4 | 13322805.55 | 603762.9 | 377 | 684 | 169 | 0 | 307
LAREDO | 0161-03-024 | VAL VERDE | SS 239 | 2024-01-24 | 1703783.37 | 291357.17 | 0 | 1935196.32 | 231412.95 | 160 | 177 | 18 | 0 | 17
FORT WORTH | 0172-06-094 | TARRANT | SS 280 | 2024-01-25 | 2609024.16 | 682942.04 | 0 | 3468390.68 | 859366.52 | 235 | 343 | 124 | 0 | 108
LAREDO | 0300-01-105 | MAVERICK | US 277 | 2024-01-25 | 5512871.65 | -108567.48 | 0 | 5485457.03 | -27414.62 | 274 | 274 | 0 | 0 | 0
SAN ANTONIO | 0521-04-294 | BEXAR | IH 410 | 2024-01-25 | 315680 | 0 | 0 | 321310.91 | 5630.91 | 32 | 7 | 0 | 0 | -25
EL PASO | 0924-06-643 | EL PASO | CS | 2024-01-26 | 494880 | 0 | 0 | 490010 | -4870 | 80 | 26 | 0 | 0 | -54
HOUSTON | 0089-09-067 | FORT BEND | US 59 | 2024-01-26 | 37743798.55 | 368715.81 | 0 | 38141042.32 | 397243.77 | 1208 | 1445 | 240 | 0 | 237
HOUSTON | 1685-05-116 | HARRIS | SH 6 | 2024-01-26 | 8982210.95 | -359626.29 | 0 | 8281906.98 | -700303.97 | 224 | 204 | 0 | 0 | -20
ATLANTA | 3403-01-001 | CAMP | SL 255 | 2024-01-29 | 5634658.36 | 1485137.02 | 0 | 7358605.68 | 1723947.32 | 334 | 404 | 96 | 0 | 70
AUSTIN | 0151-03-042 | WILLIAMSON | SH 29 | 2024-01-30 | 3739221.06 | 0 | 0 | 3575759.01 | -163462.05 | 64 | 34 | 0 | 0 | -30
WACO | 0014-24-065 | HILL | IH 35 | 2024-01-30 | 6648201.5 | 146840.04 | 0 | 6819582.81 | 171381.31 | 128 | 74 | 0 | 0 | -54
LUFKIN | 0109-08-050 | TRINITY | SH 19 | 2024-01-31 | 599425.61 | 22628 | 0 | 635216.54 | 35790.93 | 73 | 45 | 0 | 0 | -28
BRYAN | 0955-01-027 | BURLESON | FM 166 | 2024-02-01 | 1378418 | 198091.34 | 0 | 1683762.09 | 305344.09 | 117 | 143 | 26 | 0 | 26
DALLAS | 0815-03-015 | DENTON | FM 424 | 2024-02-01 | 2064269.71 | 1525.8 | 0 | 2128898.68 | 64628.97 | 116 | 57 | 0 | 0 | -59
ODESSA | 0556-04-012 | PECOS | SH 349 | 2024-02-01 | 8865264.42 | 7220 | 0 | 9001870.74 | 136606.32 | 54 | 47 | 0 | 0 | -7
BEAUMONT | 0028-07-058 | JEFFERSON | US 90 | 2024-02-02 | 753374.01 | 26169.72 | 0 | 882765.41 | 129391.4 | 102 | 111 | 15 | 0 | 9
BROWNWOOD | 2570-01-011 | BROWN | FM 2632 | 2024-02-02 | 3196924.07 | 6991.94 | 0 | 3049508.02 | -147416.05 | 150 | 178 | 0 | 0 | 28
YOAKUM | 0446-04-014 | COLORADO | FM 1093 | 2024-02-02 | 5576114.35 | 0 | 0 | 5518436.48 | -57677.87 | 255 | 238 | 0 | 0 | -17
WACO | 1926-01-018 | CORYELL | FM 1829 | 2024-02-05 | 5068817.28 | 0 | 0 | 4713928.62 | -354888.66 | 60 | 26 | 0 | 0 | -34
TYLER | 0910-00-115 | SMITH | VA | 2024-02-06 | 2493889.72 | 405085.5 | 0 | 2714562.4 | 220672.68 | 66 | 123 | 24 | 0 | 57
AMARILLO | 0379-01-046 | HUTCHINSON | SH 136 | 2024-02-07 | 9504385.15 | -437441.6 | 0 | 9209653.74 | -294731.41 | 154 | 179 | 32 | 0 | 25
HOUSTON | 0508-01-354 | HARRIS | IH 10 | 2024-02-07 | 5653887.52 | 450971.04 | 0 | 6915461.22 | 1261573.7 | 254 | 252 | 0 | 0 | -2
AUSTIN | 0914-00-474 | TRAVIS | Various | 2024-02-08 | 124791.94 | 0 | 0 | 159779.68 | 34987.74 | 38 | 23 | 0 | 0 | -15
BROWNWOOD | 0007-03-109 | EASTLAND | IH 20 | 2024-02-08 | 8087544 | -294.5 | 0 | 8035110.03 | -52433.97 | 68 | 74 | 6 | 0 | 6
TYLER | 2274-01-011 | WOOD | FM 1804 | 2024-02-08 | 634567.65 | 0 | 0 | 587878.48 | -46689.17 | 57 | 59 | 0 | 0 | 2
WICHITA FALLS | 0156-05-064 | ARCHER | BU 82F | 2024-02-08 | 1786206.5 | 0 | 0 | 1866435.55 | 80229.05 | 85 | 77 | 0 | 0 | -8
YOAKUM | 2350-01-069 | VICTORIA | SL 463 | 2024-02-08 | 642089.92 | 0 | 0 | 661991.34 | 19901.42 | 55 | 60 | 0 | 0 | 5
ABILENE | 2034-01-013 | SCURRY | FM 1298 | 2024-02-09 | 1393947.05 | 17490 | 0 | 1402628.4 | 8681.35 | 80 | 80 | 0 | 0 | 0
AUSTIN | 2690-01-036 | WILLIAMSON | FM 971 | 2024-02-09 | 8428384.67 | 1133078.02 | 0 | 9807894.1 | 1379509.43 | 410 | 312 | 0 | 0 | -98
AUSTIN | 0805-04-035 | HAYS | RM 150 | 2024-02-12 | 482719.59 | 158003.75 | 0 | 594171.57 | 111451.98 | 17 | 14 | 0 | 0 | -3
WICHITA FALLS | 0903-06-026 | CLAY | CR | 2024-02-12 | 815142.41 | 0 | 0 | 825879.08 | 10736.67 | 153 | 54 | 0 | 0 | -99
AUSTIN | 1566-02-023 | WILLIAMSON | FM 1660 | 2024-02-13 | 1092800.16 | 0 | 0 | 1132903.03 | 40102.87 | 56 | 53 | 0 | 0 | -3
BROWNWOOD | 0182-01-017 | EASTLAND | SH 36 | 2024-02-13 | 2098184.02 | 325614.74 | 0 | 3249082.4 | 1150898.38 | 176 | 165 | 33 | 0 | -11
BROWNWOOD | 0183-01-053 | COMANCHE | SH 36 | 2024-02-13 | 1557595.5 | 98094.63 | 0 | 1585276.41 | 27680.91 | 114 | 125 | 16 | 0 | 11
HOUSTON | 0502-01-222 | HARRIS | SH 225 | 2024-02-13 | 1710939.65 | 709092.94 | 0 | 2668148.97 | 957209.32 | 165 | 337 | 138 | 0 | 172
LUBBOCK | 0053-06-031 | GARZA | US 84 | 2024-02-13 | 1791545.6 | 96595 | 0 | 1930713.78 | 139168.18 | 175 | 140 | 0 | 0 | -35
ABILENE | 0068-08-063 | HOWARD | BU 87M | 2024-02-15 | 6169362.05 | 0 | 0 | 6431626.13 | 262264.08 | 72 | 56 | 0 | 0 | -16
BEAUMONT | 0028-09-123 | ORANGE | IH 10 | 2024-02-16 | 15248084.1 | -251903 | 0 | 14298872.52 | -949211.58 | 75 | 58 | 0 | 0 | -17
CHILDRESS | 0133-03-038 | KNOX | US 82 | 2024-02-16 | 12684227.53 | 71777.2 | 0 | 13176888.4 | 492660.87 | 320 | 523 | 46 | 0 | 203
HOUSTON | 0114-11-079 | WALLER | US 290 | 2024-02-16 | 1227770 | 39247.11 | 0 | 1337297.86 | 109527.86 | 51 | 47 | 0 | 0 | -4
PHARR | 0039-12-252 | CAMERON | BU 77-X | 2024-02-16 | 3330767.38 | 58858.5 | 0 | 3421708.81 | 90941.43 | 263 | 345 | 82 | 0 | 82
WACO | 0258-08-038 | MCLENNAN | SH 6 | 2024-02-16 | 723086 | 51574.4 | 0 | 695966.75 | -27119.25 | 60 | 55 | 0 | 0 | -5
AUSTIN | 0015-13-396 | TRAVIS | IH 35 | 2024-02-19 | 24590929.4 | 4410874.61 | 0 | 29737811.19 | 5146881.79 | 376 | 561 | 187 | 0 | 185
ATLANTA | 0248-01-081 | TITUS | US 271 | 2024-02-20 | 5186944.38 | 467827.93 | 0 | 5465745.77 | 278801.39 | 72 | 101 | 15 | 0 | 29
AUSTIN | 1234-02-013 | BASTROP | FM 1100 | 2024-02-20 | 468554.78 | 68389.73 | 0 | 557639.93 | 89085.15 | 27 | 8 | 0 | 0 | -19
LUFKIN | 0911-38-075 | ANGELINA | Various | 2024-02-20 | 200685 | 0 | 0 | 200669 | -16 | 24 | 7 | 0 | 0 | -17
PARIS | 0901-19-205 | GRAYSON | CS | 2024-02-20 | 3051415.5 | 166165.93 | 0 | 3278519.17 | 227103.67 | 160 | 156 | 10 | 0 | -4
WACO | 0513-01-017 | CORYELL | SH 236 | 2024-02-20 | 5087623.2 | 103206.04 | 0 | 5208581.05 | 120957.85 | 165 | 170 | 15 | 0 | 5
DALLAS | 2461-01-010 | COLLIN | FM 2170 | 2024-02-21 | 3061581.78 | 10515.64 | 0 | 2766840.55 | -294741.23 | 132 | 109 | 0 | 0 | -23
DALLAS | 2982-01-007 | KAUFMAN | FM 1390 | 2024-02-22 | 7598568.1 | 567242.45 | 0 | 7949452.41 | 350884.31 | 253 | 376 | 73 | 0 | 123
WACO | 0909-39-134 | CORYELL | CR | 2024-02-22 | 673333 | 4031.14 | 0 | 671713.88 | -1619.12 | 75 | 78 | 0 | 0 | 3
WACO | 2038-01-031 | BELL | FM 2115 | 2024-02-22 | 7148926.49 | 251153.08 | 0 | 7020327.63 | -128598.86 | 105 | 199 | 83 | 0 | 94
ATLANTA | 0330-01-033 | BOWIE | SH 98 | 2024-02-23 | 3919948.8 | 454169.88 | 0 | 4509125.17 | 589176.37 | 287 | 311 | 6 | 0 | 24
CORPUS CHRISTI | 0916-26-021 | GOLIAD | CR | 2024-02-23 | 643104.49 | 0 | 0 | 645666.04 | 2561.55 | 77 | 77 | 0 | 0 | 0
FORT WORTH | 0080-04-100 | HOOD | US 377 | 2024-02-23 | 4495837.2 | -293546.6 | 0 | 4301450.24 | -194386.96 | 48 | 29 | 0 | 0 | -19
LAREDO | 0023-02-044 | KINNEY | US 90 | 2024-02-23 | 8058700.93 | -321538.25 | 0 | 7764999.92 | -293701.01 | 120 | 94 | 0 | 0 | -26
LUFKIN | 0064-04-045 | SAN AUGUSTINE | SH 21 | 2024-02-23 | 10737998.85 | 1000 | 0 | 10344025.06 | -393973.79 | 133 | 115 | 0 | 0 | -18
LUFKIN | 3248-01-007 | NACOGDOCHES | FM 1878 | 2024-02-23 | 5498351.51 | 75424.89 | 0 | 5368052.96 | -130298.55 | 228 | 131 | 0 | 0 | -97
FORT WORTH | 0250-01-038 | PALO PINTO | US 281 | 2024-02-26 | 201204.53 | 0 | 0 | 205839.52 | 4634.99 | 40 | 40 | 0 | 0 | 0
FORT WORTH | 0902-00-314 | TARRANT | VA | 2024-02-26 | 2816506.12 | 180013.16 | 0 | 3001455.87 | 184949.75 | 360 | 235 | 0 | 0 | -125
WACO | 0055-15-067 | MCLENNAN | US 84 | 2024-02-26 | 2174993.18 | 130390.92 | 0 | 2258382.58 | 83389.4 | 105 | 85 | 0 | 0 | -20
DALLAS | 2250-02-020 | DENTON | SL 288 | 2024-02-27 | 1362510.85 | 0 | 0 | 1326983.74 | -35527.11 | 98 | 96 | 0 | 0 | -2
SAN ANTONIO | 0521-02-042 | BEXAR | SL 13 | 2024-02-27 | 6683653.51 | 26708.4 | 0 | 7137334.34 | 453680.83 | 207 | 217 | 10 | 0 | 10
TYLER | 0927-01-030 | SMITH | FM 344 | 2024-02-27 | 1833547.83 | 206112.4 | 0 | 1955892.31 | 122344.48 | 195 | 195 | 0 | 0 | 0
YOAKUM | 0027-03-073 | COLORADO | FM 102 | 2024-02-27 | 3987940.97 | -217154.81 | 0 | 4030810.66 | 42869.69 | 120 | 108 | 0 | 0 | -12
YOAKUM | 0913-09-076 | WHARTON | CR | 2024-02-27 | 670423.18 | 0 | 0 | 663453.7 | -6969.48 | 120 | 85 | 0 | 0 | -35
YOAKUM | 0913-18-033 | JACKSON | CR | 2024-02-27 | 1898927.97 | 0 | 0 | 1882212.05 | -16715.92 | 189 | 119 | 0 | 0 | -70
YOAKUM | 1090-04-016 | JACKSON | FM 1593 | 2024-02-27 | 4530158.95 | -817250.3 | 0 | 3317080.85 | -1213078.1 | 90 | 26 | 0 | 0 | -64
ATLANTA | 0063-03-065 | PANOLA | US 59 | 2024-02-28 | 8864785.93 | 60338.54 | 0 | 8817431.02 | -47354.91 | 503 | 504 | 7 | 0 | 1
ATLANTA | 0495-08-136 | HARRISON | IH 20 | 2024-02-29 | 11381826 | -139693.15 | 0 | 11752052.23 | 370226.23 | 131 | 168 | 0 | 0 | 37
AUSTIN | 1754-02-029 | HAYS | RM 1826 | 2024-02-29 | 1052438.7 | 0 | 0 | 1138964.05 | 86525.35 | 25 | 9 | 0 | 0 | -16
EL PASO | 0924-00-130 | EL PASO | Various | 2024-02-29 | 1135875 | 5671.97 | 0 | 1165301.97 | 29426.97 | 120 | 108 | 7 | 0 | -12
FORT WORTH | 0008-12-095 | TARRANT | IH 20 | 2024-02-29 | 1729558.35 | 0 | 0 | 1729558.35 | 0 | 86 | 410 | 132 | 0 | 324
TYLER | 0910-00-134 | SMITH | Various | 2024-02-29 | 470054.6 | 18108 | 0 | 540692.56 | 70637.96 | 63 | 23 | 0 | 0 | -40